## Sheet1
Work Plan for CREAM
Last updated: 10-Feb-2011
Note 1: | FTE days assume someone really can spend a full day: it is not a calendar day.
Phase 1: Initial Early Testing Release
| Requirements from ATLAS, with concrete tasks | % Done | Est. effort (FTE days) | Deadline | Depends on | Who does task? | Comments
1 | Requirement: Provide CREAM CE as a Pacman-based installation
1.1 | Build CREAM and BLAH from source & package | 100 | 5 | Done |  | VDT
1.2 | Write configuration scripts for CREAM and BLAH | 100 | 5 | Done | 1.1 | VDT
1.3 | Build new version of glexec from source & package | 100 | 10 | Done |  | VDT
1.4 | Update glexec configuration | 100 | 1 | Done | 1.3 | VDT
1.5 | Internal testing and debugging (Succesfully run 1-10 jobs with CREAM) | 25 | 5 | 2011-03-04 | 1.2, 1.4 | Suchandra, Alain | Suchandra started on Feb 10, getting up to speed
1.6 | Verify OSG environment (variables, files, etc…) are properly set up/accessible | 0 | 5 | 2011-03-04 | 1.5 | Suchandra, Alain
2 | Requirement: Integrate CREAM CE with our gridmap/VO-map authorization
2.1 | Create user sandboxes based on user configuration | 0 | 3 | 2011-03-04 |  | Suchandra, Alain
2.2 | Internal testing and debugging | 0 | 5 | 2011-03-04 | 1 | Suchandra, Alain
3 | Requirement: Upgrade VDT to use version of Condor suitable for working with CREAM.
3.1 | Upgrade Condor in VDT to 7.5.5 or later, including configuration changes | 0 | 1 | 2011-03-11 |  | Scot
3.2 | Provide tool to create LSC files | 50 | 1 | 2011-03-11 |  | Scot
3.2 | Internal testing and debugging | 0 | 1 | 2011-03-11 | 1,2 | Scot
4 | Requirement: Update configuration tools (configure-osg) to work with CREAM.
4.1 | Update configure-osg to call configure_cream and configure_blah | 0 | 1 | 2011-03-11 | 1.2,2.1 | Suchandra
4.2 | Internal testing and debugging | 0 | 1 | 2011-03-11 | 4.1 | Suchandra
5 | Requirement: Provide to ATLAS as test release
5.1 | Cut release | 0 | 1 | 2011-03-15 | 1,2,3,4 | Scot
Phase 2: Second Release (Limited production use in ATLAS)
6 | Requirement: Provide CREAM command-line client
6.1 | Build CREAM client from source and package | 0 | 5 | 2011-04-22 |  | VDT
6.2 | Internal testing and debugging | 0 | 2 | 2011-04-22 | 6.1 | VDT
7 | Requirement: Provide CREAM CE as an RPM-based installation
7.1 | Instrument CREAM, BLAH, and glexec builds to make RPMs | 100 |  | 2011-04-22 | 1 | VDT
7.2 | Flesh out RPM work plan… Could be considerable work here | 0 | ??? | 2011-04-22 | 1 | VDT
7.3 | Internal testing and debugging | 0 | 5 | 2011-04-22 | 7.2 | VDT
8 | Requirement: Integrate CREAM CE with Gratia
8.1 | Update Gratia probes | 50 | 5 | 2011-04-22 |  | Gratia
8.2 | Patch CREAM to provide more information to Gratia?? (Unclear if needed) |  | 2 | 2011-04-22 |  | Gratia
8.3 | Internal testing and debugging | 0 | 2 | 2011-04-22 | 1, 2 | Gratia, VDT
9 | Requirement: Provide to ATLAS as limited production/broader test release
9.1 | Cut release | 0 | 1 | 2011-04-29 | 6, 7, 8 | VDT
Phase 3: Production Release
10 | Requirement: Integrate CREAM CE with our information system (GIP/CEmon...)
10.1 | Update GIP to work with CREAM | 100 | 5 | 2011-08-09 |  | GIP
10.2 | Internal testing and debugging | 25 | 2 | 2011-08-09 | 1,2,3,10.1 | GIP, VDT
11 | Requirement: Integrate CREAM CE with GUMS
11.1 | Write gJAF plugin to communicate with GUMS | 0 | 20 | 2011-08-09 | 1,3 | Unknown
11.2 | Internal testing and debugging | 0 | 10 | 2011-08-09 | 11.1 | Unknown
12 | Requirement: Via RSV, provide WLCG availability reporting and other testing.
12.1 | Extend RSV so it can submit jobs via Condor-G | 0 | 5 | 2011-08-09 | 1,2,3 | Unknown
12.2 | Update WLCG availability probes to submit via Condor-G | 0 | 3 | 2011-08-09 | 12.1 | Unknown
12.3 | GOC Work to modify WLCG availbility reporting (don't require GRAM availability) | 0 | 1 | 2011-08-09 | 12.1 | GOC
12.4 | Write CREAM availability metric | 0 | 2 | 2011-08-09 | 1,2,3 | Unknown
12.5 | Update other probes to submit via Condor-G | 0 | 6 | 2011-08-09 | 12.1 | Unknown
12.6 | Extend RSV so it can choose Globus vs. CREAM | 0 | 1 | 2011-08-09 | 12.1 | Unknown
12.7 | Internal testing and debugging | 0 | 3 | 2011-08-09 | 12.1-12.6 | Unknown
13 | Requirement: Provide documentation in the OSG release documentation
13.1 | Document installation and configuration of CREAM | 0 | 5 | 2011-08-23 |  | VDT+
13.2 | Document changes to RSV | 0 | 2 | 2011-08-23 |  | VDT+
14 | Requirement: Ensure CREAM is production-ready
14.1 | VTB testing | 0 | 5 | 2011-08-16 |  | VTB
14.2 | ITB testing | 0 | 30 | 2011-08-23 |  | ITB
14.3 | Release | 0 | 2 | 2011-09-20 |  | All