## Slide 1: 1.5 Engage Year 5

## Slide 2: Prior Year Challenges
staffing issues
  Rynge transition to ISI in Nov/Dec ’09
  new hire started 7/12/2010; new to Grid computing, but a fast learner
Campus Grids realizations
  Transitioning Clemson effort to virtualization and cloud technologies
    already being used STAR and for a particularly difficult to deploy BIO application (PolyPhen-2)

## Slide 3: RENCI new hire: Steve Cox
Comes to RENCI from the financial services industry
Led a team of developers developing an equity research and brokerage platform
Previously worked at Duke Clinical Research Institute in clinical informatics research software
Background includes data, networking, wireless and 3D software startups
Steve has worked most with Java, SOAP, SQL, JavaScript and a variety of Unix scripting environments
Initial tasks include:
  Engage Infrastructure ramp up
  User Engagement
  Setting up an OSG CE in front of RENCI’s flagship cluster
  GlideinWMS deployment for Engage

## Slide 4
WBS | Task | Start date | End date | Owners
1.5 | Engage |  |  | 
1.5.1 | User Engagement |  |  | 
1.5.1.1 | Engage 10 new users | 10/01/10 | 09/30/11 | McGee
1.5.1.2 | Continue MPI efforts across OSG | 10/01/10 | 09/30/11 | Thain
1.5.1.3 | Steffen Bass et al - thoughput and iRODS | 10/01/10 | 01/30/11 | McGee, S.Cox
1.5.2 | Engage Infrastructure |  |  | 
1.5.2.1 | Maintain existing infrastructure for existing users | 10/01/10 | 09/30/11 | McGee, S.Cox
1.5.2.2 | Investigate GlideinWMS as a replacement for OSGMM | 10/01/10 | 01/30/11 | S.Cox
1.5.2.3 | Support RENCI Science Portal as an OSG access mechanism | 10/01/10 | 09/30/11 | J.Reilly, S.Cox
1.5.2.4 | OSG Access to RENCI-BlueRidge | 10/01/10 | 11/30/10 | S.Cox
1.5.3 | Clemson Contributions |  |  | 
1.5.3.1 | Engage users requiring virtualization on OSG | 10/01/10 | 09/30/11 | Goasguen
1.5.3.2 | Work with campuses to deploy | 10/01/10 | 09/30/11 | Goasguen
1.5.3.3 | Investigate VM computing across OSG, Magelllan and Future Grid | 10/01/10 | 09/30/11 | Goasguen
1.5.4 | VO Engagement |  |  | 
1.5.4.1 | LSST | 10/01/10 | 09/30/11 | Garzoglio
1.5.4.2 | ITER | 10/01/10 | 09/30/11 | Garzoglio