## Sheet1
WBS | TaskName | InCharge | Start | Finish | Status after 12/31/2011
6.1 | Project Management | Sehgal, Garzoglio
6.1.1 | Year6a work plans for each area | Sehgal | 2011-08-01 | 2011-08-30 | Completed as planned
6.1.2 | Implement capture system for ongoing activities (with metric goals) | Sehgal, Garzoglio | 2011-08-22 | 2011-09-15 | Completed as planned
6.1.3 | Baseline year6A work plans for each area and start tracking | Sehgal | 2011-09-16 | 2011-10-15 | Completed as planned
6.1.4 | Year6A SOWs signed and subcontracts initiated | Sehgal | 2011-10-01 | 2011-11-30 | Completed as planned
6.1.4.1 | SOW drafts – Sept 30 | Sehgal | 2011-09-01 | 2011-09-30 | Completed as planned
6.1.4.2 | Sign-off within OSG – Oct 30 | Sehgal | 2011-10-01 | 2011-10-30 | Completed as planned
6.1.4.3 | Subcontracts from UW-Madison – Nov 30 | Sehgal | 2011-11-01 | 2011-11-30 | Completed as planned
6.1.5 | OSG DOE Final report – April 30 | Avery, Sehgal | 2012-03-15 | 2012-04-30 | *** deleted in Jan 2012 - as the dates are outside the defined interval for year6B
6.1.6 | OSG NSF Final Report – Sept 30 | Avery, Sehgal | 2012-08-15 | 2012-09-30 | *** deleted in Jan 2012 - as the dates are outside the defined interval for year6B
6.1.7 | Implement process for OSG Stakeholder Requests | Garzoglio | 2011-10-01 | 2011-11-15 | Implemented via JIRA at GOC and methods developed for populating and updating this database; currently in execution
6.1.8 | Develop project Plan for DigiCert Pilot and track to completion | Sehgal | 2011-10-01 | 2012-02-08 | ***new*** in Jan 2012 Project plan developed and tracking and resolution is in progress; project is proceeding nominally on plan
6.1.9 | Develop project Plan for DigiCert Pilot and track to completion | Garzoglio | 2011-12-01 | 2012-03-31 | ***new*** in Jan 2012 Project plan developed and tracking and resolution is in progress; project is proceeding nominally on plan
6.1.10 | Develop project plan for DigiCert ID CA implementation in OSG (if this is the recommendation from the pilot project) | Sehgal | 2012-02-10 | 2012-03-31 | ***new*** in Jan 2012
6.2 | Documentation Architecture | Weichel | 2011-10-01 | 2012-03-31
6.3 | Communication | Boon
6.3.1 | Revise and get agreement for the revision of the OSG communications plan | Boon | 2011-10-01 | 2011-12-01 | Other priority items continue to intervene
6.3.2 | Revise format and framework for the OSG newsletter | Boon | 2011-10-01 | 2011-12-01 | Added an index to the template
6.3.3 | When asked provide information to DOE and NSF that communicate OSG’s accomplishments – expected in Dec and/or Jan | Boon, Pordes | 2011-10-01 | 2012-03-31 | Happening Ad-hoc at this time.
6.4 | Education | Cartwright
6.4.1 | OSG Summer School | Cartwright
6.4.1.1 | Post video of the 2011 summer school | Cartwright | 2011-08-01 | 2011-11-01 | Dropped. Video quality was not good enough
6.4.2 | Finish analysis of surveys and distribute | Cartwright | 2011-10-01 | 2011-12-01 | Analysis of surveys finished. Posting in progress.
6.4.2.1 | Obtain funding | Cartwright | 2012-01-01 | 2012-06-30 | Mostly, work on the proposal with XSEDE
6.4.2.2 | Prepare this year’s School | Cartwright | 2012-03-01 | 2012-06-30 | Advertise, get students, logistics, curriculum, etc.
6.4.2.3 | Deliver the School | Cartwright | 2012-06-01 | 2012-06-30 | Actual dates TBD
6.4.2.4 | Follow up from School | Cartwright | 2012-07-01 | 2012-12-31
6.5 | International Outreach | Caballero
6.5.1 | Plan and execute VO Workshop in Colombia | Caballero, Severini | 2011-08-01 | 2012-03-31 | Activity closed down.
6.5.2 | Prepare for Visitor Program in summer 2012 | Caballero, Severini |  |  | Activity closed down.
6.5.2.1 | Create checklist for Visitor Program | Caballero, Severini | 2011-08-11 | 2011-09-30 | Visitor Program was made public.
6.5.2.2 | Communicate and start arrangements for summer visitor program with U Florida | Caballero, Severini, Avery | 2011-11-01 | 2012-03-31 | Univ of Florida is not participating this year.
6.5.2.3 | Communicate and start arrangements for summer visitor program with SBGrid | Caballero, Severini, Sliz | 2011-11-01 | 2012-03-31 | HMS is not participating this year.
6.6 | Assessment | Gardner |  |  | Define, get funding, get students, execute, follow up
6.6.1 | Review Operations area WBS and define key metrics, targets, trip points against OSG strategic plan | Gardner | 2011-10-01 | 2011-11-01 | This has been done for the Operations activity
6.6.2 | Develop means to present the metrics and assessment as a "balance scorecard" | Gardner | 2011-11-01 | 2011-12-01 | Completed
6.6.3 | Work with operations to provide their assessment in the accepted format. | Gardner | 2011-11-01 | 2011-12-01 | Completed
6.6.4 | Present assessment to the OSG PM and ET | Gardner | 2012-01-01 | 2012-01-01 | Presented in area coordinator's meeting; meeting with ET and PI has been scheduled for January 20, Ruth comment: In person meeting not possible, to be rescheduled. Phone meeting brought Miron up to speed and allowed commentary
6.6.5 | Adapt process based on lessons learned. | Gardner | 2012-02-01 | 2012-03-01
6.6.6 | Select second area to work with and start work with them | Gardner | 2012-02-01 | 2012-03-31 | Process started with Production and Stakeholder Requests activities