## Sheet1
1.0.2 | Production Coordination |  |  | Fraser
1.0.2.1 | Identify and articulate OSG issues that impact the effectiveness of sites & VOs and lead/coordinate OSG teams to resolve the issues. | 2010-10-01 | 2011-09-30 | Fraser
1.0.2.1.1 | Lead weekly Production calls, highlight important issues, and follow up on action items. | 2010-10-01 | 2011-09-30 | Fraser
1.0.2.1.2 | Work with the VO, Sites, and Operation Area coordinators to coordinate activities related to production. | 2010-10-01 | 2011-09-30 | Fraser
1.0.2.1.3 | Work with the Metrics Coordinator to monitor the performance of the OSG infrastructure and develop measures and metrics that assess the state of the facility. | 2010-10-01 | 2011-09-30 | Fraser
1.0.2.1.4 | Analyze the usage patterns and efficiency of resource utilization, and develop trend data for the OSG; use that data to propose improvement plans for the facility. | 2010-10-01 | 2011-09-30 | Fraser
1.0.2.1.5 | Provide written quarterly reports to the OSG ET on production activities. | 2010-10-01 | 2011-09-30 | Fraser
1.0.2.2 | Serve as the OSG Tier-3 Liaison to the US-ATLAS and US-CMS communities and establish regular, ongoing, point-to-point contact with the US ATLAS and US CMS Tier-3 support staff to enable cross-VO communication and collaboration, where appropriate. | 2010-10-01 | 2011-09-30 | Fraser
1.0.2.2.1 | Work with Atlas and CMS to define an operational plan for supporting T3s that includes appropriate VO and OSG combined efforts. | 2010-10-01 | 2011-09-30 | Fraser, Levshina, Mambelli
1.0.2.2.2 | Work with the Security Coordinator and Atlas/CMS T3 liasons to provide a practical “hands-on” security plan for T3s. | 2010-10-01 | 2011-09-30 | Fraser, Altunay
|  | 2010-10-01 | 2011-09-30
1.0.2.3 | Manage relationships and communication with stakeholders (especially CMS, Atlas, and LIGO) to understand status and issues and communicate them to the OSG-ET, with recommendations if possible. | 2010-10-01 | 2011-09-30 | Fraser
1.0.2.3.1 | Establish effective communication channels with OSG T1/T2/T3 site admins. | 2010-10-01 | 2011-09-30 | Fraser
1.0.2.3.2 | Represent the needs of these stakeholders at key internal OSG meetings and communications and escalate priorities as needed | 2010-10-01 | 2011-09-30 | Fraser, Mambelli
1.0.2.3.3 | Include reports on these communications as part of the Production quarterly report. | 2010-10-01 | 2011-09-30 | Fraser
1.0.2.4 | Assist the Executive Team in providing guidance to and working with the Operations, Sites, VOs and Education/Training area coordinators to communicate and facilitate the resolution of issues in the prioritization and planning of activities, assessment of success, and allocation of effort across the areas. | 2010-10-01 | 2010-09-30 | Fraser
1.0.2.5 | Based on guidance and approval by the OSG Executive Team, lead and coordinate plans to improve the OSG facility. | 2010-10-01 | 2010-09-30 | Fraser