## general_report
Key | Summary | Resolution | Review Comments
TX-43 | Added goc-alert for maillog | Unresolved
TX-42 | Set GHD_Loginname so that GOC Ticket submitter can update the GGUS ticket | Unresolved
TX-41 | Fix: Value does not fall within the limits specified for the field; (Maximum length - 255) : Grid:History : GHI_Short Solution | Unresolved
TX-40 | Make all Factory configuration stuff into XML | Unresolved
RSV-39 | Fix the rsv installation script so that it will correctly install uploader component | Unresolved
RSV-38 | Fix RSV 2 SAM downtime metric generator | Unresolved
RSV-35 | Find out why /usr/local/rsv-gratia-collector/tomcat/v55/gratia/data is not logrotated on rsv-itb.grid.iu.edu | Unresolved
OIM-67 | On Resource registration form, have one service already added. | Unresolved
OIM-66 | Footprint ticket is not generated after resource registration. | Unresolved
OIM-65 | Create Downtime Comparison Report (SAM vs OIM) | Unresolved
OIM-63 | Place Role next to resource relation list | Unresolved
OIM-62 | Discuss Notification on Security Contact Change | Unresolved
OIM-60 | Security Contact Confirmation/Proposal | Unresolved
OIM-55 | Contact editor just.... sucks | Unresolved
OIM-54 | *Possible* bug in OIM resource editor. | Unresolved
OIM-53 | Clarify what each WLCG flags will do once it's checked on GUI | Unresolved
OIM-52 | Discuss if we need to restrict users from using duplicate FQDN (and overrides) with other resources. | Unresolved
MYOSG-89 | Entity selectors on the MyOSG query allows same value to be selected. | Unresolved
MYOSG-88 | Expired metric not displaybed as expired | Unresolved
MISC-110 | Implement OIM based X509 authentication module for Twiki (or fix mod_ssl/fakeauth package) | Unresolved
MISC-109 | GOC internal service feedback request / form | Unresolved
MISC-105 | Setup jira-osg.goc | Unresolved
MISC-103 | Update BDII Tier 1 Alarm to Include Troubleshooting Info | Unresolved
MISC-102 | Implement GOC Alarm | Unresolved
MISC-100 | munin on internal seems to be under heavy load | Unresolved
MISC-98 | Draw interdependency graph for sonofsam retirement | Unresolved
MISC-97 | munin page loads slow | Unresolved
MISC-91 | Discuss possibility to store our install scripts in SVN | Unresolved
MISC-87 | rsv.grid needs service monitor | Fixed
MISC-84 | Setup service monitor on twiki.grid | Unresolved
MISC-82 | Research possible replacement for TWiki (for OSG Prime) | Unresolved
MISC-71 | Discuss how to move forward with GOC self-auditing | Unresolved
MISC-61 | Use X509 and OIM for TWiki authentication | Unresolved
GOCTICKET-84 | Misc improvements on Custom Form | Unresolved
GOCTICKET-83 | Expose Metadata, and let user select them on the ticket navigator | Unresolved
GOCTICKET-80 | Discuss purpose of /storage and find a way to consolidate storage ticket. | Unresolved
GOCTICKET-77 | Display list of emails when user select checkboxes for notification form. | Unresolved
DISPLAY-11 | Change update frequency | Unresolved
BDII-19 | Once is1,2 are ported to BDII v5, start copying processed_data.ldif to is3,5 instead of rsyncing cemon_raw_incoming | Unresolved
BDII-18 | There are quite a few hidden files under /usr/local/cemon_bdii_aggregator/data/cemon_raw_incoming | Unresolved
BDII-9 | BDII-8 Document steps required to: Allow SEs to publish to PRODUCTION BDII | Unresolved
TX-19 | FNAL Remedy Ticket Exchange | Unresolved | USCMS and Gratia have expressed interest in having this in place. OSG Executive Directors approves moving forward on this project.
RSV-33 | Daily RSV reports do not calculate reliability correctly during maintenance periods | Unresolved
RSV-32 | Create ReSS RSV Probe to use condor-status | Unresolved
RSV-29 | Add calculation of RG status (and availability/reliability if feasible) to RSVProcess | Unresolved
RSV-25 | Test glexec RSV Probe | Unresolved
RSV-23 | RSV Should Creating a Proxy at Runtime | Unresolved
OIM-21 | Add help tooltips to various OIM fields | Unresolved
OIM-17 | Downtime editor does not allow deletions following a recent release | Unresolved
OIM-13 | (Per OIM-12) How should we do software "testing" at GOC? | Unresolved
OIM-11 | Update VOMS information in OIM; generate two files in software cache | Unresolved
MYOSG-76 | Google Map API V2 to V3 upgrade | Unresolved
MYOSG-66 | Setup site environment parameter information gatherer | Unresolved
MYOSG-53 | Add Open a Ticket on this Isse Link | Unresolved
MYOSG-51 | Check feasibility of using Ted Hesselroth's SE discovery tool for BDII information gathering (rendered on MyOSG) | Unresolved
MYOSG-40 | BDII Treemap does not show information on all resources for each RG | Fixed
MYOSG-37 | Implement gratia metric detail storage system for rsvprocess | Unresolved
MYOSG-2 | Install Brian's Gratia Graph on dev.grid | Unresolved
MISC-111 | Global Search Feature | Unresolved | I am assigning this to Rob to add any ideas that he has to this as he wasn't at the support meeting today. -Kyle
MISC-95 | Permanent Home for SC Viz | Unresolved
MISC-76 | twiki-itb should have warning banner | Unresolved
MISC-72 | Figure out what's wrong with is.grid's rsync script | Unresolved
MISC-62 | Create a service-monitor check to detect process run off. | Unresolved
MISC-52 | Disable Footprints email attachment | Unresolved
MISC-45 | Discussion of Network Monitoring from GRNOC to OSG Resources | Unresolved
MISC-43 | GOC_Authorization_Service status is UNKNOWN | Unresolved
GOCTICKET-81 | Hide Subject of Security Tickets | Unresolved
GOCTICKET-67 | Metrics Reporting Bug | Unresolved
GOCTICKET-36 | Support center flag to indicate unresponsive ones | Unresolved
GOCTICKET-18 | New Ticket View - All | Unresolved
DISPLAY-8 | Create 30-day graphs | Fixed
BDII-12 | Retire site count monitor script with munin alerts from infosys graph | Unresolved
MYOSG-30 | Add Open Tickets to Resource Summary | Unresolved