## Sheet1
Institution | Paid-FTE | WBS | Name | %FTE | OSG-Paid | Description | Activities
BNL | 0 | 2 | Torre Wenaus | 0.2 | N | Extensions Co-Coordinator & Co-PI | Day to day and technical coordination of the science applications and extensions program of work.
BNL | 0 | 2 | Howard Gordon | 0.05 | N | Co-PI | Principal Investigator
BNL | 0 | 2 | Michael Ernst | 0.05 | N | Project Advisor | Technical Guidance
BNL | 0.25 | 1.1 | bnl-tbd1 | 0.25 | Y | Developer | GUMS/OSG Design, implementation & documentation
BNL | 0.25 | 1.1 | John Hover | 0.25 | Y | Developer | GUMS/OSG Coordination, Design, implementation & documentation
BNL | 0.5 | 2.2 | Aaron Thor | 0.5 | Y | Developer | Extensions in Gratia; this effort is only 1st half of the year
BNL | 0.1 | 1.8 | Jose Caballero | 0.1 | Y | South America Student Outreach | Support OSG Executive Director in planning and implementing the South America Outreach program
BNL | 0.9 | 2.2 | Jose Caballero | 0.9 | Y | Developer | Workload management system monitoring.
BNL | 0.3 | 1.5 | Maxim Potekhin | 0.3 | Y | Engagement | Contribute to OSG Engagement effort and leverage and support Panda for new OSG users
BNL | 0.7 | 2.2 | Maxim Potekhin | 0.7 | Y | WMS Developer | Contribute to just-in-time workload management extensions.; adapt, extend and integrate experiment distributed production & analysis systems and middleware components for a generic workload management service.
Caltech | 0 | 1.0.4 | Kent Blackburn | 0.17 | N | PI | PI Activities and Supervision of LIGO extensions work
Caltech | 0.33 | 3 | Kent Blackburn | 0.33 | Y | Co-Chair of OSG Council | Specific initiative to improve effectiveness of the OSG Council
Caltech | 1 | 1.0.4 | Britta Daudert | 1 | Y | LIGO SW integration | Support LIGO Extensions & Production
Caltech | 0.25 | 1.0.4 | Robert Engel | 0.25 | Y | LIGO SW integration | Support LIGO Extensions & Production
Caltech | 0.25 | 1.3 | Robert Engel | 0.25 | Y | Integration | Caltech ITB site and general integration support
Caltech | 0.5 | 1.8 | Robert Engel | 0.5 | Y | Documentation Process Mgmt | Support Documentation aligment initiative with focus on process and content
Chicago | 0.75 | 1.0.2 | Dan Fraser | 0.75 | Y | Production Coordinator | At previously agreed upon FTE cost.
Chicago | 0.5 | 1.0.1 | Marco Mambelli | 0.5 | Y | Software Engineer | Software tools development coordinated by STG; using the funding vacated by Ben Clifford
Chicago | 0.5 | 1.3 | Marco Mambelli | 0.5 | Y | Sites Coordination | Site Coordination in support of the Production Coordinator
Chicago | 0.5 | 1.3 | Robert Gardner | 0.5 | Y | PI & Integration Coordinator | Integration planning and execution; Site Coordination planning and execution
Chicago | 1 | 1.3 | Suchandra Thapa | 1 | Y | Integration Engineer | Integration testing of OSG software stack on ITB and VTB; support of site coordination.
Chicago | 0.5 | 3.2 | uc-tbd2 | 0.5 | Y | Education Engineer
Chicago | 0.5 | 1.8 | uc-tbd2 | 0.5 | Y | Training Engineer
Chicago | 0.5 | 1.3 | uc-tbd1 | 0.5 | Y | ITB System Admininstrator | Unix admin for ITB; using carry-over funds, if available
Clemson | 0.15 | 1.6 | Sebastien Goasguen | 0.15 | Y | PI & Campus Grids Coordinator | PI activities, Technical Supervision
Clemson | 0.25 | 1.6 | Linton Abraham | 0.25 | Y | Developer | Campus grids integration into OSG Facility
Florida | 0.5 | 1.8 | Jim Weichel | 0.5 | Y | Training & Content Management Coordinator | Coordinate OSG work in the training and content management area
Florida | 0 | 3 | Paul Avery | 0.1 | N | PI | PI Activities
Florida | 0 | 3 | Paul Avery | 0.1 | N | Co-Chair of OSG Council | Plan and coordinate the work of the OSG Council
FNAL | 0.3 | 1.1 | Andrew Baranovski | 0.3 | Y | Integrator and Developer | VDT and Storage Extensions
FNAL | 0.85 | 3.3 | Chander Sehgal | 0.85 | Y | Project Manager | Project and Budget Management
FNAL | 0.25 | 1.1 | Chris Green | 0.25 | Y | Integrator and Developer | Software including Gratia
FNAL | 0.2 | 1.2 | Chris Green | 0.2 | Y | Integrator and Developer | Operations at Fermigrid
FNAL | 0.5 | 1.5 | Chris Green | 0.5 | Y | Integrator and Developer | Engagement including MPI, DOE
FNAL | 0.25 | 3.2 | David Ritchie | 0.25 | Y | Communication Coordinator
FNAL | 0.1 | 3.2 | Marcia Teckenbrock | 0.1 | Y | Web Designer | Webmaster, Document Librarian, OSG News and Communications.
FNAL | 0.85 | 1.7 | Mine Altunay | 0.85 | Y | Security Officer | Plans and coordinates OSG security work program; build tools, procedures
FNAL | 0.5 | 3.2 | Miriam Boon | 0.5 | Y | iSGTW Editor
FNAL | 0.5 | 1.1 | Neha Sharma | 0.5 | Y | Integrator and Developer | Storage software for VDT and Extensions
FNAL | 0 | 1.7 | Ron Cudzewicz | 0.2 | N | Security Engineer | Develop procedures and tools to support OSG security
FNAL | 0.75 | 3 | Ruth Pordes | 0.75 | Y | PI and Executive Director | Coordinate OSG Work Program across all participating institutions
FNAL | 0.7 | 1.1 | Tanya Levshina | 0.7 | Y | Integrator & Test Engineer | Coordinate Storage software for VDT
FNAL | 0.5 | 1.1 | Ted Hesselroth | 0.5 | Y | Storage Developer | Storage software for VDT
Harvard Med | 0 | 1.0.3 | Piotr Sliz | 0.05 | N | PI | PI responsibilities and Project Supervision
Harvard Med | 0 | 1.0.3 | Ian Stokes-Rees | 0.1 | N | SBGRid VO Coordinator | Technical Supervision and Outreach to local Boston area groups
Harvard Med | 0 | 1.0.3 | Ben Eisenbraun | 0.03 | N | Science Applications Integrator | Compilation and optimization of scientific applications
Harvard Med | 0 | 1.0.3 | Ian Levesque | 0.03 | N | Systems Architect | Help to train and provide senior support for grid administration
Harvard Med | 0.85 | 1.0.3 | Peter Doherty | 0.85 | Y | System Admin | Integrate SBGrid resources with OSG
Indiana | 0 | 1.2 | Fred Luehring | 0.1 | N | Co-PI | PI Activities
Indiana | 0 | 1.2 | Scott McCaulay | 0.05 | N | PI | PI Activities
Indiana | 0.9 | 1.2 | Robert Quick | 0.9 | Y | Operations Coordinator | Operations Coordinator responsible for overall OSG operational activities
Indiana | 0 | 1.0.1 | Arvind Gopu | 1 | N | GOC Software Tools Development | External software project contributions to development of tools for operations
Indiana | 1 | 1.2 | Chris Pipes | 1 | Y | GOC Operations Staff | OSG Administration and operational support
Indiana | 1 | 1.2 | Elizabeth Chism | 1 | Y | GOC Operations Staff | OSG Administration and operational support
Indiana | 0.9 | 1.2 | Kyle Gross | 0.9 | Y | GOC Operations Staff | OSG Operations Support Lead
Indiana | 0.1 | 1.8 | Kyle Gross | 0.1 | Y | Twiki Administrator | TWiki infrastructure improvements/changes in support of Training and Content Management
Indiana | 1 | 1.2 | Soichi Hayashi | 1 | Y | GOC Operations Staff | OSG Systems administration: software support and services, infrastructure service administration
Indiana | 0.5 | 1.2 | iu-tbd1 | 0.5 | Y | GOC Operations Staff | Additional effort to handle tickets from LHC data taking (staff is added in Nov 2009)
Indiana | 0 | 1.2 | iu-tbd1 | 0.5 | N | GOC Operations Staff | Additional effort to handle tickets from LHC data taking (staff is added in Nov 2009)
Indiana | 0 | 1.2 | Tom Lee | 0.5 | N | GOC Operations Staff | OSG Core Services Systems Administration
LBNL | 0.5 | 1.1 | Alex Sim | 0.5 | Y | Integrator | Support Storage software, including BeStMan and xRootD
LBNL | 0.5 | 1.7 | Doug Olson | 0.5 | Y | PI | PI activities and operate the DOE Grids CA
LBNL | 0.5 | 1.3 | Iwona Sakrejda | 1 | Y | ITB Engineer | Integration testing of OSG software stack on ITB and VTB; support of site coordination.
Nebraska | 0.5 | 3.1 | Brian Bockelman | 0.5 | Y | Metrics Coordinator | Planning, collection, and reporting of OSG production and facility metrics and measurements
Nebraska | 0 | 3.1 | David Swanson | 0.05 | N | PI | PI activities
RENCI | 0 | 1.5 | Alan Blatecky | 0.02 | N | Co-PI
RENCI | 0 | 1.5 | Chris Bizon | 0.5 | N | Engagement
RENCI | 0 | 1.5 | John McGee | 0.25 | N | Co-PI & Engagement Coordinator
RENCI | 0 | 1.5 | Mats Rynge | 0.5 | N | Engagement
RENCI | 0 | 1.5 | Michael Stealey | 0.1 | N | Engagement
UCSD | 0 | 2 | Frank Wuerthwein | 0.1 | N | Applications Co-Coordinator & PI | Institutional PI and coordination of the science applications and extensions program of work.
UCSD | 0.3 | 1.1 | Abhishek Rana | 0.3 | Y | Developer, Integrater | Storage tools. Overall support of Hadoop, including testing, integration of Hadoop into VDT, and support of stakeholder reported issues
UCSD | 0.45 | 1.4 | Abhishek Rana | 0.45 | Y | VO Support | Coordinator of VOs area responsible for support and coordination of the “at large” OSG VOs
UCSD | 0.1 | 2.1 | Haifeng Pi | 0.1 | Y | Integrator | Scalability testing and characterization
UCSD | 0.2 | 1.7 | Igor Sfiligoi | 0.2 | Y | Developer, Integrator | Operational Security/Security Development
UCSD | 0.4 | 2.1 | Igor Sfiligoi | 0.4 | Y | Integrator | Coordinate Scalability & Reliability area; execute testing and characterization leading to feedback to developers on how to improve scaling performance
UCSD | 0.1 | 2.2 | Igor Sfiligoi | 0.1 | Y | Integrator | glideinWMS operations for OSG
UCSD | 0.2 | 2.1 | Sanjay Padhi | 0.2 | Y | Integrator | Scalability testing and characterization
UCSD | 0.25 | 2.1 | Terrence Martin | 0.25 | Y | Integrator | Scalability & Reliability testing; support of VO specific targeted campaigns, as needed
UIUC | 0 | 1.4 | John Towns | 0.05 | N | Co-PI | Coordination with NCSA team
UIUC | 0 | 1.4 | Shaowen Wang | 0.05 | N | Co-PI | PI Activities
UIUC | 0.5 | 1.0.1 | Anand Padmanabhan | 0.5 | Y | SW Developer | Development of general OSG software tools
UIUC | 0.5 | 1.7 | Anand Padmanabhan | 0.5 | Y | Sw Developer | Development of security related tools
UIUC | 0 | 1.0.2 | Doru Marcusiu | 0.1 | N | Developer | Special Projects in OSG Production & Facility
UIUC | 0 | 1.7 | James Basney | 0.05 | N | Project Advisor | Technical Guidance on Security related issues
UIUC | 0.5 | 1.7 | James Barlow | 0.5 | Y | Software Security Engineer | Review and implement security policy, systems and tools needs of OSG
Wisconsin | 1 | 1.1 | Alain Roy | 1 | Y | Software Coordinator | Coordinate and lead the OSG wide software development and integration activities
Wisconsin | 0.5 | 1.5 | Greg Thain | 0.5 | Y | Integrator | Software development and MPI support of Engagement
Wisconsin | 0.25 | 1.1 | Jamie Frey | 0.25 | Y | Integrator | VDT
Wisconsin | 1 | 1.1 | Matyas Selmeci | 1 | Y | Developer | VDT
Wisconsin | 0.5 | 1 | Miron Livny | 0.5 | Y | PI and Technical Director | Technical Coordination
Wisconsin | 1 | 1.1 | Scot Kronenfeld | 1 | Y | Developer | VDT
Wisconsin | 1 | 1.1 | Tim Cartwright | 1 | Y | Developer | VDT