## Sheet1
DRAFT
|  | Start date | End date | Owners | Other areas
1.2 | Operations | 2010-10-01 | 2011-09-30 | Quick
1.2.1 | Support LHC | 2010-10-01 | 2011-09-30 | Quick | All
1.2.1.1 | Provide operational issue management for WLCG in collaboration with US-CMS and US-ATLAS | 2010-10-01 | 2011-09-30 | Quick
1.2.1.2 | Publish availability and reliability metrics to WLCG | 2010-10-01 | 2011-09-30 | Quick
1.2.1.3 | Maintain the relationship with WLCG operations entities (monitoring, GGUS ticketing, VOs, infrastructure services) | 2010-10-01 | 2011-09-30 | Quick
1.2.2 | Routine Process Execution | 2010-10-01 | 2011-09-30 | Quick
1.2.2.1 | Operate OSG Services at levels that meet the SLAs | 2010-10-01 | 2011-09-30 | Quick, Chadwick (FNAL), Sfiligoi (UCSD)
1.2.2.1.1 | Propose Configuration Management for Operational Services | 2010-10-01 | 2010-12-31 | Quick
1.2.2.2 | Communication of Operational Issues to OSG Community | 2010-10-01 | 2011-09-30 | Quick
1.2.2.2.1 | Notification of events for Core and Support Services | 2010-10-01 | 2011-09-30 | Quick
1.2.2.2.2 | Maintain 24x7 phone, email, and web support for trouble ticket submission | 2010-10-01 | 2011-09-30 | Quick
1.2.2.2.3 | Weekly operations phone cal | 2010-10-01 | 2011-09-30 | Quick
1.2.2.2.4 | Wellness visits to major OSG stakeholder sites | 2010-10-01 | 2011-09-30 | Quick
1.2.2.3 | Ticket Handling | 2010-10-01 | 2011-09-30 | Quick
1.2.2.3.1 | Continue Normal Ticket Troubleshooting and Routing | 2010-10-01 | 2011-09-30 | Quick
1.2.2.3.2 | Continue Ticket Exchange Services with Stakeholders | 2010-10-01 | 2011-09-30 | Quick
1.2.2.4 | Provide 24x7 Support for Security | 2010-10-01 | 2011-09-30 | Quick | Security
1.2.2.5 | Introduce New Services to Operational Infrastructure as Necessary | 2010-10-01 | 2011-09-30 | Quick
1.2.2.5.1 | Create SLAs for New Services | 2010-10-01 | 2011-09-30 | Quick
1.2.2.5.1.1 | Implement SLA for UCSD Glide-In Factory | 2010-10-01 | 2010-11-01 | Quick,Sfiligoi
1.2.2.5.2 | Evaluate New Services Technologies | 2010-10-01 | 2011-09-30 | Quick
1.2.2.6 | Provide OSG internal metrics on operations | 2010-10-01 | 2011-09-30 | Quick
1.2.2.6.1 | Availability and Reliability of Core Services | 2010-10-01 | 2011-09-30 | Quick
1.2.2.6.2 | Ticket Handling | 2010-10-01 | 2011-09-30 | Quick
1.2.3 | Improving Operational Processes | 2010-10-01 | 2011-09-30 | Quick
1.2.3.1 | Review/update documentation of OSG operational processes and procedures | 2010-10-01 | 2011-09-30 | Quick
1.2.3.2 | Analysis of benefit and impact of distributed operational Infrastructure | 2010-10-01 | 2011-09-30 | Quick
1.2.3.3 | Improve efficiency of administrative processes (automation) as identified | 2010-10-01 | 2011-09-30 | Quick
1.2.3.4 | Conduct an operational process review | 2010-10-01 | 2011-09-30 | Quick
1.2.3.4.1 | Conduct an internal Audit of Core Service Vital Functions | 2010-10-01 | 2011-03-30 | Quick
1.2.4 | Help Regional Grids with Operational Infrastructure | 2010-10-01 | 2011-09-30 | Quick
1.2.5 | Interaction with External Projects | 2010-10-01 | 2011-09-30 | Quick