## Slide 1: OSG Area Coordinators Meeting Operations
Rob Quick
1/11/2012

## Slide 2
 | WBS Ongoing Activities | 
1 | Support LHC | 95% Attendance at WLCG Daily Operations Meetings, 2 Face-to-Face meetings with WLCG Operations Staff.
2 | Routine Operational Process Execution | Meet services availability as defined in the SLA for each service. Push all ticket to resolution.
3 | Improving Operational Processes | Two GOC Operations Face-to-Face meetings to brainstorm procedural efficiency, these items will considered by Operations and OSG management based on effort.
4 | Help Regional Grids with Operational Infrastructure | Help GridUNESP set up operational infrastructure. Other campus and regional grids will be considered as they are identified.
5 | Interaction with External Partners | Conduct wellness visits to major stakeholders, attend the traditional OSG meetings and workshops to get customer feedback on Operational services.
6 | Support Desk Staff Training | Plan 10-12 Sessions (approximately monthly) that include the Operations Staff and various technology experts.
7 | Monitor and Report Effort for Additional Operational Services | Submit monthly effort concerns in writing to OSG ET.

## Slide 3: Ongoing Items Notes
Support LHC – First Quarter Attendance 95%, Face to Face occur in Spring and Fall
Routine Operational Process Execution – Meeting all SLA Availability and Reliability Stats and tickets are being handled efficiently
Improving Operational Processes – No meetings scheduled at this point, though many ideas are pending
Help Regional Grids with Operational Infrastructure – UNESP is awaiting a funding proposal.
Interaction with External Partners – Visited FNAL and CMS at FNAL in December to discuss ticket exchange, Gratia expectations, and RVS Reporting
Support Desk Staff Training – Have had conversations with VDT but no formal proposal to this point. This is behind.
Monitor and Report Effort for Additional Operational Services – Gratia effort during upgrade was high, I have RCA in hand but have not reviewed it.

## Slide 4
 | WBS Item |  |  | 
2.2 | Operations | Quick |  | 
2.2.1 | New Service Implementation and Upgrades | Quick |  | 
2.2.1.1 | Plan and Deploy Top Level BDII | Quick | 10/1/11 | 1/15/12
2.2.1.2 | Plan and Deploy CERN Based WMS Glide-In Factory | Quick | 10/1/11 | 2/15/12
2.2.2 | Improving Operational Processes and Services | Quick |  | 
2.2.2.1 | Evolve HA Technologies to LVS | Quick | 10/1/11 | 4/30/12
2.2.2.2 | Consolidate Public Documentation Services | Quick | 10/1/11 | 8/31/12

## Slide 5: WBS Items – Notes
Plan and Deploy Top Level BDII – Delayed due to turnover in the WLCG Information Officer position.
Plan and Deploy CERN Based WMS Glide-In Factory – Done
Evolve HA Technologies to LVS – Select ITB Services using LVS and in production on the RPM Repository
Consolidate Public Documentation Services – Plans to move the current www.opensciencegrid.org material to twiki.opensciencegrid.org in the March timeframe, soon confluence-itb.grid.iu.edu will be available for evaluation.
OSG-XSEDE Front end – Needs to be added.
APEL/Gratia Interface – Needs to be added as an evaluation item.
Network Monitoring in MyOSG – Added as an evaluation item.

## Slide 6: Concerns
Still adding more services without deprecating any services. We have just pressed beyond the single server rack threshold.
Staff training courses are behind.
New “Operational Process Improvement” ideals need a sounding board. CRM, Event Notification Systems (real time monitoring, operations ticker, customizable alerts), Collaborative Diagnostic Tools