## Sheet1
WBS | Task | Start date | End date | Owners
1.4 | VOs Group Coordination | 2010-10-01 | 2011-09-30 | Rana
1.4.1 | Track VOs opportunistic utilization and production efficiency | 2010-10-01 | 2011-09-30 | Rana
1.4.1.1 | In phase with LHC operations, gauge any limitations of opportunistic resource availability for other VOs on OSG. | 2010-10-01 | 2011-09-30 | Rana, Fraser
1.4.1.2 | Monitor accounting data and characteristics of VOs. Use both views - OSG Accounting and VOs Accounting. | 2010-10-01 | 2011-09-30 | Rana
1.4.1.3 | Preemption/Eviction is a prevalent characteristic in opportunistic grid usage. With Production and Site Areas, continue to provide support and advice to affected VOs. | 2010-10-01 | 2011-09-30 | Rana
1.4.2 | Analyze portfolio of functional VOs and recommend needed actions to the OSG-ET | 2010-10-01 | 2011-09-30 | Rana
1.4.2.1 | Value delivery to Group 1 (high activity): D0, CDF, Fermi-VO, HCC*, SBGrid. As needed, work with each VO to manage effective production across OSG. Track weekly progress. | 2010-10-01 | 2011-09-30 | Rana
1.4.2.2 | Value delivery to Group 2 (moderate activity): DES (+ JDEM), DOSAR, GLUE-X*, ILC, STAR. | 2010-10-01 | 2011-09-30 | Rana
1.4.2.3 | Value delivery to Group 3 (periodic activity): GEANT4, GridUNESP*, NYSGrid. | 2010-10-01 | 2011-09-30 | Rana
1.4.2.4 | Quarterly executive summary to ET/Project Mgmt on functional VOs. | 2010-10-01 | 2011-09-30 | Rana
1.4.3 | Manage portfolio of VOs that have limited activity | 2010-10-01 | 2011-09-30 | Rana
1.4.3.1 | IceCube: Continue expansion on OSG using glideinWMS and Squid/SRM Storage. | 2010-10-01 | 2011-03-31 | Rana
1.4.3.2 | ALICE: Establish mechanisms for increase in ALICE operations on OSG. Execute USALICE plan on NERSC & LLNL. | 2010-10-01 | 2011-09-30 | Rana
1.4.3.3 | CompBioGrid, GPN, GROW: Provide specialized support to enable OSG usage. | 2010-10-01 | 2011-03-31 | Rana
1.4.3.4 | NanoHUB: Maintain HUBzero based application/user activity on OSG. | 2010-10-01 | 2011-09-30 | Rana
1.4.3.5 | CIGI, DayaBay*, GRASE, NWICG: Assess availability of roadmaps; assist in planning. | 2010-10-01 | 2010-12-15 | Rana
1.4.3.6 | Closure of VOs: With ET's direction, assess viability (and closure) of a VO if success-roadmap and value proposition is unclear. | 2010-10-01 | 2011-09-30 | Rana
1.4.3.7 | New VO registrations in GOC: Evaluate clarity of plan, and assist EB in deciding approval or denial of registration. | 2010-10-01 | 2011-09-30 | Rana, Quick
1.4.3.8 | New VO formations via Engagement: Work with Engagement & CampusGrids Areas to assess/execute plan. | 2010-10-01 | 2011-09-30 | Rana, McGee
1.4.3.9 | Quarterly executive summary to ET/Project Mgmt on inactive VOs. | 2010-10-01 | 2011-09-30 | Rana
1.4.4 | Track consortium-wide publications for funding agencies | 2010-10-01 | 2011-09-30 | Ritchie, Rana
1.4.4.1 | Collect scientific publications of all VOs (including ATLAS, CMS, LIGO) deriving benefit from OSG for annual DOE & NSF reports. Catalog the full OSG-wide listing. | 2010-10-01 | 2011-09-30 | Ritchie, Rana
1.4.5 | Organize a forum for regular stakeholder interaction | 2010-10-01 | 2011-09-30 | Rana
1.4.5.1 | Organize Weekly-VO-Forum teleconferences, inviting select VOs and peer OSG Areas. | 2010-10-01 | 2011-09-30 | Rana, Ritchie, Teckenbrock
1.4.5.2 | Organize F2F Annual OSG VOs & Users Meeting. | 2010-12-01 | 2010-12-15 | Rana
1.4.5.3 | Organize F2F meetings with specific VOs as needed. | 2010-10-01 | 2011-09-30 | Rana, Pordes, Fraser
1.4.5.4 | Serve as conduit for peer OSG Areas to facilitate at-large VOs matters. E.g., Content Mgmt, Software, Sites Coordination, Storage, Scalability/Reliability/Usability. | 2010-10-01 | 2011-09-30 | Rana
1.4.6 | Coordinate stakeholder participation in OSG planning and software | 2010-10-01 | 2011-09-30 | Rana
1.4.6.1 | Organize periodic collection of VOs plans and requirements. Communicate VOs direct input to Council. | 2010-10-01 | 2011-09-30 | Rana
1.4.6.2 | As needed, plan and execute pre-release software validation by VOs (including ATLAS, CMS, LIGO) on ITB. | 2010-10-01 | 2011-09-30 | Rana, Gardner
1.4.6.3 | Manage and track VOs software requirements. | 2010-10-01 | 2011-09-30 | Rana, Roy
1.4.7 | Use VO-based experience to assist ET in exploring lightweight dynamic VOs | 2010-10-01 | 2011-09-30 | Rana
1.4.7.1 | Using experience with diverse VOs, try to simplify entrance of small communities into OSG. | 2010-10-01 | 2011-09-30 | Rana, Fraser
1.4.7.2 | Explore relevant stakeholder requirements. As needed: investigate architecture, resource provisioning, and lifecycle mgmt related to short-lifespan small-scale dynamic VOs. | 2010-10-01 | 2011-09-30 | Rana, Pordes, Wuerthwein
Note: [ * = new VO in Y4]