## Slide 1: OSG Area Coordinators Meeting Operations
Rob Quick
2/22/2012

## Slide 2
 | WBS Ongoing Activities | 
1 | Support LHC | 95% Attendance at WLCG Daily Operations Meetings, 2 Face-to-Face meetings with WLCG Operations Staff.
2 | Routine Operational Process Execution | Meet services availability as defined in the SLA for each service. Push all ticket to resolution.
3 | Improving Operational Processes | Two GOC Operations Face-to-Face meetings to brainstorm procedural efficiency, these items will considered by Operations and OSG management based on effort.
4 | Help Regional Grids with Operational Infrastructure | Help GridUNESP set up operational infrastructure. Other campus and regional grids will be considered as they are identified.
5 | Interaction with External Partners | Conduct wellness visits to major stakeholders, attend the traditional OSG meetings and workshops to get customer feedback on Operational services.
6 | Support Desk Staff Training | Plan 10-12 Sessions (approximately monthly) that include the Operations Staff and various technology experts.
7 | Monitor and Report Effort for Additional Operational Services | Submit monthly effort concerns in writing to OSG ET.

## Slide 3: Ongoing Items Notes
Support LHC – First Quarter Attendance 95%+, Face to Face occur in Spring (EGI Community Forum and CHEP) and Fall (EGI Technical Forum)
Routine Operational Process Execution – Meeting all SLA Availability and Reliability Stats and tickets are being handled efficiently
Improving Operational Processes – Last meeting in October, targeting April or May for the next.
Help Regional Grids with Operational Infrastructure – UNESP is awaiting a funding proposal.
Interaction with External Partners – Visited FNAL in December and Visited UCSD in January for Glide-In Factory workshop.
Support Desk Staff Training – Have had conversations with VDT but no formal proposal to this point. This is behind! May use Condor Week as a second training exercise for 1 or 2 staff.
Monitor and Report Effort for Additional Operational Services – Gratia effort during upgrade was high, RCA is posted on Operational Twiki Web. https://twiki.grid.iu.edu/bin/view/Operations/GratiaUpgradeRCA

## Slide 4
 | WBS Item |  |  | 
2.2 | Operations | Quick |  | 
2.2.1 | New Service Implementation and Upgrades | Quick |  | 
2.2.1.1 | Plan and Deploy Top Level BDII | Quick | 10/1/11 | 1/15/12
2.2.1.2 | Plan and Deploy CERN Based WMS Glide-In Factory | Quick | 10/1/11 | 2/15/12
2.2.2 | Improving Operational Processes and Services | Quick |  | 
2.2.2.1 | Evolve HA Technologies to LVS | Quick | 10/1/11 | 4/30/12
2.2.2.2 | Consolidate Public Documentation Services | Quick | 10/1/11 | 8/31/12

## Slide 5: WBS Items – Notes
Plan and Deploy Top Level BDII – Sidelined for now, Brian and Soichi are researching other options for Information Systems as part of the Technology Area and will have a report available next week.
Plan and Deploy CERN Based WMS Glide-In Factory – Done
Evolve HA Technologies to LVS –Production on the RPM Repository, Pacman Repository is schedule for next maintenance window.
Consolidate Public Documentation Services – Plans to move the current www.opensciencegrid.org material to twiki.opensciencegrid.org on Feb 28th.
  Planning document at https://twiki.grid.iu.edu/bin/view/Operations/OpenScienceGridWeb
  ITB Mock Up at https://twiki-itb.grid.iu.edu/bin/view
OSG-XSEDE Front end – Hardware Installation Done.
APEL/Gratia Interface – Added to EGI requirements document.
Network Monitoring in MyOSG – Added as an evaluation item.
DigiCert Transition and Front End – Needs to be added.

## Slide 6: Concerns
Staff training courses are behind.
Prioritization of the Content Management project.
Continued growth in number of JIRA requests.
DigiCert transition.

## Slide 7: Growth of Operational Services (Spring 2009 – Present)
Deprecated Services | Added Services
VORS – Summer 2009 | MyOSG – Spring 2009
 | OIMv2
 | Ticket Web UI
Ticket Email Exchange Scripts | GOC Ticket Synchronizer
 | RSV – SAM Messaging and Reports
 | Display
 | Glide-In Factory (3 Locations)
 | RPM Repo
 | JIRA
 | Gratia Web
 | Blog Consolidator
 | XSEDE Front End (New)
 | DigiCert Front End (New)
Note: Does not include internal service such as LVS, Munin, Data repo and report tools, GOC Monitoring and Alerting, Ops Blog etc.