## Slide 1: OSG Area Coordinators Meeting Security Team Report
Mine Altunay
6/6/2012

## Slide 2
 | WBS Ongoing Activities | 
1 | Incident response and vulnerability assessment | Minimizing the end-end response time to an incident, 1 day for a severe incident, 1 week for a moderate incident, and 1 month for a low-risk incient.
2 | Troubleshooting; processing security tickets including user requests, change requests from stakeholders, technical problems | Goal is to acknowledge tickets within one day of receipt.
3 | Maintaining security scripts (vdt-update-certs, vdt-ca-manage, cert-scripts, etc) | Maintain and provide bug fixes according to the severity of bugs. For urgent problems, provide an update in one week; For moderate severity, provide an update in a month; For low risk problems, provide an update in 6 months.
4 | Supporting OSG RA in processing certificate requests | Each certificate request is resolved within one week; requests for GridAdmin and RA Agents are served within 3 days.
5 | Preparing CA releases (IGTF), modifying OSG software as the changes in releases require | CA release for every two months
6 | Security Policy work with IGTF, TAGPMA, JSPG and EGI | Meet with IGTF and TAGPMA twice a year. Attend JSPG and EGI meteings remotely and face-face once a year. Track security policy changes and report to OSG management.
7 | Security Test and Controls | Execute all the controls included in the Security Plan and prepare a summary analysis.
8 | Weekly Security Team Meeting to review work items | Coordinate weekly work items.
9 | Weekly reporting to OSG-Production | Report important items that will affect production; incidents, vulnerabilities, changes to PKI infrastructure
10 | Monthly reporting to OSG-ET | Meet with ET once a month to discuss work items
11 | Quarterly reporting to Area Coordinator meeting | Meet with area coordinators to discuss work items.

## Slide 3: Ongoing Work: Operational Security
Software Vulnerabilities/Incidents
  No incident at OSG. EGI reported a DDoS attack using EGI resources. The attacker used the grid resources to attack a third party victim. Sent out an announcement; cautionary steps to prevent this.
  Software vulnerabilities: 12 vulnerabilities have been assessed, including, gridFTP, Hadoop, mysql, openSSL, Voms, Mac Java, Kernel, Tomcat vulnerabilities.
  4 security announcements sent since 4/11/2012 (last security report)
  An incident drill with Tier 3s, 7 out of 11 sites participated. First half was drilled in May. The second half is drilled this week. Report will be sent to ET.

## Slide 4: Ongoing Work: Operational Security
  1. XESEDE operational interface: Calling into weekly Incident Response calls and biweekly Security Operations calls.
2. Stakeholder requests: FermiCloud stakeholder request. Identify pilot jobs and ensure that they invoke glexec
4. New request for investigation sent to DOEgrids CA. Generating CRLs seem to take longer than what CP/CPS allows.
  5. Two items
  CA release process update. OLD location of GOC CA rpm cache turned off.
  New project: We had an earlier project to make our software compatible with CA bundle layouts designed for SHA-2. We have been releasing CA bundles with both old layouts (sha-1) and new layouts (sha-2). We start a project plan to phase out the old bundles from production.

## Slide 5: Ongoing Work: Operational Security
5. 3 IGTF releases since April.
6. IGTF All Hands and Security Policy Group Meetings in May.
7. Security test and Controls: Started in May. 60% completed. It will be finished before mid-July.

## Slide 6: WBS Items
4 | Security |  |  |  | 
4.1 | Identity Management | Basney, Altunay |  |  | 
4.1.1 | Work Plan agreed by OSG Management and Security team | Basney, Altunay | 8/1/11 | 9/15/11 | Completed
4.1.2 | Integrate a UCSD VO with CILogon CA to utilize local resources | Basney, Altunay | 8/15/11 | 9/30/11 | Completed
4.1.3 | Integrate a VO with Cilogon CA which can submit jobs to OSG resources | Basney, Altunay | 9/16/11 | 12/30/11 | Completed
4.2 | Conduct Security Controls and Tests | Altunay, Slagell |  |  | 
4.2.1 | Execute the security controls in OSG Security Plan | Altunay, Slagell | 5/1/12 | 7/1/12 | 
4.2.2 | Prepare a report on findings from the Security Controls | Altunay, Slagell | 7/1/12 | 7/22/12 | 
4.4 | Evaluate and update CA release process | Altunay, Roy, Quick | 12/21/11 | 2/29/12 | ***new*** Completed
4.5 | Provide DES VO with guidance over Security Policies and Procedures | Altunay | 1/12/12 | 2/31/2012 | ***new*** Completed

## Slide 7: WBS Items
4.4. is completed on time. As reported in Ongoing Activities.
Phasing out old CA bundle layouts will proceed the item 4.4.

## Slide 8: Any Other Issues
Kevin Hill officially transitioned to security team on June 1st.
Marco ramped down to zero.
Vacations coming up for July.
  Kevin will be on vacation almost all of July.