## Slide 1: OSG PKI Contingency and Recovery Plans
Mine Altunay, Von Welch
OSG Council
August 23, 2012

## Slide 2: OSG PKI Failure Cases
4 Failure Types:
  Back-End CA Compromise
  OSG OIM Front-End Compromise
  Back-End CA Loss of Availability
  OSG OIM Front-End Loss of Availability
Back-End CA and OIM Front-End Compromises have the highest impact.
OIM Front-End compromise is more likely to happen than Back-End CA compromise.

## Slide 3: Recovery Plans: Back-End CA Compromise
Day 1
Discovery
Day 2
IR Team &
Comm.
Prevent Unauthorized Access Impact: None
Day 3
Remove the failing CA. Impact: Production stops
Use other IGTF CAs (CERN, Fermi, NCSA, XSEDE, NERSC). Impact: Production at most at 50% of normally available CPU hours. Most productive sites and LHC users obtain certificates
Day 5
Day 20
Establish a Temporary Non-IGTF CA
Day 80
Establish an IGTF
CA
Propagate new DNs. Impact: Production restored to normal
Day 82
Use the Non-IGTF CA. Impact: all Sites and users are in production. Not compatible with outside of the US

## Slide 4: Recovery Plans: Back-End CA Compromise
Low Likelihood with High Impact
Production is most affected between Day 3 and Day 20. After Day 20, OSG establishes a Temporary Non-IGTF CA (a simple openSSL CA).
  The Temporary CA brings production back close to regular levels, but WLCG interoperability will be impacted. Job and data transfer between Europe and OSG will be impacted.
After Day 80, production goes back to normal
  Either, compromised CA will get restored by DigiCert, which is very likely to happen
  Or, OSG establish a new IGTF CA.

## Slide 5: Recovery Plans: Back-End CA Compromise
Choices:
  Accept to operate with a Temporary CA for two months.
    (+) Production close to being normal.
    (-) WLCG Interoperability gets hit.
    (-) Council members may refuse to use an unaccredited CA.
  OR, Prepare a back up IGTF CA.
    (-) High cost for building and maintaining.
    (+) Eliminates interoperability and un-accreditation problems.

## Slide 6: Recovery Plans: OIM Front-End Compromise
Day 1:
Discovery
Form IR Team
Establish
Comm.
Impact: None
Identify and disable the compromised Front-End accounts. Revoke and re-issue any certs previously issued by compromised RAs and GA accounts.
Impact: No major impact on production. Temporary short-term loss of access for compromised certificates. Remaining RAs and GA will take the compromised agents workload.
Week 4
If compromise spread too widely, treat this as a CA compromise. Revoke all existing certs and re-issue new certs with the same DN. If OSG Front-End is unusable, issue certs directly form Digicert MPKI. Impact: Temporary short-term loss of access for all users: at best a day, at worst two weeks of access loss for an individual user.
Day 3
Patch the OSG Front-end. Re-instate access to all RAs and GAs. Impact: None on Production. Less work for uncompromised RA and GAs.
Patch the OSG Front-end. Re-instate access to all RAs and GAs. Impact: None on Production. Less work for uncompromised RA and GAs.

## Slide 7: Recovery Plans: OIM Front-End Compromise
Higher likelihood of compromise.
Worst-case Impact is almost equal to CA compromise
  except the CA keys are uncompromised.
  But, all certificates must be revoked and re-issued.
  Production level drops for 2 weeks while revoking illicitly issued certs and re-issuing them.
Precautions that can be taken now:
  Assess security of the OIM Front-End against attacks
  Document and Practice forensics and investigation activities for a Front-End compromise.
  Ensure all OSG software can work directly against DigiCert web front-end

## Slide 8: Recovery Plans: CA Service Loss
Day 1:
Service Loss
Form IR Team
Establish
Comm.
Impact: None
Day 3
Make other IGTF CAs (CERN, Fermi, NCSA, XSEDE, NERSC)
available to OSG
Impact: New users and expiring certificates out of the production. The rest of OSG works normally
Week 4
Establish a Non-IGTF CA
Establish an IGTF
CA
Week 12
Week 2
Release a New CA Bundle, Ban Revoked
certs
Week 3
Direct users to non-IGTF
CA. Impact: Less burden on IGTF CAs.
Use the IGTF CA. Impact: Production back to normal.
Unknown
Direct users to IGTF CAs (CERN, Fermi, NCSA, XSEDE, NERSC). Impact: New users and expiring certificates join production. Extra work burden on external CAs

## Slide 9: Recovery Plans: CA Service Loss
Moderate Likelihood with Moderate Impact
Existing certs will continue to function.
New users and expired certs will be impacted. Expiring certs can/should renew a month in advance. So production will truly get impacted after two months of service loss.
If CA does not restore services, send users first to external IGTF CAs and then establish a Temporary non-IGTF CA

## Slide 10: Recovery Plans: OIM Front-End Service Loss
Day 1: Front-End
Service Loss
Form IR Team
Establish
Comm.
Impact: None
Directly Access DigiCert MPKI
Impact: No impact on production. Extra burden on OSG staff to access DigiCert MPKI
Week 4
Put Back-up OIM service in production. Impact: Production is restored back to normal
Week 2
Week 3

## Slide 11: Recovery Plans: OIM Front-End Service Loss
Moderate Likelihood with Low Impact
No impact on OSG Production. OSG staff can access DigiCert web front-end to issue, revoke, renew certs. More inconvenient for the OSG staff.
The main front-end is at Indiana University Bloomington with a spare at IUPUI (Indianapolis) that can be switched to within 24 hours
In the worst-case scenario, OSG will use DigiCert web front-end directly.

## Slide 12: Questions?