## general_report
Key | Summary | Priority | Due Date | Community Notification | Review Comments
TX-40 | Make all Factory configuration stuff into XML | Major |  | No
TX-35 | Research what it takes to setup tx2 along with tx1 | Minor |  | No
TX-19 | FNAL Remedy Ticket Exchange | Minor | 2010-05-17 | Yes | USCMS and Gratia have expressed interest in having this in place. OSG Executive Directors approves moving forward on this project.
SYS-82 | SYS-79 Set up multiple OpenVPN servers to eliminate the single point of failure | Major |  | No
SYS-81 | SYS-79 Fix routing on IUPUI hosts to use IUPUI private VLAN in preference to OpenVPN link when possible | Major |  | No
SYS-80 | SYS-79 Renumber the private VLAN IP addresses | Major |  | No
SYS-79 | Improve robustness of private VLAN on IUPUI hosts | Major |  | No
SYS-78 | Add service monitor on jump.grid to detect any malicious activities | Major |  | No
SYS-77 | Observe and report on incoming packets on sonofsam | Major | 2010-08-31 | No
SYS-74 | Setup test LVS | Major |  | No
SYS-73 | Make is-itb function as is-itb | Major |  | No
SYS-69 | Learn about the border router | Minor |  | No
SYS-62 | SYS-60 Install new VM hosts and KVM at ICTC | Major |  | No
SYS-61 | SYS-60 Install new VM hosts in IDC | Major |  | No
SYS-60 | Install new VM hosts | Major |  | No
SYS-56 | Add instructions for VMWare console access for Mac users | Minor | 2010-06-10 | No
SYS-43 | Configure syslog-ng on internal to forward urgent messages to goc-alert | Minor |  | No
SYS-17 | IU DNS Alias | Minor
SYS-16 | Review GRNOC Nagios Monitoring | Critical | 2009-12-10
RSV-33 | Daily RSV reports do not calculate reliability correctly during maintenance periods | Minor |  | No
RSV-32 | Create ReSS RSV Probe to use condor-status | Minor |  | No
RSV-29 | Add calculation of RG status (and availability/reliability if feasible) to RSVProcess | Minor |  | No
RSV-25 | Test glexec RSV Probe | Minor | 2010-05-04 | No
RSV-23 | RSV Should Creating a Proxy at Runtime | Minor | 2010-04-11 | Yes
OIM-52 | Discuss if we need to restrict users from using duplicate FQDN (and overrides) with other resources. | Major |  | No
OIM-21 | Add help tooltips to various OIM fields | Minor |  | No
OIM-17 | Downtime editor does not allow deletions following a recent release | Minor |  | No
OIM-13 | (Per OIM-12) How should we do software "testing" at GOC? | Minor
OIM-11 | Update VOMS information in OIM; generate two files in software cache | Minor
MYOSG-77 | MYOSG-60 Turn Apache RSV Probe into OSG Web Page and OSG Doc DB and RSV Report Probe | Major |  | No
MYOSG-67 | Fix RSV status map anchor history issue | Minor |  | No
MYOSG-66 | Setup site environment parameter information gatherer | Minor | 2010-07-12 | No
MYOSG-60 | Create Operations Status Overview Page in MyOSG | Major |  | No | This view already exists: http://tinyurl.com/24y9x9v
MYOSG-53 | Add Open a Ticket on this Isse Link | Minor |  | No
MYOSG-51 | Check feasibility of using Ted Hesselroth's SE discovery tool for BDII information gathering (rendered on MyOSG) | Minor |  | No
MYOSG-40 | BDII Treemap does not show information on all resources for each RG | Minor |  | No
MYOSG-37 | Implement gratia metric detail storage system for rsvprocess | Minor |  | No
MYOSG-30 | Add Open Tickets to Resource Summary | Trivial |  | No
MYOSG-2 | Install Brian's Gratia Graph on dev.grid | Minor | 2009-11-27
MISC-94 | Create read-only production twiki instance (twiki2?) | Major |  | No
MISC-93 | Fix chkconfig procedure on install scripts | Major |  | No
MISC-91 | Discuss possibility to store our install scripts in SVN | Major |  | No
MISC-87 | rsv.grid needs service monitor | Major |  | No
MISC-84 | Setup service monitor on twiki.grid | Major |  | No
MISC-82 | Research possible replacement for TWiki (for OSG Prime) | Major |  | No
MISC-76 | twiki-itb should have warning banner | Minor |  | No
MISC-72 | Figure out what's wrong with is.grid's rsync script | Minor |  | No
MISC-71 | Discuss how to move forward with GOC self-auditing | Major |  | No
MISC-62 | Create a service-monitor check to detect process run off. | Minor |  | No
MISC-61 | Use X509 and OIM for TWiki authentication | Major |  | Yes
MISC-53 | Configure RT Nagios Instance to check service monitor statues. | Minor |  | No
MISC-52 | Disable Footprints email attachment | Minor |  | Yes
MISC-7 | MISC-6 Request display1, display2, and display RR from DNS admins | Minor
GOCTICKET-75 | When non-Footprint user update a ticket, it sets the name to "goc". | Major |  | No
GOCTICKET-67 | Metrics Reporting Bug | Minor |  | No
GOCTICKET-60 | Find a way for user to chose a better ticket title | Minor |  | No
GOCTICKET-53 | GOCTICKET-45 Show associated ticket for each resource in MyOSG | Minor |  | No
GOCTICKET-50 | GOCTICKET-45 Add "Hot Issue" button | Minor |  | No
GOCTICKET-49 | GOCTICKET-45 Similar ticket search | Minor |  | No
GOCTICKET-47 | GOCTICKET-45 Ticket Metadata Templates | Minor |  | No
GOCTICKET-46 | GOCTICKET-45 Blank GOC Ticket Creation Form | Minor |  | No
GOCTICKET-45 | Implement action items from GOC user experience lab | Minor |  | No
GOCTICKET-36 | Support center flag to indicate unresponsive ones | Minor |  | No
GOCTICKET-18 | New Ticket View - All | Minor |  | No
GOCTICKET-12 | Investiage why FP SOAP API is so slow. | Minor
DISPLAY-8 | Create 30-day graphs | Minor |  | No
BDII-14 | Improve BDII server status page | Major |  | No
BDII-13 | is1 still receiving file from somewhere it shouldn't | Major |  | No
BDII-12 | Retire site count monitor script with munin alerts from infosys graph | Minor |  | No
BDII-11 | Don't let CeMon BDII upgrade stall | Major |  | No
BDII-9 | BDII-8 Document steps required to: Allow SEs to publish to PRODUCTION BDII | Major |  | No
BDII-6 | Create Summary Report of Diff between reources reporting to CEMon (is1 vs is2) | Major |  | No