## Sheet1
WBS_Number | Work_Item | Start_Date | End_Date | Owners | Staff | Metrics
3.1 | Metrics |  |  | BB
3.1.1 | Metrics Analysis |  |  | RG | RG
3.1.1.1 | Metrics requirements, definition, and liaison with existing information sources | 2010-10-01 | 2011-09-30 | RG | RG
3.1.1.2 | Data mining and filtering and derived metrics data management | 2010-10-01 | 2011-09-30 | RG | RG
3.1.1.3 | Creation of OSG intelligence and key analytics | 2010-10-01 | 2011-09-30 | RG | RG
3.1.1.4 | Communicate interpretations in various forums (reports, blog, newsletter articles) | 2010-10-01 | 2011-09-30 | RG | RG
3.1.2 | Metrics Liason/Coordination |  |  | BB | BB
3.1.2.1 | Gratia Liason | 2010-10-01 | 2011-09-30 | BB | BB
3.1.2.2 | MyOSG Liason (revisit / redefine?) | 2010-10-01 | 2011-09-30 | BB | BB
3.1.2.3 | Refine and deliver Gratia reports | 2010-10-01 | 2011-09-30 | BB | KA
3.1.2.4 | Define strategy for pilot and cloud accounting | 2010-10-01 | 2010-11-01 | BB | BB
3.1.3 | Reporting and Operations |  |  | BB | BB
3.1.3.1 | Deploy all metrics reports at GOC | 2010-10-01 | 2010-12-01 | BB | BB, SH
3.1.3.2 | Continue coordination of normalization constants for WLCG | 2010-10-01 | 2011-10-01 | BB | AC
3.1.3.3 | Monthly WLCG/eJOT reports | 2010-10-01 | 2011-10-01 | BB | AC
3.1.3.4 | Ongoing maintenance of metrics queries | 2010-10-01 | 2011-10-01 | BB | BB, AG
3.1.3.5 | OSG Display upkeep and maintenance | 2010-10-01 | 2011-10-01 | BB | BB, SH
3.1.3.6 | Ongoing maintenance and evangelism of the consistency RSV probe | 2010-10-01 | 2011-10-01 | BB | BB
3.1.3.7 | Monthly thumbnail reports | 2010-10-01 | 2011-10-01 | BB | JL