## Slide 1: OSG’ Planning work in progress… Major stakeholder meeting – August 17th 2010 Council Meeting - August 18th 2010 Ruth Pordes OSG Executive Director, on behalf of the OSG Project V4

## Slide 2: Schedule (run past DOE and NSF)
Funding available for current staff through to Sept 30th 2011.
Develop draft proposal by October 15th. Need small working team for writing..
  how detailed should it be?
  Look at different scopes.
Present to agency sponsors.
  Have talked briefly with DOE OHEP, ASCR, NP, NSF MPS to request JOT or similar forums/fora in early November. (This is a better time for Alan Stone than October). NSF MPS are on board with this pending talking with OCI.
Propose to have proposal at least to DOE and NSF by February 1 2011.
Make a general enough model of the work and organization deliverables that we can respond to specifics quickly.

## Slide 3: Preparatory Documents – seen before
Software Hardening http://osg-docdb.opensciencegrid.org/cgi-bin/ShowDocument?docid=866
Campus https://twiki.grid.iu.edu/twiki/pub/Council/Agenda2009Aug11/NCI__the_Campuses_v3.pdf
Workforce development http://osg-docdb.opensciencegrid.org/cgi-bin/ShowDocument?docid=864
OSG-TG Principles of Collaboration https://twiki.grid.iu.edu/twiki/pub/Council/Agenda2009Aug11/OSG_TG_SharedPriciples_v4-3.docx
Current Architecture (Draft) http://osg-docdb.opensciencegrid.org/0009/000966/001/OSG-Architecture-V2.pdf
ATLAS/CMS Response to DOE/NSF program managers regarding OSG https://twiki.grid.iu.edu/twiki/pub/Council/Agenda2010Mar11/USLHC-OSG-Council-03-2010-1.ppt
Definition of Satelliteshttp://osg-docdb.opensciencegrid.org/0009/000913/002/OSG%20Interface%20to%20Satellite%20Projects%20v3.pdf

## Slide 4: Annual Staff retreat in July
Core ET and area coordinators discussed program of work, ideas, out-of-band brainstorming, principles etc to help with an outline of a proposal to put before the Council. Here it is:
OSG 2011 – 2016
PI Input
Context
Vision
Science and Engineering Benefits
Customer profiles
Major accounts
Standard accounts
Cooperating Communities
Possible
Accomplishments to Date
Key Directions for 2011 – 2016
Organization
Project Management improvements
Program of Work

## Slide 5: PI Input
To be a success such that no one will dream to question the existence of OSG.
We support open distributed science. Noone else can do it.
What we need to do:
Become more efficient.
Replace complex/difficult pieces of software stack from VDT and clean things up.
Engage with first class of scientists.
Do we solve new users/VO problems with technology or services?
Start from and Preserve the local environment and then extend this to OSG.
Success of institution A is also the success of institution B because we are all in OSG.
Satellites are key:
Endorse and manage the overhead of satellites.
More efficient to have multiple projects than running a 12-15 million $ project.
OSG project should anchor satellites.
Data:
HDFS, Consider approach/principles of contributing to open source community based software: e.g? hadoop, fedora, apache/squid....
WLCG Demonstrators - are these the best approach with Caching on demand as the mantra.
Need to consider the Theory of data and data management.
Would be extremely successful if we could have offered a storage and backup solution to the biologists.
Consider how to successfully address needs at the end of the WBS: Documentation. Education. Management.

## Slide 6: Context
Integrative collaboration. End-user researcher requirements drive activities.
Sustaining quality production for active science societies
Transformation and innovation in end-to-end distributed science
Anchoring satellite projects for independent but synergistic contributions
Focus on hundreds of commodity cluster resources of various types, connected via production and/or wide area experimental networks.
Additionally providing access to specialized resources for specific tests and/or applications.
Closer ties and partnerships with DOE ASCR facilities and NSF XD and CF21 programs.

## Slide 7: DOE ASCR facilities
ESNET
  Proposed a model of association for discussion.
  What is in the “Facility Operations” for potential ?
    Operational Support.
    Operational Hosted Services.
    Availability, accounting and monitoring of Registered (Site and other) Services.
    Operational Security.
    Support services – documentation, mail lists etc.
NERSC
  First discussion of synergistic areas with s/w

## Slide 8: Strategic partnership with ESNET is in OSG’s interest.

## Slide 9: NSF CF21
2 XD CMS proposals submitted July 16th.
Separate letters of support/commitment from OSG
First review mid-September.
NSF XD
SSI/SSE/S2I2
Workshop to provide input to "Distributed Computing, Multidisciplinary Science and the NSF's Software Insitute Program,” under the direction of Miron Livny, Ian Foster, Ruth Pordes. https://sites.google.com/site/distributedcomputings2i2/ Workshops at end of August. Report in mid-september to NSF.

## Slide 10: Vision
Extend current “society” to include other communities, projects, partners.
Fully integrate the campuses as part of the national cyberinfrastructure.
Stronger partnerships with DOE distributed computing facilities and NSF XD, CF21, and future programs, advances and innovations in this area.
Extend the current collaborations to interface to and benefit from satellites.
Distributed computing laboratory for study and evolution
Enable science and engineering – ie both pure and applied research.
Be agile with respect to new capabilities needed by the stakeholders.
Help with the design and planning, requirements and constraints on external development.
Help with hardening, transition to production, integration and support.

## Slide 11: Science and Engineering Benefits – Customer profiles – (1
Major accounts
Designated by the funding agencies rather than by OSG itself. Should they have a separate “group” for discussions/planning/decisions? Do we gain by formalizing it or not?
LHC x 10 in data size and computation
LIGO x 10 in data size and computation, open data, going global
Standard accounts – are these subdivided
Incubator? Production? Can we clarify “At –Large” “Collective” better for OSG’?
Run II – transition to use non-owned resources
Glue-X – part way on the path to dependency on OSG
Alice – request to be at the table as a major stakeholder.
STAR
SBGrid – NIH – request to be at the table as a major stakeholder.
Sum (0-> ) of the “independent investigators/small groups”

## Slide 12: Science and Engineering Benefits – Customer profiles (2
Cooperating Communities
Multidisciplinary regional (campus, state, area), enablers, engaging local communities:
HCC
Glow
“OSG”
“South East/McGee”
…
Sociotechnologists
Computer science – basic and applied
Possibilities
DUSEL/LBNE
SNS/APS
DES
Networking projects (I2, ESNET)

## Slide 13: Accomplishments to Date
Met LHC deliverables
Met LIGO Needs
Enabled other physics and non-physics science
Proven leading the (Virtual) Society organizational framework, principles, technologies and methods to include new entrants.
Success in federated operation with EGEE (now EGI) and WLCG.
Credited by DOE and NSF program offices and projects (including ESNET, I2 and Teragrid, letters of commitment to both XD teams) as part of the ongoing distributed computing landscape.
Demonstrated that the whole is greater than the sum of the parts for existing members, new entrants and new science.
Advanced the national interests in services, support, and software for distributed systems physics and beyond.
Enabled science for multiple “SGs”
Improved project management processes
:

## Slide 14: Key Directions for 2011 – 2016
Meet LHC operational needs (see Assessment document)
Meet LIGO software needs
Growing the expertise; providing career paths for the staff and participants.
Role and contributions of Satellites
Support production, security, users, for an increasing set of communities.
Continue and expand support for Software collections.
Where does the testbed fit in?
Addressing LHC futures:
Configuration Management
Integration of Commercial and Scientific Clouds
Usability for collaborative analysis
Active management of shared capacity, utilization planning, accounting, reporting, change
End-to-End Data Management challenges in light of advanced networks
Ensure campus are “first class objects” in national CI
Integration, hardening, support and broadening the usability to other VOs building on LHC data management/access demonstrators
Addressing LIGO futures:
Software distributions fully integrated into the underlying OS?
Reuse and broader support of LIGO security model?
Better transparency between LDG and OSG and production support for additional analysis.
Run II, SBGRid, Glue-X, STAR… futures:
:
:

## Slide 15: Organization (1
Consortium
Council
Science Advisory Group
Management Teams
Project Core
Satellites
External projects
Partnerships
Which other successful organizations are we most like (and might learn from) for parts of OSG, whereas as a whole OSG may not be similar to any: e.g.Lockheed Martin, eBay, Redhat/Ubuntu -.
As we grow our customer base, sphere of influence, leaders, capabilities and capacities there are natural lines of distinction between larger groupings of our work than the >14 areas that we now have. Does having these larger groupings – tied at the hip to the overall core OSG project –make us more effective and more efficient towards our pervasive national ambitions.
With a commitment to a broader set of core stakeholders – and a thrust to a deeper support of biologist and non-physics – need to revisit a broader Management structure/Executive Team and a more active, focused Council. With Satellites and/or cooperative partnerships as a more important part of the model will need additional coordination and communication effort across ET and Council. Can this be an action item from the August 18th Council meeting?

## Slide 16: Organization (2 – rationalize current areas..)
Project
Connecting organizational staff including cross-cutting Security (oversight, compliance, auditing), Architecture and Technology Group, Assessment and policies/economic model, Council staff, Project Management, Satellite Interfaces, Communications and External Relations, Documentation. Additionally, the following have effort in all the specific areas below and are coordinated from the cross-cutting staff area:
  Security
  WLCG
User Support
Software
Production and Operation
Medium term technology investigations
Campus infrastructures
Extensions as closely aligned Satellites
Council staff
Estimate that Council chair effort is ~1 FTE : 0.5 Chair + 0.5 FTE administrative support. Include this in the cross-cutting project staff.
Project Management improvements
Plan, decide, act, assess; Tradeoffs, training;
Methodologies: cmm-sei, agile software, test first “development”
Relationship to transformation and innovation
Solid and robust and/or principled evolution

## Slide 17: Program of Work
US ATLAS, US CMS, (US ALICE), WLCG Operations (see assessment document). LIGO, standard customer operations.
Production and User Support.
Software & Security.
Create campus societies, core from the Tier-3s.
Provide access to greater diversity of resources as they become available including commercial and scientific clouds, federated infrastructures.
International collaborations..
Distributed and layered data center of unique scale and reach: (>100 universities, >5 national labs, >5 organizational peers).
  Adopt recognized methodology (ITIL, eTOM, ISO20K, other..).
  Continuous improvement.
  Management of change.
  Transform and innovate.
  Investigate outsourcing by the end of the project
Collaborate with/contribute to open source projects we. (do or might) depend on:
Additional capabilities seen as on the community roadmap (not yet explicit):
  Integration with dynamic network provisioning and overlays.
  More complex workflows.
  Data curation.
  Integration with other security /privacy/management services.
International Collaborations through existing OSG communities: e.g. European clients

## Slide 18: Satellites
Contributing specific services and deliverables to the mission of the OSG Consortium.
Existing:
CI team
CorralWMS,
ExTENCI,
HTPC,
ANI,
LIGO
PIF,
DISUN
Proposed
Condor/ATLAS/CMS/LIGO (submitted)
?Nano@UNL (submitted)
Education/AIM/Summer School
Integrated Networks
SBGrid
ISGTW
LIGO PIF’
DISUN’
SE Regional Grid
Supplements
Condor
Build and Test
Overhead to the Cross-organizational staff effort (at Council or Project layer) <~1 month/Satellite.

## Slide 19: From Aug 2009 & Mar 2010

## Slide 20: Core Mission - 1
Continue operations of the production infrastructure:
Improve the usability and reduce the effort to operate at all levels.
Maintain a usable, secure, robust, distributed facility open to all contributors (resources and applications) in the scientific, research, and education domains. (No commercial use).
Continue support for the OSG Virtual Data Toolkit for the OSG Consortium and other projects, including the evolution of WLCG and EGI.
Solidify presence and usability of shared cyberinfrastructure within the US University campuses and transparent use of local and wide area cyberinfrastructure nationally.

## Slide 21: Core Misson - 2
Extend:
The capabilities and capacities offered for the stakeholders at the table, including those represented on the OSG Consortium Council, VOs represented by the “at-large” Council member, and users through the Campus, Engagement, Education and Outreach activities.
Strengthen organizational, operational and technical gateways between OSG and other peer infrastructures including the TeraGrid and XD, and EGI and NGIs in Europe, Campus and regional grids in the US and off-shore, and commercial cloud resource providers.
Workforce training for the future…TBA.

## Slide 22: Operations Services, Security, Sites
Critical operations center services – problem recording, triaging, ticketing and ownership; gateways and publishing to the WLCG services.
Provide frameworks and exemplars for general utility to the communities within the operations framework
Lower the barrier to use, improve usability of all services and installations.
Increase automation, alarming.
Reduce the impact of site-to-site variability and lower the barrier to use.
Operational support for US LHC Tier 3s and small sites in general.
Active monitoring and notification of software bugs in s/w.
Support for Virtual Machines across all operational services impacted (STAR).
Improve usability of end-to-end security infrastructure – identity token acquisition and management.
Support for MPI (CIGI, LIGO?, SBGrid)
Increase the resources accessible for sharing (CDF, D0)
Help grow sustainable and usable (lower the barrier to entry) regional grids (NYSGrid).
Campus grids. (GPN, GROW)