## Sheet1
WBS | Act-Num | Activity | Performance Goal | InCharge | Status after 12/31/2011
6.1 | 1 | Quarterly institutional cost reports and overall budget summary to OSG-ET | Executed within 1-month after end of each quarter; with coverage > 90% of budgeted institutions. | Sehgal, Lockhart, Werner | Completed for quarter ending Sept 30, 2011
6.1 | 2 | Weekly Area Coordinator Meeting to review work-plan progress (rotating schedule with each Area covered about every 6 weeks) | Each functional area reviewed with period not to exceed 8 weeks. | Garzoglio, Sehgal, Lockhart | Implemented; now in 2nd round of reviews for all functional areas
6.1 | 3 | Weekly reporting to OSG-ET (based on Area Coordinator meeting) on 1) changes to work plan; or 2) items in jeopardy and needing assistance | Email report to OSG-ET within 2 business days of overall status, recent changes, and items needing attention. | Garzoglio, Sehgal | Progressing as planned; reports are sent to ET with key updates and issues
6.1 | 4 | Periodic meeting (typically 6-8 weeks) with selected external projects (e.g. CDIGS) to coordinate deliverables and requirements | Email report to OSG-ET within 2 business days of overall status, recent changes, and items needing attention. | Garzoglio, Sehgal | CDIGS calls continue on a periodicity of ~6 weeks
6.2 | 1 | Hold regular documentation meetings with all document coordinators | <10 additional meetings needed during the year due to non- attendance by the relevant documentation coordinator | Weichel | Completeted the release of the new navigation and documentation scheme. Meetings transitioned to the Software area.
6.2 | 2 | Monitor the user feedback on the documents and ensure issues and errors are fixed. | Address small documentation comments in <3 days on average throughout the year. | Weichel | Handed over to the regular ticketing system and Software area to address.
6.2 | 3 | Keep on top of new services and software in order to make sure documentation is included in their delivery. | Documentation completeed before delivery in >75% of the instances | Weichel | Documentation was available fornew releases of the software. Now under responsibilities of the software area.
6.3 | 1 | Collect material for, edit and publish the monthly OSG newsletter whose audience is mainly internal to the OSG community, including sponsors and stakeholders. | Increase in number of positive responses to >=10 | Boon | Monthly newsletter has been published. We are finding it much easier to get input now.
6.3 | 2 | Collect material for, edit and publish biweekly ISGTW in collaboration with the international team across the EU and US. | Increase in number of positive responses to >=50 | Boon | iSGTW is being published. The US Editor will be available until June 18th. After which this OSG activity ceases. Any activity will be part of a separate project - satellite.
6.3 | 3 | Reporting as part of the cross-project support area to the Area Coordinators meetings |  | Boon | reports included in 2 area coordinators meetings
6.3 | 4 | Represent OSG communications as part of the XSEDE communications group | Inclusion of >=1 OSG article in XSEDE communications output | Boon, Pordes
6.4 | 1 | Continue contacts beween mentors and students | >5 students using DHTC services during the first six months of FY12 | Cartwright, Weichel | One student attended the AHM and gave a poster and presentation on GridUNESP which was well received.
6.5 | 1 | Monthly contacts with collaborators in Colombia and GridUNESP | Increase of >=2 in number of sites on Coloumbia or GridUNESP infrastructures, increase of >=3 in number of individual Users of Colombia and/or GridUNESP. | Caballero | see above
6.5 | 2 | Ensure accurate and timely responses to requests for information and help from collaborators in Americas | <5 working days in initial response time and follow up to requests for information and help. | Caballero | Ceased as part of the budget reduction for OSG"
6.6 | 1 | Create quarterly reviews of performance of OSG areas already "onboarded" in terms of progress towards strategic goals | Executed within 1-month after end of each quarter for each assessment-deployed area | Gardner | Completed for first area
6.6 | 2 | Collect and synthesize assessment data for each OSG area that has been "onboarded" on a 6 week time basis; provide this data on an approximately weekly basis to OSG project management for Area Coordinator meetings. | Each functional area that has been onboarded assessed with period not to exceed 8 weeks. | Gardner | Completed for first area
6.6 | 3 | Periodically meeting (approximately monthly or as deemed necessary) with the Project Manager to review and interpret assessment performance data collected from a strategic view point, and the overall assessment workflow with Area Coordinators and others, as appopriate | Sumarize review activity and key findings and forward action items to the OSG Project manager within 2 business days of meeting. | Gardner | Bi-weekly Assessment activity meetings have been established with supporting matertials published.
6.6 | 4 | Periodically meeting (approximately quarterly or as deemed necessary) with ET and/or Council to review assemment metrics, key performance indicators, score card and dashboard as applied in the context of the OSG Strategic Plan and make adjustments as necessary | Sumarize review activity and key findings and forward action items to the OSG ET within 2 business days of meeting. | Gardner | First meeting with PI scheduled for January 20