## Sheet1
ID | WBS | Agency Milestone | Name | In Charge | Start Date | Finish Date | % Done | Status
237 | 1.4.4.1 | No | Organize Weekly-VO-Forum teleconferences, inviting select VOs and peer OSG Areas. | Rana, Ritchie, Teckenbrock | 2009-10-01 | 2010-09-30 | 25% | This is on-going. Marcia has been chairing the call and doing minutes.
241 | 1.4.4.5 | No | Collect VOs scientific publications (including ATLAS, CMS, LIGO) for annual DOE & NSF reports. | Ritchie, Rana | 2009-10-01 | 2010-09-30 | 0% | We have had discussions about helping us collect information between the Fermilab library and us.
427 | 3.2 | No | Communications and Education | Ritchie | 2009-10-01 | 2010-09-30 | 0%
428 | 3.2.1 | No | Provide Communications | Ritchie | 2009-10-01 | 2010-09-30 | 0%
429 | 3.2.1.1 | No | Provide Communications to Wide Area Audiences | Ritchie, Teckenbrock | 2009-10-01 | 2010-09-30 | 0%
430 | 3.2.1.1.1 | No | Communicate via print media | Ritchie, Teckenbrock | 2009-10-01 | 2010-09-30 | 0% | Have arranged to refresh OSG post cards based on Supercomputing 08 and 09 materials
431 | 3.2.1.1.2 | No | Communicate via multi-media | Ritchie, Urish, Teckenbrock | 2009-10-01 | 2010-09-30 | 0% | Some plans for AH in progress.
432 | 3.2.1.2 | No | Provide Communications to External Communicators | Ritchie, Teckenbrock | 2009-10-01 | 2010-09-30 | 0%
433 | 3.2.1.2.1 | No | Communicate via one-on-one email conversations | Ritchie, Teckenbrock | 2009-10-01 | 2010-09-30 | 0% | Only ocassional interactions.
434 | 3.2.1.2.2 | No | Communicate via Quarterly Phone Meetings | Ritchie, Teckenbrock | 2009-10-01 | 2010-09-30 | 0% | Need to schedule Q1
435 | 3.2.1.2.3 | No | Communicate via Annual Face-To-Face at AHM | Ritchie | 2009-10-01 | 2010-09-30 | 0% | Planned as part of AHM in March
436 | 3.2.1.3 | No | Produce Research Highlights | Ritchie | 2009-10-01 | 2010-09-30 | 0% | Some underconsideration
437 | 3.2.1.4 | No | Produce iSGTW | Ritchie, Boon | 2009-10-01 | 2010-09-30 | 25% | Miriam and Dan, the iSGTW co-editors, are continuing to produce a weekly publication with ~5700 subscribers as of December 2009.
438 | 3.2.1.4.1 | No | Convene monthly meeting between iSGTW editor and OSG to identify ideas for articles | Ritchie, Boon | 2009-10-01 | 2010-09-30 | 25% | One lunch meeting held.
439 | 3.2.1.5 | No | Produce OSG News | Ritchie, Teckenbrock | 2009-10-01 | 2010-09-30 | 10% | 1 Newsletter produced
440 | 3.2.2 | No | Provide Education | Ritchie | 2009-10-01 | 2010-09-30 | 0%
441 | 3.2.2.1 | No | Contribute to National CyberInfrastructure? Education Activities | Ritchie | 2009-10-01 | 2010-09-30 | 0% | A proposal with others is in progress.
442 | 3.2.2.1.1 | No | Joint OSG TeraGrid? Student programs at OSG AH | Ritchie, tbd2-uc | 2009-10-01 | 2010-09-30 | 0% | Must launch
443 | 3.2.2.1.2 | No | Joint OSG TeraGrid? Student programs at TG10 | Ritchie, tbd2-uc | 2009-10-01 | 2010-09-30 | 0% | Discussed
444 | 3.2.2.1.3 | No | SuperComputing? 09 Education Programs | Ritchie, tbd2-uc | 2009-10-01 | 2010-09-30 | 0% | Not accomplished.
445 | 3.2.2.1.4 | No | Grace Hopper | Ritchie, tbd2-uc | 2009-10-01 | 2010-09-30 | 0% | Not accomplished.
446 | 3.2.2.2 | No | Publicise OSG Computer Science Fellowship program | Ritchie, tbd2-uc | 2009-10-01 | 2010-09-30 | 0%
447 | 3.2.2.3 | No | Publicise OSG intern and summer student activities | Ritchie, tbd2-uc | 2009-10-01 | 2010-09-30 | 0% | Not accomplished.
448 | 3.2.3 | No | Track Publications | Ritchie, Rana | 2009-10-01 | 2010-09-30 | 0%
449 | 3.2.3.1 | No | Track and document publications By OSG Members | Ritchie, Rana | 2009-10-01 | 2010-09-30 | 0% | Not accomplished.
450 | 3.2.3.2 | No | Track and document publications in which OSG resources are responsible for research results | Ritchie, Rana | 2009-10-01 | 2010-05-30 | 0% | Not accomplished.