## Sheet1
WBS | Agency | TaskName | InCharge | Start | Finish
3.2 | No | Communications and Education | Ritchie | 2010-10-01 | 2011-09-30
3.2.1 | No | Provide Communications | Ritchie | 2010-10-01 | 2011-09-30
3.2.1.1 | No | Provide Materials at Conferences | Ritchie, Teckenbrock | 2010-10-01 | 2011-09-30
3.2.1.2 | No | Provide Communications to External Communicators | Ritchie, Teckenbrock | 2010-10-01 | 2011-09-30
3.2.1.3 | No | Produce Research Highlights | Techenbrock, Ritchie | 2010-10-01 | 2011-05-30
3.2.1.4 | No | Produce iSGTW | Boon, Ritchie | 2010-10-01 | 2011-09-30
3.2.1.5 | No | Produce OSG News | Lockhart, Teckenbrock, Pordes | 2010-10-01 | 2011-09-30
3.2.2 | No | Track and document list of publications in which OSG resources are responsible for science results | Ritchie, Rana | 2010-10-01 | 2011-05-30