## Slide 1: OSG Area Coordinators Meeting Cross-Project Area Report
Ruth Pordes
2/8/2011

## Slide 2: Sub-areas
Assessment
Education
Communications
Project Management
Documentation
International Outreach

## Slide 3
6.6 | Assessment | Gardner |  |  | 
6.6.1 | Review Operations area WBS and define key metrics, targets, trip points against OSG strategic plan | Gardner | 10/1/11 | 11/1/11 | 
6.6.2 | Develop means to present the metrics and assessment as a "balance scorecard" | Gardner | 11/1/11 | 12/1/11 | 
6.6.3 | Work with operations to provide their assessment in the accepted format. | Gardner | 11/1/11 | 12/1/11 | 
6.6.4 | Present assessment to the OSG PM and ET | Gardner | 1/1/12 | 1/20/12 | In person meeting not possible, to be rescheduled. Phone meeting brought Miron up to speed and allowed commentary
6.6.5 | Adapt process based on lessons learned. | Gardner | 2/1/12 | 3/1/12 | 
6.6.6 | Select second area to work with and start work with them | Gardner | 2/1/12 | 3/31/12 | 

## Slide 4
6.3 | 1 | Collect material for, edit and publish the monthly OSG newsletter whose audience is mainly internal to the OSG community, including sponsors and stakeholders. | Increase in number of positive responses to >=10 | Boon | Monthly newsletter has been published. We are finding it much easier to get input now.
6.3 | 2 | Collect material for, edit and publish biweekly ISGTW in collaboration with the international team across the EU and US. | Increase in number of positive responses to >=50 | Boon | iSGTW is being published. There is concern as to what happens after April 1st.
6.3 | 3 | Reporting as part of the cross-project support area to the Area Coordinators meetings |  | Boon | 
6.3 | 4 | Represent OSG communications as part of the XSEDE communications group | Inclusion of >=1 OSG article in XSEDE communications output | Boon, Pordes | 
6.3 | Communication | Boon |  |  | 
6.3.1 | Revise and get agreement for the revision of the OSG communications plan | Boon | 10/1/11 | 12/1/11 | 
6.3.2 | Revise format and framework for the OSG newsletter | Boon | 10/1/11 | 12/1/11 | Partially completed, the new format is easier to use
6.3.3 | When asked provide information to DOE and NSF that communicate OSG’s accomplishments – expected in Dec and/or Jan | Boon, Pordes | 10/1/11 | 3/31/12 | Mainly sent to NSF items related to the US EU collaboration opportunities.

## Slide 5
WBS | TaskName | InCharge | Start | Finish | Status after 12/31/2011
6.4 | Education | Cartwright |  |  | 
6.4.1 | 2011 OSG Summer School | Cartwright |  |  | 
6.4.1.1 | Post video from the 2011 School | Cartwright | 8/1/11 | 3/31/12 | Low priority, no one identified to complete task right now
6.4.2 | 2012 OSG User School | Cartwright |  |  | 
6.4.2.1 | Obtain funding | Cartwright | 1/1/12 | 6/30/12 | Mostly, work on the proposal with XSEDE
6.4.2.2 | Prepare this year’s School | Cartwright | 3/1/12 | 6/30/12 | Advertise, get students, logistics, curriculum, etc.
6.4.2.3 | Deliver the School | Cartwright | 6/1/12 | 6/30/12 | Actual dates TBD
6.4.2.4 | Follow up from School | Cartwright | 7/1/12 | 12/31/12 | 
6.4.3 | OSG Admin School | Cartwright |  |  | 
6.4.3.1 | Define need, scope, and market; explore funding options; define remaining steps | Cartwright | 1/1/12 | 3/31/12 | 
6.4.4 | OSG Students at 2012 AHM | Cartwright, Weichel | 1/1/12 | 3/31/12 | Define, get funding, get students, execute, follow up
6.4 | 1 | Continue contacts beween mentors and students | >5 students using DHTC services during the first six months of FY12 | Cartwright, Weichel | 7 students reported use of DHTC at the October teleconference.
Tim will send email about suggested dates for the summer school soon.
Possibilities are one of the last three of June. Leaning towards the later dates.

## Slide 6
WBS | TaskName | InCharge | Start | Finish | Status after 12/31/2011
6.1 | Project Management | Sehgal, Garzoglio |  |  | 
6.1.1 | Year6a work plans for each area | Sehgal | 8/1/11 | 8/30/11 | Completed as planned
6.1.2 | Implement capture system for ongoing activities (with metric goals) | Sehgal, Garzoglio | 8/22/11 | 9/15/11 | Completed as planned
6.1.3 | Baseline year6A work plans for each area and start tracking | Sehgal | 9/16/11 | 10/15/11 | Completed as planned
6.1.4 | Year6A SOWs signed and subcontracts initiated | Sehgal | 10/1/11 | 11/30/11 | Completed as planned
6.1.4.1 | SOW drafts – Sept 30 | Sehgal | 9/1/11 | 9/30/11 | Completed as planned
6.1.4.2 | Sign-off within OSG – Oct 30 | Sehgal | 10/1/11 | 10/30/11 | Completed as planned
6.1.4.3 | Subcontracts from UW-Madison – Nov 30 | Sehgal | 11/1/11 | 11/30/11 | Completed as planned
6.1.5 | OSG DOE Final report – April 30 | Avery, Sehgal | 3/15/12 | 4/30/12 | *** drop as the dates are outside the defined interval for year6B
6.1.6 | OSG NSF Final Report – Sept 30 | Avery, Sehgal | 8/15/12 | 9/30/12 | *** drop as the dates are outside the defined interval for year6B
6.1.7 | Implement process for OSG Stakeholder Requests | Garzoglio | 10/1/11 | 11/15/11 | Implemented via JIRA at GOC and methods developed for populating and updating this database; currently in execution
6.1.8 | Develop project Plan for DigiCert Pilot and track to completion | Sehgal | 10/1/11 | 2/8/12 | **new** Project plan developed and tracking and resolution is in progress; project is proceeding nominally on plan
6.1.9 | Develop project Plan for DigiCert Pilot and track to completion | Garzoglio | 12/1/11 | 3/31/12 | **new** Project plan developed and tracking and resolution is in progress; project is proceeding nominally on plan
6.1.10 | Develop project plan for DigiCert ID CA implementation in OSG (if this is the recommendation from the pilot project) | Sehgal | 2/10/12 | 3/31/12 | **new**

## Slide 7
 |  |  | Project Management |  | 
WBS | Act | Activity | Performance Goal | InCharge | Status after 12/31/2011
6.1 | 1 | Quarterly institutional cost reports and overall budget summary to OSG-ET | Executed within 1-month after end of each quarter; with coverage > 90% of budgeted institutions. | Sehgal, Lockhart, Werner | Completed for quarter ending Sept 30, 2011
6.1 | 2 | Weekly Area Coordinator Meeting to review work-plan progress (rotating schedule with each Area covered about every 6 weeks) | Each functional area reviewed with period not to exceed 8 weeks. | Garzoglio, Sehgal, Lockhart | Implemented; now in 2nd round of reviews for all functional areas
6.1 | 3 | Weekly reporting to OSG-ET (based on Area Coordinator meeting) on 1) changes to work plan; or 2) items in jeopardy and needing assistance | Email report to OSG-ET within 2 business days of overall status, recent changes, and items needing attention. | Garzoglio, Sehgal | Progressing as planned; reports are sent to ET with key updates and issues
6.1 | 4 | Periodic meeting (typically 6-8 weeks) with selected external projects (e.g. CDIGS) to coordinate deliverables and requirements | Email report to OSG-ET within 2 business days of overall status, recent changes, and items needing attention. | Garzoglio, Sehgal | CDIGS calls continue on a periodicity of ~6 weeks

## Slide 8
6.2 | Documentation Architecture | Weichel | 10/1/11 | 3/31/12 | Documentation ready for Release3 releases. New navigation in review. Website being moved to TWiki.
6.2 | 1 | Hold regular documentation meetings with all document coordinators | <10 additional meetings needed during the year due to non- attendance by the relevant documentation coordinator | Weichel | Held 8 meetings as part of Software Team Meeting. Held 2 Doc Fests.
6.2 | 2 | Monitor the user feedback on the documents and ensure issues and errors are fixed. | Address small documentation comments in <3 days on average throughout the year. | Weichel | Only working large issues for Release3 and Navigation so far.
6.2 | 3 | Keep on top of new services and software in order to make sure documentation is included in their delivery. | Documentation completeed before delivery in >75% of the instances | Weichel | Documentation was available for first 2 releases of Release3.

## Slide 9
6.5 | International Outreach | Caballero |  |  | 
6.5.1 | Plan and execute VO Workshop in Colombia | Caballero, Severini | 8/1/2011 | 3/31/2012 | No request for Workshop in Colombia for 2012, so far. There was a request for an “trainers training” school for 2011, but it was rejected. Brazil may request a workshop for 2nd quarter of 2012
6.5.2 | Prepare for Visitor Program in summer 2012 | Caballero, Severini |  |  | done. Final hosting institutions are GOC and FNAL.
6.5.2.1 | Create checklist for Visitor Program | Caballero, Severini | 8/11/2011 | 9/30/2011 | Visitor Program was made public.
6.5.2.2 | Communicate and start arrangements for summer visitor program with U Florida | Caballero, Severini, Avery | 11/1/2011 | 3/31/2012 | Univ of Florida is not participating this year.
6.5.2.3 | Communicate and start arrangements for summer visitor program with SBGrid | Caballero, Severini, Sliz | 11/1/2011 | 3/31/2012 | HMS is not participating this year.
6.5 | 1 | Monthly contacts with collaborators in Colombia and GridUNESP | Increase of >=2 in number of sites on Coloumbia or GridUNESP infrastructures, increase of >=3 in number of individual Users of Colombia and/or GridUNESP. | Caballero | Colombia has setup around 10 sites and registered them in OIM. They have an educational VO and started to create a VO on Bio-informatics. Brazil (GridUNESP) is going to setup an OSG ITB.
6.5 | 2 | Ensure accurate and timely responses to requests for information and help from collaborators in Americas | <5 working days in initial response time and follow up to requests for information and help. | Caballero | 

## Slide 10: Things to think about
Move of www.opensciencegrid.org to twiki
All Hands meeting
Newsletter
Other training /education?