## Sheet1
Control Type | OSG Control Family | OSG Control Name | Control number | Control Method E/I/T | Last Tested | Frequency | Due Date | Log Entries | Working Comments | POC | Artifact Location | Verified Date | Verified By
Management | Integrate Computer Security Management | Roles and Responsibilities – Line Organization | 2.3.1.1 | E | 2008-09-17 | 6mos |  |  |  | R. Pordes | https://osg-docdb.opensciencegrid.org:440/cgi-bin/RetrieveFile?docid=389&version=17&filename=OSGSecurityPlan.doc
Management | Integrate Computer Security Management | Awareness for OSG Managers | 2.3.1.2 | E |  | 1year |  |  | Mine will send list of OSG awareness materials. | M. Altunay
Management | Integrate Computer Security Management | Accountability of Sites, Users, and Vos | 2.3.1.3 | E |  | 1year |  | Updated Roles and Responsibilities chart inserted in Security Plan. | email questions to RQ confirming GOC is able to bar users. | R. Quick | https://osg-docdb.opensciencegrid.org:440/cgi-bin/RetrieveFile?docid=389&version=17&filename=OSGSecurityPlan.doc
Management | Security Processes | Computer Secuirty Lifecycle Meeting | 2.3.2.1 |  | 2008-09-17 |  |  | Meeting mintues are kept in the twiki. Updated SP accordingly with this new location. | SP updated accordingly w. new minutes archive location. | R. Cudzewicz | https://osg-docdb.opensciencegrid.org:440/cgi-bin/RetrieveFile?docid=389&version=17&filename=OSGSecurityPlan.doc
Management | Security Processes | Briefing of the EB (Area Coordinators) | 2.3.2.2 |  | 2008-09-17 |  |  | Examined minutes kept on the OSG twiki. Security reports to the EB periodically. This control will be changed to consist of minutes of the Area Coordinators monthly meetings. | ask RP if we should change the control, instead of EB meeting should this be Area Coordinators meeting? Every 3 weeks Mine goes to AC meeting. Change approved | M. Altunay | https://twiki.grid.iu.edu/bin/view/Management/AreaCoordinator
Management | Security Processes | Risk Assessment | 2.3.2.3 | E | 2008-10-13 |  |  | Risk Assessment update is due. | Plan needs update. plan last udpated back in 2006. Security Head is the keeper. RC, MA, JB | M. Altunay | https://osg-docdb.opensciencegrid.org:440/cgi-bin/ShowDocument?docid=488
Management | Security Processes | Policies, plans and Procedures | 2.3.2.4 | E |  |  |  |  | asks for appropriate signatures. Ask Alicia Simmons about signatures. | A. Simmons | https://osg-docdb.opensciencegrid.org:440/cgi-bin/ShowDocument?docid=389
Management | Security Processes | Self Assessment | 2.3.2.5 |  |  | annual | 2008-01-10 |  | is there a Division self-assessment mechanism already in place that includes this? Should we combine this with the annual Peer Review? Mine A, Ron C, Jim B, Doug O. | M. Altunay | TBD
Management | Security Processes | Peer review | 2.3.2.6 | [5 empty] | Help Ruth setup a peer review for sometime in Nov 20 Ruth P.
Management | Trust relationships | Approval | 2.3.3.1 | E |  |  |  |  | OIM and GOC managers have access to the records for approval? A record=? | R. Quick | https://oim.grid.iu.edu/
Management | Trust relationships | Documentation | 2.3.3.2 | E | 2008-09-17 | annual | 2008-12-18 | Ruth Pordes examined lists and verified they have been approved. Rc | ask RP to exam list of resourses, Vos and Support centers | R. Pordes | https://oim.grid.iu.edu/pub/resource/show.php
Management | Trust relationships | Roles and Responsibilities | 2.3.3.3 | E/T | 2008-10-13 | annual | 2008-12-18 | Verified list of R&R persons is kept up to date and contact info has been verified accurate. | are these R&Rs in the Contact Spreadsheet Ruth and Jemise keep? Test contact info too. Look in OIM | J. Lockhart | https://osg-docdb.opensciencegrid.org:440/cgi-bin/ShowDocument?docid=757 |  | rc
Management | Trust relationships | Review | 2.3.3.4 |  | 2008-09-17 |  |  | Ruth Pordes examined lists and verified they have been approved. Rc |  | R. Pordes | https://oim.grid.iu.edu/pub/resource/show.php
Operational | Security Training and Awareness | Formal Training | 2.4.1.1 | E | 2008-10-30 | 6mos |  | Formal training program not developed. | need training process, tests developed, verification mechansim. FAILED. (modify control for next year, frequency change to 1yr. Etc | M. Altunay | https://twiki.grid.iu.edu/bin/view/Security/SecurityPlanning#Developing_the_Awareness_and_Tra |  | rc
Operational | Security Training and Awareness | Regular Phone Conf. | 2.4.1.2 |  | 2008-09-29 |  |  | Weekly meetings notes have been kept on OSG Twiki |  | M. Altunay | https://twiki.grid.iu.edu/bin/view/Security/WeeklySecurityMeetings
Operational | Security Training and Awareness | Security Mailing Lists | 2.4.1.3 |  | 2008-10-13 |  |  | Examined secuirty mailing list archives and membership lists. | Ron C examine security mailing list archives and membership lists | M. Altunay | NA |  | rc
Operational | Security Training and Awareness | Security Briefings, Discussions, Consortium Meetings | 2.4.1.4 | E |  | annual | 2008-12-18 |  | locate cosortium meeting presentations and agendas archives. Verify security value. M. Altunay | M. Altunay
Operational | Incident Response | Incident Planning | 2.4.2.1 | E | 2008-10-07 | annual |  | New procedure doc pending before EB see also https://twiki.grid.iu.edu/bin/view/Security/IncidentResponseProcess |  | M. Altunay | OSG Security list
Operational | Incident Response | Incident Discovery and Mandatory Reporting | 2.4.2.2 | T/I |  |  |  |  | control assessment interviews are sent to OSG Security mailing list. Ronc interview users, test at: https://twiki.grid.iu.edu/bin/view/Security/IncidentDiscoveryReporting | M. Altunay | OSG Security list
Operational | Incident Response | Invocation of the Incident Response Plan | 2.4.2.3 | T/E |  |  |  |  | see above control | M. Altunay | OSG Security list
Operational | Incident Response | Incident Handling | 2.4.2.4 | E |  | annual |  |  | see above control | M. Altunay | OSG Security list
Operational | Incident Response | Incident Analysis and Reporting | 2.4.2.5 | E | 2008-10-02 | annual |  | incidents are kept on the twiki, inspected by ronc https://twiki.grid.iu.edu/bin/view/Security/OSG-SEC-2008-07-16 |  | M. Altunay | OSG Security list
Operational | Data Integrity | Integrity and Availability | 2.4.3.1 | E/I | 2007-11-06 | annual |  |  | ask application owners for changes from last year | M. Altunay | OSG Security list
Operational | Data Integrity | Identification and Handling of Sensitive Personal Data | 2.4.3.2 | E/I | 2007-11-06 | annual |  |  | ask application owners for changes from last year | M. Altunay | OSG Security list
Operational | Data Integrity | Identification and Handling of Restricted Data | 2.4.3.3 | E/I | 2007-11-06 | annual |  |  | ask application owners for changes from last year | M. Altunay | OSG Security list
Operational | Data Integrity | Identification and Handling of Limited Distribution Data | 2.4.3.4 | E/I | 2007-11-06 | annual |  |  | ask application owners for changes from last year | M. Altunay | OSG Security list
Operational | Data Integrity | Classification By the OSG Security Officer | 2.4.3.5 | E | 2008-11-06 | annual |  |  |  | M. Altunay | OSG Security list
Operational | Configuration Management | Monitoring | 2.4.4.1 | E/T | 2007-12-18 | annual | 2008-12-18 |  | verify the location of the artifacts from previous testing |  | https://twiki.grid.iu.edu/twiki/bin/view/Security/ControlsAssessment2007
Operational | Configuration Management | Version Control | 2.4.4.2 | E | 2007-12-18 | annual | 2008-12-18 |  | verify examination results of CVS system, located where? |  | https://twiki.grid.iu.edu/twiki/bin/view/Security/ControlsAssessment2007
Operational | Configuration Management | Security review of proposed changes | 2.4.4.3 | E | 2007-12-18 | annual | 2008-12-18 |  | archive of documented change process meetings, notes, etc. where? |  | https://twiki.grid.iu.edu/twiki/bin/view/Security/ControlsAssessment2007
Operational | Vulnerability Management | General Reporting | 2.4.5.1 | I | 2007-10-10 | annual |  |  | Mine will contact GOC supervisor | M. Altunay | OSG Security TG
Operational | Vulnerability Management | Primary Reporting | 2.4.5.2 | E | 2007-10-05 | annual |  |  |  | M. Altunay | OSG Security TG
Operational | Vulnerability Management | Secondary Awareness | 2.4.5.3 | E | 2007-11-06 | annual |  |  | vulnerability logs examined | M. Altunay | opensciencegrid.org docdb #id 696
Operational | Vulnerability Management | Primary Mitigation | 2.4.5.4 | E | 2007-10-05 | annual |  |  | examine OSG Doc 541, yearly metrics | M. Altunay
Operational | Vulnerability Management | Special Roles, Security Officer | 2.4.5.5 | E | 2007-12-19 | annual | 2008-12-18 |  |  | M. Altunay | OSG Security TG
Operational | Vulnerability Management | OSG Security Life Cycle, Vulnerabilities | 2.4.5.6 | E | 2007-12-19 | annual | 2008-12-18 |  |  | M. Altunay | OSG Security TG
Operational | Vulnerability Management | Vulnerability Awareness | 2.4.5.7 | E | 2007-11-06 | annual |  |  | exam awareness materials | M. Altunay | OSG Security TG
Operational | Physical Access and Site Management | Physical Access | 2.4.6.1 | I | 2007-12-18 | annual | 2008-12-18 |  | ask for changes from last year | R. Quick | OSG Security TG
Operational | Physical Access and Site Management | Console Access | 2.4.6.2 | E | 2007-12-18 | annual | 2008-12-18 |  | edit SP text: Trojan Floppy should be Trojan removable media. |  | OSG Security TG
Operational | Physical Access and Site Management | Network Access | 2.4.6.3 | I | 2007-12-18 | annual | 2008-12-18 |  |  |  | OSG Security list
Operational | Physical Access and Site Management | Network Service Restrictions | 2.4.6.4 | I | 2007-12-18 | annual | 2008-12-18 |  |  |  | OSG Security list
Operational | Physical Access and Site Management | Redundancy | 2.4.6.5 | E | 2007-12-18 | annual | 2008-12-18 |  |  |  | OSG Security list
Operational | Physical Access and Site Management | Data Retention | 2.4.6.6 | I | 2007-12-18 | annual | 2008-12-18 |  |  |  | OSG Security list
Technical | Monitoring | Recording Resource Usage |  | E
Technical | Access Control for Core Admins/Users | Auth for Privileged Access
Technical | Access Control for Core Admins/Users | Auth for Privileged Access
Technical | Access Control for Core Admins/Users | Non-priveleged Access |  | I | 2007-12-18 | annual | 2008-12-18
Technical | Scanning | Web Service Vulnerability
Technical | Scanning | Web Intrusion Detection
Technical | Scanning | Vulnerability |  | E | 2007-12-18 | annual | 2008-12-18
Note on C1: ron c: Red text indicates status in ST&E Tool