## Sheet1
WBS_Number | Work_Item | Start_Date | End_Date | Owners | Staff | Metrics
1.3 | Integration and Sites |  |  | RG
1.3.1 | Improve release processes for ITB |  |  | ST
1.3.1.1 | Adapt ITB testing process to native packaging tools |  |  | ST | ST | Number of new processes defined
1.3.1.2 | Provide installation packages and cache in a managed software repository |  |  | ST | ST | Number of packages modified
1.3.1.3 | Coordinate with GOC to provide testing of central services |  |  | ST | ST | # of services checked
1.3.1.4 | Coordinate with Security to provide testing of ca cert and certificate updates and changes |  |  | ST | ST | # of updates checked,
1.3.1.5 | Coordinate with Storage to provide more testing of storage releases and coverage of additional components as they are added |  |  | ST | ST | # of new packages tested
1.3.2 | Automate VTB & ITB Testing |  |  | ST
1.3.2.1 | Improve existing tests and integrate with osg test suite if possible |  |  | ST | ST
1.3.2.2 | Create site to present historical information on previous test runs |  |  | ST | ST | # of jobs, # of work-types, # submitters
1.3.2.3 | Provide clear and easy to understand report on tests conducted for each release |  |  | ST | ST | # of jobs, # of work-types, # submitters
1.3.3 | Improve management and operation of the persistent ITB |  |  | ST
1.3.3.1 | Define operational SLA for pledged sites. |  |  | ST |  | Number of sites signning SLA
1.3.3.2 | Keep sites up to date with incremental updates. |  |  | ST | NH, IS | Number of sites * number of updates | 9
1.3.3.3 | Commission OSG-dedicated persistent ITB site |  |  | ST | NH | Number of ITB job slots, # GB
1.3.3.4 | Provide continuous monitoring of ITB resources. |  |  | ST | ST | Number of operational tickets + # issues
1.3.3.5 | Provide support for on-demand VO testing. |  |  | ST | IS | Number of VOs testing on-demand
1.3.3.6 | Virtualize ITB resources to allow testing to be reproduced reliably and to aid in troubleshooting |  |  | ST | ST | # of services and systems virtualized
1.3.3.7 | Setup configuration management of ITB site for better reliability |  |  | ST | ST
1.3.4 | Community building for site administrators |  |  | MM
1.3.4.1 | Organize hands-on site administrator’s workshops. |  |  | MM | MM | Number of workshops, toal # participants
1.3.4.2 | Organize site administrators online meetings. |  |  | MM | MM | Number of onine meetings, total # particpants
1.3.4.3 | Support sites through chat support |  |  | MM | ST, IS, MM | Total number of Campfire hours
1.3.4.4 | Contribute to campus grids program of work to foster OSG spreading at the campus level |  |  | MM | ST, MM | Number of workshops+meetings; # new CG
1.3.4.5 | Create sites forum, blog, content collaborative platform |  |  | MM | MM | Number of registered users, page views, forum
1.3.5 | Documentation |  |  | ST, MM
1.3.5.1 | Update documentation based on recommendations of documentation group |  |  | ST | ST, IS, MM | Number of pages: created, edited, removed
1.3.5.2 | Review and prune existing documentation to remove outdated materials |  |  | ST | ST, IS, MM | Number of pages: created, edited, removed
1.3.5.3 | Work with Content Management and Training to develop technical materials relevant to OSG site administrators. |  |  | MM | RE, ST, IS, MM | Number of consultation hours given to C&T
1.3.5.4 | Contribute technical content and documentation relevant for OSG site administrators. |  |  | MM | RE, ST, IS, MM | Number of pages: created, edited, removed
1.3.5.5 | Contribute technical documentation for automated testing |  |  | ST | ST | Number of pages: created, edited, removed
1.3.5.6 | Contribute technical content and documentation relevant for the persistent ITB. |  |  | ST | RE, ST, IS | Number of pages: created, edited, removed
1.3.6 | Small Scale Sites |  |  | MM
1.3.6.1 | Lower level of effort for site administrators for small sites |  |  | MM | MM | average # of FTE needed to administer a small site
1.3.6.2 | Ease entrance into OSG for smaller sites |  |  | MM | MM | # of new sites joining OSG, # of VO and groups in OSG
1.3.6.3 | Work with Production area to provide support for LHC Tier 3 sites. |  |  | MM | MM | Number of consultation hours given to T3
1.3.6.4 | Work with VO area to provide support forfor sites of other VOs, especially smaller sites with limited IT personnel |  |  | MM | MM | Number of consultation hours given to small sites
1.3.6.5 | Create, maintain and use a virtual Tier 3 cluster to test different configurations |  |  | MM | MM | Running cluster, possible options
1.3.6.6 | Test software solution targeting simple deployment for small sites |  |  | MM | MM | # of different configurations and tests