## Effort Detail
Current OSG Software Team Effort
Numbers do not reflect leave
Numbers in italics are estimates by Alain and are not from the staff member
Project | Subproject | Desired End Date | Staff | 2011-02-01 | 2011-03-01 | 2011-04-01 | 2011-05-01 | 2011-06-01 | 2011-07-01 | 2011-08-01 | 2011-09-01 | 2011-10-01 | 2011-11-01 | 2012-12-12
Native Packaging | RPM Transition | 2011-12-16 | Alain | 0 | 0 | 0 | 0 | 5 | 10 | 10 | 10 | 10 | 10 | 10
Native Packaging | RPM Transition | 2011-12-16 | Alex | 0 | 0 | 0 | 0 |  | 5 | 0 | 0 | 0 | 0 | 0
Native Packaging | RPM Transition | 2011-12-16 | Brian | 2011-02-01: 0; 2011-03-01: 0; 2011-04-01: 0; 2011-05-01: 0; 2011-08-01: 0
Native Packaging | RPM Transition | 2011-12-16 | Derek | 0 | 0 | 0 | 0 |  | 24 | 20 | 0 | 0 | 0
Native Packaging | RPM Transition | 2011-12-16 | Doug | 0 | 0 | 0 | 0 | 50 | 60 | 50 | 45 | 15 | 35 | 20
Native Packaging | RPM Transition | 2011-12-16 | Jeff | 2011-02-01: 0; 2011-03-01: 0; 2011-04-01: 0; 2011-05-01: 0
Native Packaging | RPM Transition | 2011-12-16 | Marco | 0 | 0 | 0 | 0 | 0 | 10 |  | 10 | 10
Native Packaging | RPM Transition | 2011-12-16 | Mat | 0 | 0 | 0 | 0 | 45 | 100 | 100 | 100 | 70 | 100 | 100
Native Packaging | RPM Transition | 2011-12-16 | Neha | 0 | 0 | 0 | 0 | 0 | 30 | 25 | 0 | 30 | 25 | 20
Native Packaging | RPM Transition | 2011-12-16 | Scot | 0 | 0 | 0 | 0 | 5 | 25 | 40 | 50 | 30 | 5 | 15
Native Packaging | RPM Transition | 2011-12-16 | Suchandra | 0 | 0 | 0 | 0 | 0 | 40 | 50 | 50
Native Packaging | RPM Transition | 2011-12-16 | Tanya | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 50 | 0
Native Packaging | RPM Transition | 2011-12-16 | Tim | 0 | 0 | 0 | 0 | 24 | 29 | 32 | 41 | 2 | 20 | 28
Native Packaging | Integration Testing | Ongoing | Suchandra | 0 | 0 | 0 | 0 | 0 | 10 | 50 | 50 | 70 | 75 | 30
Native Packaging | Integration Testing | Ongoing | Xin | 2011-11-01: 30; 2012-12-12: 30
Native Packaging | Xrootd | 2011-12-16 | Tim | 2011-02-01: 40; 2011-03-01: 20; 2011-04-01: 2; 2011-05-01: 0
Native Packaging | Xrootd | 2011-12-16 | Mat | 2011-02-01: 10; 2011-03-01: 15; 2011-04-01: 0; 2011-05-01: 0
Native Packaging | Xrootd | 2011-12-16 | Tanya | 2011-02-01: 0; 2011-03-01: 15; 2011-04-01: 18; 2011-05-01: 10; 2011-06-01: 10
Native Packaging | Xrootd | 2011-12-16 | Doug | 0 | 20 | 40 | 35 |  |  |  | 20 |  | 5 | 0
Native Packaging | Bestman | 2011-12-16 | Doug | 2011-09-01: 10; 2012-12-12: 20
Native Packaging | Worker Node | 2011-03-30 | Mat | 2011-02-01: 90; 2011-03-01: 80; 2011-04-01: 10; 2011-05-01: 0
Native Packaging | LIGO distribution maintenance | Ongoing | Tim | 0 | 10 | 0 | 2 |  |  |  | 31 | 38 | 3 | 10
Native Packaging | LIGO distribution maintenance | Ongoing | Mat | 2011-02-01: 0; 2011-03-01: 5; 2011-04-01: 5; 2011-05-01: 5; 2011-10-01: 30
Native Packaging | Community Packaging Plan | 2011-06-01 | Alain | 2011-02-01: 0; 2011-03-01: 0; 2011-04-01: 10; 2011-05-01: 15
Native Packaging | Community Packaging Plan | 2011-06-01 | Tim | 2011-02-01: 0; 2011-03-01: 0; 2011-04-01: 13; 2011-05-01: 3
Native Packaging | Community Packaging Plan | 2011-06-01 | Mat | 2011-02-01: 0; 2011-03-01: 0; 2011-04-01: 20; 2011-05-01: 20; 2011-06-01: 45
CREAM | Basic Functionality with Pacman | 2011-03-31 | Alain | 2011-02-01: 10; 2011-03-01: 10; 2011-04-01: 10; 2011-05-01: 5
CREAM | Basic Functionality with Pacman | 2011-03-31 | Suchandra | 2011-02-01: 0; 2011-03-01: 50; 2011-04-01: 50; 2011-05-01: 10
CREAM | Native Packaging | 2010-04-30 | Mat | 2011-02-01: 0; 2011-03-01: 0; 2011-04-01: 0; 2011-05-01: 0
Pacman VDT Releases |  | Continuous | Scot | 20 | 20 | 20 | 20 | 10 | 5 | 0
Pacman VDT Releases |  | Continuous | Suchandra | 2011-11-01: 3; 2012-12-12: 0
Pacman VDT Releases |  | Continuous | Mat | 2011-02-01: 0; 2011-03-01: 0; 2011-04-01: 65; 2011-05-01: 75; 2011-06-01: 10
VDT Support | General Support | Continuous | Scot | 5 | 5 | 5 | 5 | 5 | 5 | 10 | 5 | 5 | 0 | 5
VDT Support | General Support | Continuous | Alain | 10 | 10 | 10 | 10 | 5 | 5 | 5 | 5 | 5 | 5 | 5
VDT Support | Storage Support Coordination | Continuous | Neha | 2011-02-01: 2; 2011-03-01: 2; 2011-04-01: 2; 2011-05-01: 2
Specific VO Support | LIGO data movement plan | TBD | Tanya | 2011-02-01: 2; 2011-03-01: 2; 2011-04-01: 0; 2011-05-01: 2; 2011-06-01: 2
Specific VO Support | STAR Bestman Support | TBD | Alex | 10 | 10 | 5 | 5 | 10 | 10 | 5 | 5 | 5 | 0 | 0
Specific VO Support | ATLAS Bestman Support | TBD | Alex | 0 | 0 | 15 | 10 | 5 | 10 | 20 | 5 | 5 | 5 | 0
OSG Education |  | 2011-07-01 | Tim | 20 | 30 | 53 | 43 | 72 | 11 | 5 |  |  | 2 | 5
OSG Education |  | 2011-07-01 | Alain | 2011-02-01: 0; 2011-03-01: 10; 2011-04-01: 10; 2011-05-01: 10; 2011-06-01: 25
OSG Education |  | 2011-07-01 | Scot | 2011-06-01: 25
Xrootd config/test |  | Ongoing | Tanya | 2011-02-01: 20; 2011-03-01: 6; 2011-04-01: 0; 2011-05-01: 6; 2011-06-01: 6
Bestman | Development/Maintenance | Ongoing | Alex | 2011-10-01: 0; 2011-11-01: 45; 2012-12-12: 40
Bestman | Development/Maintenance | Ongoing | Neha | 2011-11-01: 25; 2012-12-12: 15
Bestman | Support | Ongoing | Alex | 30 | 30 | 25 | 30 | 30 | 25 | 25 | 40 | 40 | 0 | 0
Bestman | Pre-release testing/configuration | Ongoing | Tanya | 2011-02-01: 16; 2011-03-01: 15; 2011-04-01: 25; 2011-05-01: 10; 2011-06-01: 10
Bestman | Pre-release testing/configuration | Ongoing | Neha | 2011-02-01: 2; 2011-03-01: 2; 2011-04-01: 2; 2011-05-01: 2; 2012-12-12: 15
Development | Pigeon Tools/RSV Probes | Ongoing | Marco | 2011-09-01: 20; 2011-10-01: 20; 2011-11-01: 10; 2012-12-12: 0
Development | Pigeon Tools/RSV Probes |  | Tanya | 2011-02-01: 12; 2011-03-01: 6; 2011-04-01: 1; 2011-05-01: 0; 2011-06-01: 0
Development | Pigeon Tools/RSV Probes | 2011-03-01 | Doug | 2011-02-01: 35; 2011-03-01: 10; 2011-04-01: 0; 2011-05-01: 10; 2011-10-01: 15
Development | Pigeon Tools/RSV Probes | 2011-03-02 | Neha | 2011-02-01: 6; 2011-03-01: 6; 2011-04-01: 0; 2011-05-01: 0
Development | Gratia storage probes |  | Doug | 2011-02-01: 5; 2011-03-01: 5; 2011-04-01: 5; 2011-05-01: 5
Development | Discovery Tools |  | Doug | 2011-02-01: 0; 2011-03-01: 0; 2011-04-01: 0; 2011-05-01: 0
Development | Storage testsuite improvement | TBD | Tanya | 2011-02-01: 2; 2011-03-01: 2; 2011-04-01: 0; 2011-05-01: 2; 2011-06-01: 2
Development | Storage testsuite improvement | TBD | Neha | 10 | 10 | 10 | 10 | 10 | 0 | 0
Development | osg-configure | TBD | Suchandra | 2011-10-01: 15; 2011-11-01: 10; 2012-12-12: 50
Hadoop | Background | 2011-03-01 | Tanya | 2011-02-01: 2; 2011-03-01: 6; 2011-04-01: 10; 2011-05-01: 0; 2011-06-01: 0
Hadoop | Tutorial | 2011-03-01 | Doug | 2011-02-01: 10; 2011-03-01: 0; 2011-04-01: 0; 2011-05-01: 0
Hadoop | Repository | Ongoing | Jeff | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
Hadoop | Testing | Ongoing | Doug | 2011-02-01: 0; 2011-03-01: 10; 2011-04-01: 10; 2011-05-01: 5; 2011-11-01: 10; 2012-12-12: 10
dCache | Configuration | Continuous | Tanya | 2011-02-01: 10; 2011-03-01: 6; 2011-04-01: 5; 2011-05-01: 10; 2011-06-01: 10
dCache | Packaging/Testing | Continuous | Neha | 30 | 30 | 30 | 30 | 40 | 20 | 0
Public Storage | Improve Gratia storage probes | TBD | Doug | 2011-02-01: 0; 2011-03-01: 5; 2011-04-01: 0; 2011-05-01: 0
Public Storage | Investigate globus.org for bulk transfer | TBD | Tanya | 2011-02-01: 0; 2011-03-01: 6; 2011-04-01: 5; 2011-05-01: 5; 2011-06-01: 5
Collaborate with EMI on next-gen SRM |  | TBD | Alex | 2011-02-01: 10; 2011-03-01: 10; 2011-04-01: 10; 2011-05-01: 5; 2011-06-01: 5
Management |  | Continuous | Alain | 60 | 60 | 30 | 60 | 65 | 65 | 85 | 85 | 85 | 85 | 85
Management |  | Continuous | Tanya | 2011-02-01: 6; 2011-03-01: 6; 2011-04-01: 6; 2011-05-01: 6; 2011-06-01: 6
Management | OSG site admin meeting |  | Doug | 2011-07-01: 15
Management | OSG site admin meeting |  | Derek | 2011-08-01: 5
Documentation |  | Continuous | Neha | 2011-10-01: 20
Documentation |  | Continuous | Doug | 2011-10-01: 35
Documentation |  | Continuous | Marco | 2011-09-01: 20; 2011-10-01: 40; 2011-11-01: 60; 2012-12-12: 50
Documentation |  | Continuous | Suchandra | 2011-10-01: 5; 2011-11-01: 0; 2012-12-12: 15
Evaluation |  | Continuous | UCSD | 2011-10-01: 90; 2011-11-01: 50; 2012-12-12: 50

## Project Effort Summaries
Project Effort Summaries
Values
Row Labels | Sum of Feb 2011 | Sum of Mar 2011 | Sum of Apr 2011 | Sum of May 2011 | Sum of Jun 2011 | Sum of Jul-11 | Sum of Aug-11 | Sum of Sep-11 | Sum of Oct-11 | Sum of Nov-11 | Sum of 12-Dec
Bestman | 48 | 47 | 52 | 42 | 40 | 25 | 25 | 40 | 40 | 70 | 70
Pre-release testing/configuration | 18 | 17 | 27 | 12 | 10 | [5 empty] | 15
Support | 30 | 30 | 25 | 30 | 30 | 25 | 25 | 40 | 40 | 0 | 0
Development/Maintenance | [8 empty] | 0 | 70 | 55
Collaborate with EMI on next-gen SRM | 10 | 10 | 10 | 5 | 5
(blank) | 10 | 10 | 10 | 5 | 5
CREAM | 10 | 60 | 60 | 15
Basic Functionality with Pacman | 10 | 60 | 60 | 15
Native Packaging | 0 | 0 | 0 | 0
dCache | 40 | 36 | 35 | 40 | 50 | 20 | 0
Configuration | 10 | 6 | 5 | 10 | 10
Packaging/Testing | 30 | 30 | 30 | 30 | 40 | 20 | 0
Development | 70 | 39 | 16 | 27 | 12 | 0 | 0 | 20 | 50 | 20 | 50
Pigeon Tools/RSV Probes | 53 | 22 | 1 | 10 | 0 |  |  | 20 | 35 | 10 | 0
Storage testsuite improvement | 12 | 12 | 10 | 12 | 12 | 0 | 0
Gratia storage probes | 5 | 5 | 5 | 5
Discovery Tools | 0 | 0 | 0 | 0
osg-configure | [8 empty] | 15 | 10 | 50
Hadoop | 27 | 31 | 35 | 20 | 15 | 15 | 15 | 15 | 15 | 25 | 10
Background | 2 | 6 | 10 | 0 | 0
Repository | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
Tutorial | 10 | 0 | 0 | 0
Testing | 0 | 10 | 10 | 5 | [5 empty] | 10 | 10
Management | 66 | 66 | 36 | 66 | 71 | 80 | 90 | 85 | 85 | 85 | 85
Native Packaging | 140 | 165 | 118 | 90 | 184 | 393 | 427 | 467 | 305 | 308 | 283
Worker Node | 90 | 80 | 10 | 0
Xrootd | 50 | 70 | 60 | 45 | 10 |  |  | 20 |  | 5 | 0
LIGO distribution maintenance | 0 | 15 | 5 | 7 |  |  |  | 31 | 68 | 3 | 10
Community Packaging Plan | 0 | 0 | 43 | 38 | 45
RPM Transition | 0 | 0 | 0 | 0 | 129 | 383 | 377 | 356 | 167 | 195 | 193
Integration Testing | 0 | 0 | 0 | 0 | 0 | 10 | 50 | 50 | 70 | 105 | 60
Bestman | [7 empty] | 10 |  |  | 20
Public Storage | 0 | 11 | 5 | 5 | 5
Specific VO Support | 12 | 12 | 20 | 17 | 17 | 20 | 25 | 10 | 10 | 5 | 0
LIGO data movement plan | 2 | 2 | 0 | 2 | 2
STAR Bestman Support | 10 | 10 | 5 | 5 | 10 | 10 | 5 | 5 | 5 | 0 | 0
ATLAS Bestman Support | 0 | 0 | 15 | 10 | 5 | 10 | 20 | 5 | 5 | 5 | 0
VDT Support | 17 | 17 | 17 | 17 | 10 | 10 | 15 | 10 | 10 | 5 | 10
General Support | 15 | 15 | 15 | 15 | 10 | 10 | 15 | 10 | 10 | 5 | 10
Storage Support Coordination | 2 | 2 | 2 | 2
Xrootd config/test | 20 | 6 | 0 | 6 | 6
(blank) | 20 | 6 | 0 | 6 | 6
Documentation | [7 empty] | 20 | 100 | 60 | 65
(blank) | [7 empty] | 20 | 100 | 60 | 65
Evaluation | [8 empty] | 90 | 50 | 50
(blank) | [8 empty] | 90 | 50 | 50
Pacman VDT Releases | 20 | 20 | 85 | 95 | 20 | 5 | 0 |  |  | 3 | 0
(blank) | 20 | 20 | 85 | 95 | 20 | 5 | 0 |  |  | 3 | 0
OSG Education | 20 | 40 | 63 | 53 | 122 | 11 | 5 |  |  | 2 | 5
(blank) | 20 | 40 | 63 | 53 | 122 | 11 | 5 |  |  | 2 | 5
Grand Total | 500 | 560 | 552 | 498 | 557 | 579 | 602 | 667 | 705 | 633 | 628

## Staff Effort Summaries
Values
Row Labels | Sum of Feb 2011 | Sum of Mar 2011 | Sum of Apr 2011 | Sum of May 2011 | Sum of Jun 2011 | Sum of Jul-11 | Sum of Aug-11 | Sum of Sep-11 | Sum of Oct-11 | Sum of Nov-11 | Sum of 12-Dec
Alain | 80 | 90 | 70 | 100 | 100 | 80 | 100 | 100 | 100 | 100 | 100
Alex | 50 | 50 | 55 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 40
Doug | 50 | 50 | 55 | 55 | 50 | 75 | 50 | 75 | 65 | 50 | 50
Jeff | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
Mat | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
Neha | 50 | 50 | 44 | 44 | 50 | 50 | 25 | 0 | 50 | 50 | 50
Scot | 25 | 25 | 25 | 25 | 45 | 35 | 50 | 55 | 35 | 5 | 20
Suchandra | 0 | 50 | 50 | 10 | 0 | 50 | 100 | 100 | 90 | 88 | 95
Tanya | 70 | 70 | 70 | 51 | 51 | 50 | 50 | 50 | 0
Tim | 60 | 60 | 68 | 48 | 96 | 40 | 37 | 72 | 40 | 25 | 43
Brian | 0 | 0 | 0 | 0 |  |  | 0
Derek | 0 | 0 | 0 | 0 |  | 24 | 25 | 0 | 0 | 0
Marco | 0 | 0 | 0 | 0 | 0 | 10 |  | 50 | 70 | 70 | 50
UCSD | [8 empty] | 90 | 50 | 50
Xin | [9 empty] | 30 | 30
Grand Total | 500 | 560 | 552 | 498 | 557 | 579 | 602 | 667 | 705 | 633 | 628