## Sheet1
WBS Number | Work Item | Start Date | End Date | In Charge
1.1 | Software Tools Group |  |  | Roy
1.1.1 | Ongoing OSG support and documentation | 2010-10-01 | 2011-09-30 | Roy, Levshina
1.1.1.1 | Direct user support | 2010-10-01 | 2011-09-30 | Roy, Levshina
1.1.1.2 | Maintain OSG-owned packaging and configuration | 2010-10-01 | 2011-09-30 | Roy, Levshina
1.1.1.3 | Update software in the OSG software stack, as needed | 2010-10-01 | 2011-09-30 | Roy, Levshina
1.1.1.4 | Continue to improve internal testing of software stack. | 2010-10-01 | 2011-09-30 | Roy, Levshina
1.1.1.5 | Participate in the ITB and VTB processes | 2010-10-01 | 2011-09-30 | Roy, Levshina
1.1.1.6 | Participate in the documentation needs of OSG, as related to software | 2010-10-01 | 2011-09-30 | Roy, Levshina
1.1.1.7 | Maintain documentation aimed at Tier 3s | 2010-10-01 | 2011-09-30 | Roy, Levshina
1.1.2 | Ongoing partner support | 2010-10-01 | 2011-09-30 | Roy, Levshina
1.1.2.1 | Support WLCG's use of the VDT | 2010-10-01 | 2011-09-30 | Roy
1.1.2.2 | Participate in WLCG via EMT meetings | 2010-10-01 | 2011-09-30 | Roy
1.1.2.3 | Provide quarterly VDT reports to WLCG | 2010-10-01 | 2011-09-30 | Roy
1.1.2.4 | Participate in WLCG Technical group, report to ET as appropriate | 2010-10-01 | 2011-09-30 | Roy, Levshina
1.1.2.5 | Support software collaboration with TeraGrid | 2010-10-01 | 2011-09-30 | Roy
1.1.2.6 | Support other grid's usage of VDT (GridUNESP, NGS, others as appropriate) | 2010-10-01 | 2011-09-30 | Roy
1.1.2.7 | Participate in OSG/CDIGS meetings | 2010-10-01 | 2011-09-30 | Roy
1.1.2.8 | Monitor WLCG install capacity activites related tot SE Glue Schema | 2010-10-01 | 2011-09-30 | Levshina
1.1.3 | Build software not currently being built in the software stack
1.1.3.1 | Bestman | 2010-10-01 | 2010-11-30 | Roy, Levshina
1.1.3.2 | VOMS Admin | 2010-10-01 | 2010-12-30 | Roy
1.1.3.3 | GUMS | 2010-10-01 | 2010-11-30 | Roy
1.1.4 | Upgrade or improve software infrastructure
1.1.4.1 | CREAM | 2010-10-01 | 2010-10-30 | Sfiligoi
1.1.4.1.1 | Investigate detailed effort to add CREAM to software stack | 2010-10-01 | 2010-10-30 | Roy
1.1.4.1.2 | Report to ET on effort to add CREAM; expand WBS based on feedback | 2010-10-01 | 2010-10-30 | Roy, Sfiligoi
1.1.4.2 | Globus 5 |  |  | Roy
1.1.4.2.1 | Add GridFTP 5 to software stack (for CREAM support) | 2010-10-01 | 2010-10-30 | Roy
1.1.4.2.2 | [After CREAM] Add GRAM 5 to software stack | ? | ? | Roy
1.1.4.3 | Update to new VOMS/VOMS Admin | 2010-10-01 | 2010-12-30 | Roy
1.1.4.4 | Submit Host | 2010-01-01 | 2010-01-31 | Roy
1.1.4.4.1 | Define contents of submit host (with Fraser) | 2010-01-01 | 2010-01-31 | Roy
1.1.4.4.2 | Report to ET on effort to add submit host; expand WBS based on feedback | 2010-01-01 | 2010-01-31 | Roy
1.1.4.5 | Operations Center Software (with Quick) | 2010-01-01 | 2010-01-31 | Roy
1.1.4.5.1 | Define contents of Operations Center software with GOC | 2010-01-01 | 2010-01-31 | Roy
1.1.4.5.2 | Elaborate WBS based on definition | 2010-01-01 | 2010-01-31 | Roy
1.1.4.6 | Bestman | 2010-10-01 | 2011-09-30 | Levshina
1.1.4.6.1 | Work with Bestman developers to minimize downtime for storage upgrade | 2010-10-01 | 2011-09-30 | Levshina
1.1.4.6.2 | Evaluate and test Bestman 2 | 2010-10-01 | 2010-11-01 | Levshina
1.1.4.7 | dCache | 2010-10-01 | 2011-09-30 | Levshina
1.1.4.7.1 | Work with dCache developers to minimize downtime for storage upgrade | 2010-10-01 | 2011-09-30 | Levshina
1.1.4.7.2 | Evaluate and test dCache support for access control lists | 2010-10-01 | 2011-12-01 | Levshina
1.1.4.7.3 | Evaluate and test dCache SRM load balancing | 2010-12-01 | 2011-02-01 | Levshina
1.1.4.8 | Xrootd | 2010-10-01 | 2010-12-01 | Levshina
1.1.4.8.1 | Evaluate and test Xrootd and XrootdFS security | 2010-10-01 | 2010-12-01 | Levshina
1.1.4.9 | Pigeon Tools (for storage team to debug problems) | 2010-10-01 | 2011-02-01 | Levshina
1.1.4.9.1 | Incorporate into RSV | 2010-10-01 | 2011-01-01 | Levshina
1.1.4.9.2 | Incorporate into upcoming pilot job test suite | 2011-01-01 | 2011-02-01 | Levshina
1.1.4.10 | Community Chest Tools | 2010-10-01 | 2011-09-30 | Levshina
1.1.4.10.1 | Collect from site admins, test and add tools for Hadoop, Xrootd. | 2010-10-01 | 2011-09-30 | Levshina
1.1.4.11 | NEES Archiver Toolkit | 2011-01-01 | 2011-04-01 | Levshina
1.1.4.11.1 | Work with NEES to plan effort | 2011-01-01 | 2011-02-01 | Levshina
1.1.4.11.2 | Expand WBS in consultation with ET | 2011-02-01 | 2011-04-01 | Levshina
1.1.4.12 | SHA-1 transition |  |  | Roy
1.1.4.12.1 | With assistance from security team, evalute move away from SHA-1 | ? | ? | Roy
1.1.4.12.2 | Expand WBS based on evaluation | ? | ? | Roy
1.1.5 | Public (Opportunistic) Storage | 2010-10-01 | 2011-03-01 | Levshina
1.1.5.1 | Define requirements | 2010-10-01 | 2010-11-01 | Levshina
1.1.5.2 | Evaluate iRODS to see if matches requirements | 2010-10-01 | 2010-11-01 | Levshina
1.1.5.3 | If needed, evaluate other tools | 2010-11-01 | 2011-02-01 | Levshina
1.1.5.4 | Report to ET, expand WBS based on feedback | 2011-02-01 | 2011-03-01 | Levshina
1.1.6 | Native Packaging
1.1.6.1 | Complete glexec packaging | 2010-08-01 | 2010-10-30 | Roy
1.1.6.2 | Complete worker node packaging | 2010-10-01 | 2010-12-30 | Roy
1.1.6.3 | Evaluate next steps in native packging, expand WBS appropriately | 2010-12-01 | 2010-12-30 | Roy, Levshina
1.1.7 | OSG Summer School |  |  | Roy
1.1.7.1 | Prepare proposal for summer school. (With TeraGrid?) | 2010-10-01 | 2010-12-30 | Roy, Cartwright
1.1.7.2 | Organize summer school | 2011-01-01 | 2010-07-01 | Roy, Cartwright
1.1.7.3 | Run summer school | 2010-07-11 | 2010-07-22 | Roy, Cartwright