## Effort Detail
Current OSG Software Team Effort
Numbers do not reflect leave
Project | Subproject | WBS Item(s) | Desired End Date | Staff | 2011-02-01 | 2011-03-01 | 2011-04-01 | 2011-05-01 | 2011-06-01
Native Packaging | Xrootd | None | TBD | Tim | 40 | 20 | 2 | 0
Native Packaging | Xrootd | None | TBD | Mat | 10 | 15 | 0 | 0
Native Packaging | Xrootd | None | TBD | Tanya | 0 | 15 | 18 | 10
Native Packaging | Xrootd | None | TBD | Doug | 0 | 20 | 40 | 0
Native Packaging | Worker Node | 1.1.6.2 | 2011-03-30 | Mat | 90 | 80 | 10 | 10
Native Packaging | LIGO distribution maintenance |  | Ongoing | Tim | 0 | 10 | 0 | 0
Native Packaging | LIGO distribution maintenance |  | Ongoing | Mat | 0 | 5 | 5 | 0
Native Packaging | Community Packaging Plan | N/A | 2011-06-01 | Alain | 0 | 0 | 10 | 10
Native Packaging | Community Packaging Plan | N/A | 2011-06-01 | Tim | 0 | 0 | 13 | 10
Native Packaging | Community Packaging Plan | N/A | 2011-06-01 | Mat | 0 | 0 | 20 | 0
CREAM | Basic Functionality with Pacman | 1.1.4.1 | 2011-03-31 | Alain | 10 | 10 | 10 | 0
CREAM | Basic Functionality with Pacman | 1.1.4.1 | 2011-03-31 | Suchandra | 0 | 50 | 50 | 0
CREAM | Native Packaging | 1.1.4.1 | 2010-04-30 | Mat | 0 | 0 | 0 | 0
VDT Releases |  | 1.1.1 | Continuous | Scot | 20 | 20 | 20 | 20
VDT Releases |  | 1.1.2 | Continuous | Mat | 0 | 0 | 65 | 50
VDT Support | General Support | 1.1.1.0 | Continuous | Scot | 5 | 5 | 5 | 5
VDT Support | General Support | 1.1.1.0 | Continuous | Alain | 10 | 10 | 10 | 10
VDT Support | Storage Support Coordination | 1.1.1.1 | Continuous | Neha | 2 | 2 | 2 | 2
Specific VO Support | LIGO data movement plan | 1.0.4.2.1 | TBD | Tanya | 2 | 2 | 0 | 2
Specific VO Support | STAR Bestman Support | ? | TBD | Alex | 10 | 10 | 5 | 10
Specific VO Support | ATLAS Bestman Support | ? | TBD | Alex | 0 | 0 | 15 | 10
OSG Summer School |  | 1.1.7 | 2011-07-01 | Tim | 20 | 30 | 53 | 30
OSG Summer School |  | 1.1.7 | 2011-07-01 | Alain | 0 | 10 | 10 | 10
Xrootd config/test |  | 1.1.4.8 | Ongoing | Tanya | 20 | 6 | 0 | 6
Bestman | Support | 1.1.4.6 | Ongoing | Alex | 30 | 30 | 25 | 30
Bestman | Pre-release testing/configuration | 1.1.4.6 | Ongoing | Tanya | 16 | 15 | 25 | 10
Bestman | Pre-release testing/configuration | 1.1.4.6 | Ongoing | Neha | 2 | 2 | 2 | 2
Development | Pigeon Tools/RSV Probes | 1.1.4.9 |  | Tanya | 12 | 6 | 1 | 0
Development | Pigeon Tools/RSV Probes | 1.1.4.9 … | 2011-03-01 | Doug | 35 | 10 | 0 | 0
Development | Pigeon Tools/RSV Probes | 1.1.4.9 … | 2011-03-02 | Neha | 6 | 6 | 0 | 0
Development | Gratia storage probes |  |  | Doug | 5 | 5 | 5 | 5
Development | Discovery Tools |  |  | Doug | 0 | 0 | 0 | 0
Development | Storage testsuite improvement | 1.1.1.4, 1.1.4.6.2, 1.1.4.8.1, 1.1.4.13.1 | TBD | Tanya | 2 | 2 | 0 | 2
Development | Storage testsuite improvement | 1.1.1.4, 1.1.4.6.2, 1.1.4.8.1, 1.1.4.13.2 | TBD | Neha | 10 | 10 | 10 | 0
Hadoop | Background | 1.1.4.13 | 2011-03-01 | Tanya | 2 | 6 | 10 | 0
Hadoop | Tutorial | 1.1.4.14 | 2011-03-01 | Doug | 10 | 0 | 0 | 0
Hadoop | Repository | 1.1.4.15 | Ongoing | Jeff | 15 | 15 | 15 | 15
Hadoop | Testing | 1.1.4.15 | Ongoing | Doug | 0 | 10 | 10 | 10
dCache | Configuration | 1.1.4.7 | Continuous | Tanya | 10 | 6 | 5 | 10
dCache | Packaging/Testing | 1.1.4.8 | Continuous | Neha | 30 | 30 | 30 | 30
Public Storage | Improve Gratia storage probes | 1.1.5 | TBD | Doug | 0 | 5 | 0 | 0
Public Storage | Investigate globus.org for bulk transfer | 1.1.5 | TBD | Tanya | 0 | 6 | 5 | 5
Collaborate with EMI on next-gen SRM |  | None | TBD | Alex | 10 | 10 | 10 | 10
Management |  | N/A | Continuous | Alain | 60 | 60 | 30 | 60
Management |  | N/A | Continuous | Tanya | 6 | 6 | 6 | 6
Inactive Projects I'm worried about
Upgrade to new VOMS/VOMS Admin | 1.1.4.3
Add "Submit Host" to VDT | 1.1.4.4
Define "Operations Center Software" | 1.1.4.5
SHA-1 transition | 1.1.4.12

## Project Effort Summaries
Project Effort Summaries
Values
Row Labels | Sum of Feb 2011 | Sum of Mar 2011 | Sum of Apr 2011 | Sum of May 2011
Bestman | 48 | 47 | 52 | 42
Pre-release testing/configuration | 18 | 17 | 27 | 12
Support | 30 | 30 | 25 | 30
Collaborate with EMI on next-gen SRM | 10 | 10 | 10 | 10
(blank) | 10 | 10 | 10 | 10
CREAM | 10 | 60 | 60 | 0
Basic Functionality with Pacman | 10 | 60 | 60 | 0
Native Packaging | 0 | 0 | 0 | 0
dCache | 40 | 36 | 35 | 40
Configuration | 10 | 6 | 5 | 10
Packaging/Testing | 30 | 30 | 30 | 30
Development | 70 | 39 | 16 | 7
Pigeon Tools/RSV Probes | 53 | 22 | 1 | 0
Storage testsuite improvement | 12 | 12 | 10 | 2
Gratia storage probes | 5 | 5 | 5 | 5
Discovery Tools | 0 | 0 | 0 | 0
Hadoop | 27 | 31 | 35 | 25
Background | 2 | 6 | 10 | 0
Repository | 15 | 15 | 15 | 15
Tutorial | 10 | 0 | 0 | 0
Testing | 0 | 10 | 10 | 10
Management | 66 | 66 | 36 | 66
Native Packaging | 140 | 165 | 118 | 40
Worker Node | 90 | 80 | 10 | 10
Xrootd | 50 | 70 | 60 | 10
LIGO distribution maintenance | 0 | 15 | 5 | 0
Community Packaging Plan | 0 | 0 | 43 | 20
OSG Summer School | 20 | 40 | 63 | 40
Public Storage | 0 | 11 | 5 | 5
Specific VO Support | 12 | 12 | 20 | 22
LIGO data movement plan | 2 | 2 | 0 | 2
STAR Bestman Support | 10 | 10 | 5 | 10
ATLAS Bestman Support | 0 | 0 | 15 | 10
VDT Releases | 20 | 20 | 85 | 70
(blank) | 20 | 20 | 85 | 70
VDT Support | 17 | 17 | 17 | 17
General Support | 15 | 15 | 15 | 15
Storage Support Coordination | 2 | 2 | 2 | 2
Xrootd config/test | 20 | 6 | 0 | 6
(blank) | 20 | 6 | 0 | 6
Grand Total | 500 | 560 | 552 | 390

## Staff Effort Summaries
Staff Effort Summaries
Values
Row Labels | Sum of Feb 2011 | Sum of Mar 2011 | Sum of Apr 2011 | Sum of May 2011
Alain | 80 | 90 | 70 | 90
Alex | 50 | 50 | 55 | 60
Doug | 50 | 50 | 55 | 15
Jeff | 15 | 15 | 15 | 15
Mat | 100 | 100 | 100 | 60
Neha | 50 | 50 | 44 | 34
Scot | 25 | 25 | 25 | 25
Suchandra | 0 | 50 | 50 | 0
Tanya | 70 | 70 | 70 | 51
Tim | 60 | 60 | 68 | 40
Grand Total | 500 | 560 | 552 | 390