## Slide 1: OSG Area Coordinators Meeting Operations
Rob Quick
2/22/2012

## Slide 2
 | WBS Ongoing Activities | 
1 | Support LHC | 95% Attendance at WLCG Daily Operations Meetings, 2 Face-to-Face meetings with WLCG Operations Staff.
2 | Routine Operational Process Execution | Meet services availability as defined in the SLA for each service. Push all ticket to resolution.
3 | Improving Operational Processes | Two GOC Operations Face-to-Face meetings to brainstorm procedural efficiency, these items will considered by Operations and OSG management based on effort.
4 | Help Regional Grids with Operational Infrastructure | Help GridUNESP set up operational infrastructure. Other campus and regional grids will be considered as they are identified.
5 | Interaction with External Partners | Conduct wellness visits to major stakeholders, attend the traditional OSG meetings and workshops to get customer feedback on Operational services.
6 | Support Desk Staff Training | Plan 10-12 Sessions (approximately monthly) that include the Operations Staff and various technology experts.
7 | Monitor and Report Effort for Additional Operational Services | Submit monthly effort concerns in writing to OSG ET.

## Slide 3: Ongoing Items Notes
Support LHC – First Quarter Attendance 96%+, Face to Face occur in Spring (EGI Community Forum and CHEP) and Fall (EGI Technical Forum)
Routine Operational Process Execution – Meeting all SLA Availability and Reliability Stats and tickets are being handled efficiently
Improving Operational Processes – Met in October with entire group, in May at CHEP with leads (Scott and Kyle)
Help Regional Grids with Operational Infrastructure – No new action. UNESP is awaiting a funding proposal.
Interaction with External Partners – Visited FNAL in December and Visited UCSD in January for Glide-In Factory workshop.
Support Desk Staff Training – VDT training April 16th https://twiki.grid.iu.edu/bin/view/Operations/VDTSoftwareTraining. Condor week attended by Elizabeth and Kyle. GlidinFactory Training set for July 2nd.
Monitor and Report Effort for Additional Operational Services – No current concerns.

## Slide 4
 | WBS Item |  |  | 
2.2 | Operations | Quick |  | 
2.2.1 | New Service Implementation and Upgrades | Quick |  | 
2.2.1.1 | Plan and Deploy Top Level BDII | Quick | 10/1/11 | 1/15/12
2.2.1.2 | Plan and Deploy CERN Based WMS Glide-In Factory | Quick | 10/1/11 | 2/15/12
2.2.2 | Improving Operational Processes and Services | Quick |  | 
2.2.2.1 | Evolve HA Technologies to LVS | Quick | 10/1/11 | 4/30/12
2.2.2.2 | Consolidate Public Documentation Services | Quick | 10/1/11 | 8/31/12

## Slide 5: WBS Items – Notes
Plan and Deploy Top Level BDII – Sidelined for now, Brian and Soichi are researching other options for Information Systems as part of the Technology Area and will have a report available at https://docs.google.com/document/d/1NtClBProVLwkuH6L77YsAjMe50Wyf9B720bN-ec9qDg/edit?pli=1
Plan and Deploy CERN Based WMS Glide-In Factory – Done
Evolve HA Technologies to LVS – Repo and Software done. ticket, myosg, display, gratiaweb, blogs, and oim have LVS certs and will be transitioned in the near future.
Consolidate Public Documentation Services – Done.
  Services moving to openscincegrid.org aliases over the next few months.
OSG-XSEDE Front end – Done.
APEL/Gratia Interface – Added to EGI requirements document.
Network Monitoring in MyOSG – Need an update from ET on recent networking discussions.
DigiCert Transition and Front End – DigiCert front end will be part of OIM, some changes to enable this have been released. We are still working on the mechanics of batch requests with DigiCert Engineers.

## Slide 6: Concerns
DigiCert transition impact on Operations Load.
  Sustained effort for PKI Frontend and Other new services (OASIS, iRODS, Pakiti, etc.)
  Many JIRA items put on hold while this work is being done.
Event Notification project. (WBS Ongoing Activity 3 and WBS Item 2.2.2 Improving Operational Processes and Services.) CHEP Poster
10-12 Training sessions is high. The appropriate number is probably 5-6.