## Sheet1
1.6 | Campus Grids |  |  | Fraser
1.6.1 | Document the Benefits of Campus Grids and Identify a prioritized list of Campus proponents | 2010-10-01 | 2010-10-30 | Fraser
1.6.2 | Field Survey at least 6 existing and potential campus Grid sites to understand and Articulate Campus Grid successe, barriers, and needs | 2010-11-01 | 2010-12-15 | Fraser
1.6.3 | Represent OSG Campus Grids (and vision) at appropriate conferences and workshops | 2010-10-01 | 2011-09-30 | Fraser, TBD
1.6.4 | Create a plan for Campus Grid deployments | 2011-01-01 | 2011-02-15 | Fraser
1.6.4.1 | Articulate and circulate use cases |  |  | Fraser
1.6.4.2 | Identify necessary development efforts |  |  | Fraser
1.6.4.3 | Identify manpower that will be used to complete the Y5 effort |  |  | Fraser
1.6.5 | Identify and work with one campus as a prototype | 2011-01-01 | 2011-06-01 | Fraser, TBD
1.6.5.1 | Create a design architecture | 2010-02-01 | 2011-03-01 | Fraser, TBD
1.6.5.2 | Deploy a Campus Grid prototype | 2011-03-01 | 2011-06-01 | Fraser, TBD