## Sheet2
1.7 | No | Security | Altunay | Yes | 2009-07-30 08:00 | 2010-09-30 | 43%
1.7.1 | No | Increased Support for Sites (T3-T2-T1) and VOs | Barlow, Sfiligoi | Yes | 2009-09-01 08:00 | 2010-09-30 | 100%
1.7.1.1 | No | Direct communication with VO and site contacts. Concrete goal: a phone call with a site and VO contact per week. | Barlow, Sfiligoi | No | 2009-09-01 08:00 | 2010-09-30 | 100%
1.7.1.2 | No | Understand security environment of VO and site. (Friendly conversation, not a hostile security questionnaire. VO security contact may not know the security environment) | Barlow, Sfiligoi | No | 2009-09-01 08:00 | 2010-09-30 | 100%
1.7.1.3 | No | Understand what type of support needs exist in stakeholder community | Barlow, Sfiligoi | No | 2009-09-01 08:00 | 2010-09-30 | Dropped per EB's approval
1.7.2 | No | Incident Response and Monitoring | Padmanabhan, Barlow, Altunay | Yes | 2009-09-01 08:00 | 2010-09-30 | 100%
1.7.2.1 | No | Focus on proactive monitoring tools | Padmanabhan, Altunay | Yes | 2009-09-01 08:00 | 2010-09-30 | 100%
1.7.2.1.1 | No | Identify high level threats and if needed, find and/or develop monitoring tools for these threats (This is the only software development activity for next year) | Padmanabhan, Altunay | No | 2009-09-01 08:00 | 2010-09-30 | 100%
1.7.2.1.2 | No | Use Gratia records to establish regular usage patterns in OSG. | Padmanabhan, Altunay | No | 2009-09-01 08:00 | 2010-09-30 | Dropped per EB's approval
1.7.2.1.3 | No | check if a site has applied announced patches. e.g. check access logs, check vdt version or look rsv probe results | Padmanabhan, Altunay | No | 2009-09-01 08:00 | 2010-09-30 | 100%
1.7.2.2 | No | Conduct Incident Drills | Barlow | Yes | 2009-09-01 08:00 | 2010-09-30 | 100%
1.7.2.2.1 | No | Repeat WLCG drill against Tier-2 and Tier-1s | Barlow | No | 2009-09-01 08:00 | 2010-09-30 | 100%
1.7.2.2.2 | No | Drop a VO | Barlow | No | 2009-09-01 08:00 | 2010-09-30 | 0%
1.7.2.2.3 | No | Drop a site | Barlow | No | 2009-09-01 08:00 | 2010-09-30 | 0%
1.7.2.2.4 | No | Conduct a silent drill against OSG services to measure OSG staff’s awareness, e.g. show penetrating into VDT software cache, GOC security tickets, etc | Barlow | No | 2009-09-01 08:00 | 2010-09-30 | 0%
1.7.3 | No | Audit, Risk Assessment and Mitigation | Olson, Sfiligoi, Padmanabhan | Yes | 2009-07-30 08:00 | 2010-09-30 | 55%
1.7.3.1 | No | Mitigate risks found in RA infrastructure | Olson | No | 2009-07-30 08:00 | 2010-09-30 | 90%
1.7.3.2 | No | Document and Analyze certificate revocation Issues when an individual leaves a VO | Olson | No | 2009-08-20 08:00 | 2009-10-31 | 100%
1.7.3.3 | No | Implement disaster recovery plans | Olson | No | 2009-07-30 08:00 | 2010-09-30 | 100%
1.7.3.4 | No | Implement or ask VDT and GOC to implement secure software distribution channels and secure CA distribution channels. | Sfiligoi, Roy, Quick | No | 2009-07-30 08:00 | 2010-03-01 | 50%
1.7.3.5 | No | Implement or ask VDT to implement a vulnerability notification process with software providers | Sfiligoi, Roy | No | 2009-07-30 08:00 | 2010-03-01 | 100%
1.7.3.6 | No | Understand and review the software components in VDT. This is not a code-level audit. This is a general understanding of which authN, configuration variable and etc are used by a component. | Padmanabhan, Sfiligoi | No | 2009-09-01 08:00 | 2010-09-30 | 10%
1.7.3.7 | No | Transition to SHA-2 | Padmanabhan, Sfiligoi | No | 2009-09-01 08:00 | 2010-09-30 | 20%
1.7.4 | No | Education & Documentation | Olson, Altunay | Yes | 2009-07-30 08:00 | 2010-09-30 | 46%
1.7.4.1 | No | Contribute to documentation effort | Olson | No | 2009-07-30 08:00 | 2010-09-30 | 20%
1.7.4.2 | No | Prepare How to guides: | Olson, Altunay | Yes | 2009-07-30 08:00 | 2010-09-30 | 50%
1.7.4.2.1 | No | How to respond to incidents | Olson | No | 2009-07-30 08:00 | 2010-09-30 | 100%
1.7.4.2.2 | No | How to securely configure and install VDT (including non-security software) | Altunay | No | 2009-07-30 08:00 | 2010-09-30 | 0%
1.7.4.2.3 | No | How to operate a site securely (for site admins, day-day tasks, how to register with OIM, read security advisories, check security team’s signatures, etc) | Olson | No | 2009-07-30 08:00 | 2010-09-30 | 100%
1.7.4.2.4 | No | How to access OSG for end user (get cert, import into a browser, renew, register with VOMS, etc) | Olson | No | 2009-07-30 08:00 | 2010-09-30 | 100%
1.7.4.2 | No | Training | Altunay | Yes | 2009-07-30 08:00 | 2010-09-30 | 50%
1.7.4.2.1 | No | Security Training for OSG staff (once a year) | Altunay, Olson | No | 2009-07-30 08:00 | 2010-09-30 | Dropped per EB's approval
1.7.4.2.2 | No | Security Training for sites, VO, users | Altunay, Olson | No | 2009-07-30 08:00 | 2010-09-30 | 100%
1.7.5 | No | Continuous Operational Security Tasks | Altunay, Barlow | Yes | 2009-07-30 08:00 | 2010-09-30 | 50%
1.7.5.1 | No | Respond to incidents | Barlow, Altunay, Olson, Padmanabhan, Sfiligoi | No | 2009-07-30 08:00 | 2010-09-30 | 100%
1.7.5.2 | No | Operational Security Tickets with GOC | Barlow | No | 2009-07-30 08:00 | 2010-09-30 | 100%
1.7.5.3 | No | Read software vulnerability bulletin boards for 3rd party software | Altunay, Barlow, Olson, Padmanabhan, Sfiligoi | No | 2009-07-30 08:00 | 2010-09-30 | 100%
1.7.5.4 | No | Prepare CA package | Olson | No | 2009-07-30 08:00 | 2010-09-30 | 100%
1.7.5.5 | No | Run RA | Olson | No | 2009-07-30 08:00 | 2010-09-30 | 100%
1.7.5.6 | No | Prepare 2 identity workshop with ESNet | Olson | No | 2009-07-31 08:00 | 2009-11-01 | 100%
1.7.5.7 | No | ST&E | Cudzewicz, Altunay | No | 2009-08-03 08:00 | 2009-12-31 | Dropped per EB's approval
1.7.5.8 | No | Update risk assessment document. | Altunay | No | 2009-08-03 08:00 | 2009-12-31 | Dropped per EB's approval
1.7.5.9 | No | Attend Security forums and advise stakeholders of proposed changes affecting their operations and inter-operability with other Grids | Altunay, Olson | Yes | 2009-10-01 08:00 | 2010-09-30 | 100%
1.7.5.9.1 | No | attend EuGridPMA 3 times a year, Europe | Olson | No | 2009-10-01 08:00 | 2010-09-30 | 100%
1.7.5.9.2 | No | attend TAGPMA 2 times a year, Americas | Olson | No | 2009-10-01 08:00 | 2010-09-30 | 100%
1.7.5.9.3 | No | attend JSPG only remote | Altunay | No | 2009-10-01 08:00 | 2010-09-30 | 100%
1.7.5.12 | No | CA/CRL outages communicate to IGTF | Olson | No | 2009-07-30 08:00 | 2010-09-30 | 100%
1.7.5.14 | No | Automated merging of VO packaged (Leftover from last year) | Sfiligoi | No | 2009-08-20 08:00 | 2009-10-20 | 100%
1.7.5.15 | No | Build interactive comm mechanisms with security contacts | Altunay, Quick | No | 2009-08-20 08:00 | 2009-12-31 | 100%
1.7.5.16 | No | Software Tickets with VDT | Sfiligoi | No | 2009-07-30 08:00 | 2010-09-30 | 100%
1.7.5.17 | No | Monitor results of RSV tests and Gratia reports | Altunay | No | 2009-08-20 08:00 | 2009-10-20 | 100%

## Sheet4
1. Security announcement process completed | in WBS?
1.1 A process for creating and announcing security tickets. access granted to site security contacts, several times made mistakes because ticket was publicly available. completely finished. We developed silent tests that tell us which site admins actually read the security tickets. We contacted the ones who do not read it to understand the reason. Understood that they need extra information in the email to be interested with the ticket, modified the process accordingly. We repeat this until we get a high number of admins reading the tickets. We decide to do this tests a few times during teh year randomly. | Yes
2. Software vulnerability process is created and executed. | Yes
2.1 New process created to follow, debug and fix software security problems. process is still followed every week.
2.2. Mine, Anand and Igor got accounts at RT at VDT to deal with and monitor security tickets.
3. T3 site admins meetings | Yes
3.1 Number one issue was communications. Basics like which email lists to subscribe and which announcements to read. Secure email communications have been explained; We put up our pictures, certificates, pgp keys on security web site.
3.2 Admins asked how to find all announcements at a single place and see an archive of announcements. Started a security blog to archive all our announcements.
4. Privacy Policy is completed. VDT built the disclaimer into the software. we decided not to make any more changes into the configuration | Yes
5. T3 site base support has started. | Yes
5.1 We called and introduced our security team and our work. We listened to sites stories. This activity continued until T3 activity under Dan's coordination.
6. Tier2 sites incident drill. | Yes
6.1 23 sites, not only cms and atlas but also other mid-size sites.
6.2 Wrote a server and simple probing client. timing the site admins responses.
6.3 the drill and the results are on the web site.
6.4 contacted sites back with items they failed on.
--In August, Jim basney left and we were effortless until Barlow came on board. Barlow fully integrated into the team in around October. Dan started Tier3 work at the same time and Barlow started coordinating our tier3 calls with Dan.
7. DOEGrids security evaluation | Yes
7.1 Contingency plans have been completed. Loss of GOC CA caches and Loss of DOEGrids CA. plans are on the twiki.
7.2 Monitoring for discovered vulnerabilities in RA infrastructure have been implemented.
8. Authentication and Identity Infrastructure: | Yes
8.1 2 security workshops on security/authN/authZ are held. Reports from this work has been sent to Council and Esnet management.
8.2 VOs are sent a detailed survey before the Madison workshop. Problem areas are identified. Usability of certificates came across as the priority. (October)
8.3 We did another survey with registration agents from VOs. How to change and modify the certificate backend.
8.4 Current situation and fixes:
8.4.1 To monitor and examine the bottlenecks in the DOEGrids infrastructure, we replicated the ESNet CA infarstructure and wrote queries to analyze the system. We found out Atlas takes twice as long as CMS to issue certs, and most sponsors lose emails or take too long to respond. We contacted Michael Ernst and Burt, and set the tolerable wait limit at 5 days. We identified any request taking longer than 5 day and emailed the user, sponsor and agent to debug the issue.
8.4.2 I worked directly with Bill Baltz at BNL and understood Atlas sponsor list is too old, has no back up people at different institutions and sponsors cannot sign their emails.
8.4.3 Doug and me set up a series of meetings with 30+ Ra agents. close to 4-5 meetings. asks their opinion of the changes. everyone agrees and promises to enforce the changes.
8.4.4 We changed the existing process: make it transparent to the user. At every new step, user gets copied to the emails. We worked with Hover to find new sponsor for Atlas who will be faster with their response; changed the email signing requirement to phone conversation. sent continous summary metrics to Ernst until atlas started hitting their timelines. The testing infrastructure still exists and used twice monthly for all VOs.
8.4.5 twice sent emails to users who have spent more than 10 days for their certs.
8.4.6 Doug audited RA agents with random certificates asking for the vetting trail.
8.4.7. Designed a new certificate request web page. Surveyed RA agents which features should be on the page. Tested with closed to 30 new science users, discovered bugs and fixed, asked new users to test the usability of the new site. the site is ready to roll out and in talks with GOC to host it.
8.5 Long-term fixes and solutions
8.5.1 created registration workflow document.
8.5.2 created a roadmap of solutions. Multiple solutions are possible for different VO scenarios. Tested available tools for each solution: MyProxyCA Firefox Plug-in, MyProxyCA java client, existing CA tools from Duthc and UK e-science CA, revisited command line scripts, got certificates from Verisign and compared their workflow to ours. Encouraged European CA developers to merge and generate a single client for the end users. There will be a suite of solutions and they shuld be advertised to VOs as needed. Command line CA tools are advertised at VO and site meetings.
8.5.3 Used SBgrid as a test case. Generated an end-end certificate infrastructure specific to SBGrid.Eliminated the 8 step SBgrid registration workflow:user has to make only 1 request and gets his certificate and register with VOMS. Eliminate the 9-step SBgrid registration workflow. MyProxy firefox plugin is tested and made available to Sbgrid and Atlas (Panda)
8.5.4 Hosted ShibFest at FNAL, started testing with Shib architectures.
8.5.5 Made prep work to start testing with CILogon CA. We are ready to start testing with OSG as an alternative shib based CA. This will give us more flexbility in supporting US-based science users. I will set up a test Shib IdP at Fermilab and test with CILogon server.
8.5.6 Worked with IGTF and all agreed LIGO CA, and any other similar CAs, are IGTF accreditable. This also helped us with moving forward with Myproxy-CA or CILogon CA or both. (Our test with these new CAs are a very important WBS item for next year.)
8.5.7 Our tests results from above CAs will give our roadmap the final shape. .
9. Major GUMS problems since start of October. | No
9.1 New developer Dave Stampf joined the GUMS project. 10 bugs have been reported against the GUMS, 2 of which is important. John Hover and Dave stampf unable to compile and deploy and test GUMS 1.3.17. Things stays unresolved until in June 2010, Dave comes to Fermilab and Mine sits down with him to compile and deploy and run the GUMS server. Mine and Dave sends the source code to Alain to build from the source and test. tests turned successful.
10. Linux Kernel root level vulnerabilities discovered | Yes
10.1 WLCG reacts strongly and asks every site to patch until a certain deadline or be out of the grid. We had 30+ sites in OSG who has not patched or understood the problem. WLCG and OSG asks us to work with Tier2 and Tier3s one-by-one. We run tests individually on each site, call them and walk them through the patching operation.
10.2 Pakiti. As a follow up to kernel root vulnerabilities, european developers design a new service that automates checking for patches. I asked Anand to check it out and see if it is useful. Tier3 coordinator and security team agree this is useful for tier3s and we should move ahead. We decide we need secure access to the Pakiti and ask Europeans to develop it. We work with the developer on one-to-one basis and he finish developing last month. We installed and use the service on another root level kernel vulnerability for Tier3s.
11. CA and CRL outages becomes all too common. | Yes
11.1 Causing a lot of panick and RSV failures among the sites. Also, costing a lot of time for the security team.
11.2 We start keeping records of down times and compute time lost due to each outage. Mine presents this at IGTF and asks more scruntiy of the CA operators. Dave Groep promises closer inspection and enforcement over CAs.
11.3 Mine asks for a central CRL distribution service that can hide these problems from sites. She propose whether SL and Debian would distribute CA certs. IGTF opposes initially, but 6 months later EGI moves onto adopt this mechanism.
11.4 OSG does not have the effort to do any new services. But FNAL fermigrid agrees to implement a CRL cache for themselves with the plan that this will be open to OSG sites eventually. The service is available to FermiGrid, then CMS tier2 and 3s and finally to OSG.
12. Over the Christmas, UCSD has a failure due to CRL and fetch-crl script problems. Security team finds an temp solution. Contacts the fetch-crl developer to develop a more long term solution. Desired solution is developed and shipped in March, and tested by security team. Still waiting for VDT to package and ship it. | No
13. Secure software distribution. Mine asks GOC and VDT to at least sign a hash of the software packages against security attacks. GOC is urged to get a commercial certificate and they did. Alain also gets a commercial certificate. We spent time with Alain on how to sign the software hashes. This still did not get implemented due to VDT and GOC's load. Security team implements a method to sign CA distribution packages. | Yes
--We send an update of our current work items and ask for dropping a few items. SEcurity controls for year 2009 is dropped. (March)
14. Debian CA packages. in November, we get an immediate request from LIGO for Debian packaging for the CAs. I had to go to OSG mgmt to get Dave Dykstra's help. | No
15. DOEGrids new certificate profile. November, DOEgrids moves onto a new certificate profile without fully informing us. The problem is discovered a day after the release. | No
15.1 Doug writes a root-cause analysis report. We decide to create a ITB testing Cache.
16. New certificate layout testing. | No
16.1 At the end of January, IGTF announces to move onto the new CA layout due to SHA-2 transition. We already plan to create a CA test infrastructure. We decide to start with this. We start testing in March (after finishing debian repos). Created a CA cache in ITB. Had to create a new process for creating ca packages. and another new process to test in ITB and then ditribute to GOC. Had to work on RSV probes. test the whole software. Tests are almost complete, as of end of June.
17. Security reviews: | Yes
17.1 NeBioGrid and SBGrid , per director's request. Bestman security review. glexec pilot review. (Igor)
18. Only one incident with Maryland. | Yes
18.1 Admin deleted everything. decide to create a what-to-do-after-you-report-and-discover an encident. We decide to email these instructions automatically whenever someone submits a incident ticket to GOC. have not completed.
18.2 Discovered some security team members do not have access to the security tickets.(Igor and Jim)
--Miscellaneous: openssl bug, tsl renegotiation bug, java 5 reaches end of life, asked vdt to test with java 6, compiler security bug, rocks software root security problem, several TG ssh incidents. Fermi KCA moving to new CA. | Yes
--egee to egi transtion. We connect with European team to understand our new contact points. complete. | No
--sites we helped with along the way: tufts (site security did not understand grid -- helpd meetings, illinois hep), atlast tier3 Samira's site.

## Sheet3
WBS | Task | Start date | End date | Owners
1.7 | Security
1.7.1 | Operational Security
1.7.1.1 | Incident Response and Prevention | 2010-08-01 | 2011-08-30 | Barlow, Altunay, Anand
1.7.1.1.1 | Exchange information with other grid security teams (Barlow) | 2010-08-01 | 2011-08-30 | Barlow
1.7.1.1.2 | Participate in grid-sec, globus-sec and other email lists for possible threats, vulnerabilities | 2010-08-01 | 2011-08-30 | Barlow
1.7.1.1.3 | Perform vulnerability watch : check security bulletins, one team member each week (everyone) | 2010-08-01 | 2011-08-30 | Team
1.7.1.1.4 | Conduct an incident drill with VOs |  |  | Anand, Altunay
1.7.1.2 | T3 Support
1.7.1.2.1 | Continue support for T3s (T2 and T1 included when necessary) | 2010-08-01 | 2011-08-30 | Altunay
1.7.1.2.2 | Continue and finalize installation and deployment of Pakiti. Help transitioning the service to GOC | 2010-10-01 | 2011-12-30 | Anand
1.7.1.2.3 | Maintain and operate the service, contact T3 admins based on their experience (Anand) | 2010-08-01 | 2011-08-30 | Barlow, and the Team
1.7.1.3 | Continuous Operational Work
1.7.1.3.1 | Prepare CA distribution packages, every two months |  |  | Doug
1.7.1.3.2 | Run DOEgrids RA |  |  | Doug
1.7.1.3.3 | Maintain Security RSV probes |  |  | Anand
1.7.1.3.4 | Participate in IGTF, send comments to JSPG |  |  | Doug, Altunay
1.7.1.3.5 | Work on security tickets in GOC and VDT ticketing queue |  |  | Altunay
1.7.2 | Authentication and Identity Infrastructure |  |  | Altunay, Olson, Anand
1.7.2.1 | Test CILogon CA in OSG infrastructure. Setup a test Shib IdP to be tested with CILogon | 2010-08-01 | 2010-10-30
1.7.2.2 | Complete OSG identity roadmap. Advertise the results of tested solutions to user community. Provide a suite of Identity services | 2010-08-01 | 2011-08-31
1.7.2.3 | Test feasibility of VOMS as a Identity provider | 2010-08-01 | 11/31/10
1.7.2.4 | Setup a test CA that manages certificates for the end users (combination of MyProxy CA) | 2010-11-01 | 2011-01-31 | Altunay
1.7.2.5 | Develop and integrate the necessary tools as a result of the roadmap. | 2010-08-31 | 2011-08-31 | Altunay
1.7.2.6 | Configure and Deploy OSG specific Registration Manager for RHCS 8.0 (needed for 1.4) |  | 3 months | Olson
| Establish notification filtering/sorting by VO | 2010-10-01 | 2010-12-31 | Olson
1.7.3 | Virtualization technologies | 2010-08-31 | 2011-08-31 | Altunay
Understand and discuss security needs of virtualization technologies and clouds
Write a roadmap on how OSG security infrastructure can be realized in a virtualized env. Auditing and deployment of Vms, access control problems.
1.7.4 | Software
1.7.4.1 | Prepare for transition to SHA-2 |  |  | Anand
1.7.4.2 | Validate the feature set in GUMS |  |  | Altunay
1.7.5 | Training, Education and Documentation | 2010-08-01 | 2011-08-31
1.7.5.1 | Prepare how-to guides for sites and users | 2010-08-01 | 2011-08-31 | Sfiligoi
1.7.5.2 | How to securely configure and install VDT (including non-security software) | 2010-08-01 | 2011-08-31 | Sfiligoi
1.7.5.3 | How to operate a site securely (for site admins, day-day tasks, how to register with OIM, read security advisories, check security team’s signatures, etc) | 2010-08-01 | 2011-08-31 | Sfiligoi
1.7.5.4 | How to access OSG for end user (get cert, import into a browser, renew, register with VOMS, etc) | 2010-08-01 | 2011-08-31 | Sfiligoi
1.7.5.5 | Help with completing documentation project | 2010-08-01 | 2011-08-31 | Barlow, Sfiligoi, team