## Sheet1
WBS | TaskName | InCharge | Start | Finish
1.8 | Content Management | Engel | 2010-10-01 | 2011-10-01
1.8.1 | Staff and Contributor Coordination and Delivery
1.8.1.1 | Run biweekly meetings to review and plan and discuss documentation activities | Engel | 2010-10-01 | 2011-10-01
1.8.1.2 | Continue to help document area coordinators with the infrastructure and delivery of documents | Engel, Document Area Coordinators. | 2010-10-01 | 2011-10-01
1.8.1.3 | Identify owners for each documentation area | Engel
1.8.2 | Manage relationships & raise issues with the ET when necessary | Engel
1.8.3 | Content Management Infrastructure | Engel
1.8.3.1 | Evolve standards and templates for documents | Engel | 2010-10-01 | 2011-10-01
1.8.3.2 | Implement an effective search for Documentation - is this complete at the end of FY10? | Engel
1.8.3.3 | Get all Documentation into new process | Engel | 2010-10-01 | 2011-01-01
1.8.3.4 | Participate in providing plan for new content management infrastructure. | Engel | 2010-10-01 | 2011-01-01