## Slide 1: OSG Project Manager Report for OSG Council Meeting May 12, 2009 Chander Sehgal

## Slide 2: 2009 OSG NSF Annual Report
Process:
Same document structure as last year; update sections based on work
spanning July 2008 to June 2009. Last year’s report is at:
http://osg-docdb.opensciencegrid.org/cgi-bin/ShowDocument?docid=770&version=1
Schedule:
June 5 - June 12: Canvass for inputs
  Paul Avery will handle Science accomplishments & list of publications
  Chander Sehgal will handle OSG internal work areas
June 15 - June 22: Paul and Chander edit inputs for the NSF fastlane submission
June 22 – June 24: Review by OSG PIs
June 26: Submit into Fastlane

## Slide 3: OSG Supplemental Proposals
Supplemental proposal to DOE re: Production Coordinator
  Re-direct $125K/year from BNL to U-Chicago (via UW-Madison) as partial funding for Production Coordinator
  Approved: April 21, 2009
  U-Chicago SOW being revised to arrange subcontract of DOE funds and additional NSF funds (1 FTE for 4/1/09 to 9/30/09; 0.5 FTE thereafter)
Supplemental proposal to NSF re: Condor support
  Provide releases and support for Condor for one year ($750K)
  Approved: April 27, 2009
  Working to establish project management and tracking of Condor work performed as part of OSG

## Slide 4: OSG Future Planning Schedule (from Ruth Pordes based on March 2009 Council Mtg)
Phase 1 by June 2009
Gather and document requirements & expectations from major stakeholders for 2010 to 2015
Solicit guidance from OSG Council on key directions for future
Phase 2 by Aug 2009
Face-to-Face Council Mtg
2-page plan for each OSG work area (or functional unit)
List/abstract of satellite proposals
Phase 3 by Dec 2009
Analysis => outline for proposal
Document Architecture
Identify particpating senior personnel (and institutions)
Phase 4 at March 2010 All Hands Meeting
Endorsement of proposal by stakeholders