## Sheet1
WBS | Description | Start Date | End Date | Owner | BNL | Caltech | Chicago | Clemson | Fermilab | Florida | HMS | Indiana | Internet2 | Illinois | LBNL | Nebraska | RENCI | UCSD | Wisconsin
1 | OSG year4 Program of Work | 2009-10-01 | 2010-09-30 | Pordes, Livny |  |  |  |  | Co-lead | [9 empty] | Co-lead
1.0.1 | Software Tools Group |  |  | Roy, Altunay |  |  |  |  | Co-lead | [9 empty] | Co-lead
1.0.1.1 | Continue overseeing OSG-owned software | 2009-10-01 | 2010-09-30 | Roy, Altunay |  |  |  |  | Co-lead | [9 empty] | Co-lead
1.0.1.1.1 | RSV development | 2009-10-01 | 2010-09-30 | Quick | [7 empty] | Lead
1.0.1.1.2 | OIM development | 2009-10-01 | 2010-09-30 | Quick | [7 empty] | Lead
1.0.1.1.3 | OSG VO Map development | 2009-10-01 | 2010-09-30 | Roy | [14 empty] | Lead
1.0.1.2 | Continue overseeing OSG-catalyzed software | 2009-10-01 | 2010-09-30 | Roy, Altunay |  |  |  |  | Co-lead | [9 empty] | Co-lead
1.0.1.2.1 | PPDG Cert Scripts | 2009-10-01 | 2010-09-30 | Altunay |  |  |  |  | Lead
1.0.1.2.2 | GUMS | 2009-10-01 | 2010-09-30 | Altunay |  |  |  |  | Lead
1.0.1.2.3 | Bestman | 2009-10-01 | 2010-09-30 | Sim | [10 empty] | Lead
1.0.1.2.4 | Gratia | 2009-10-01 | 2010-09-30 | Bockelman | [11 empty] | Lead
1.0.1.3 | Improve transparency of STG operations | 2009-10-01 | 2010-10-01 | Roy, Altunay |  |  |  |  | Co-lead | [9 empty] | Co-lead
1.0.1.3.1 | Collect and examine stakeholder requirements | 2009-10-01 | 2010-10-01 | Roy, Altunay |  |  |  |  | Co-lead | [9 empty] | Co-lead
1.0.1.3.2 | Improve procedure for sending timely updates to requestors, developers and OSG staff | 2009-10-01 | 2009-11-15 | Roy, Altunay |  |  |  |  | Co-lead | [9 empty] | Co-lead
1.0.1.4 | Integrate software development best practices into STG-managed software lifecycle | 2009-10-01 | 2010-09-30 | Roy, Altunay |  |  |  |  | Co-lead | [9 empty] | Co-lead
1.0.1.4.1 | Work with STG-managed software to improve unit and regression testing | 2009-10-01 | 2010-09-30 | Roy, Altunay |  |  |  |  | Co-lead | [9 empty] | Co-lead
1.0.1.4.1.1 | Work with RSV team to improve unit and regression tests | 2009-10-01 | 2009-12-31 | Quick | [7 empty] | Lead
1.0.1.4.1.2 | Work with GIP team to improve unit and regression tests | 2009-10-01 | 2009-12-31 | Holzman |  |  |  |  | Lead
1.0.1.4.1.3 | Work with Bestman team to improve unit and regression tests | 2010-01-01 | 2010-04-30 | Sim | [10 empty] | Lead
1.0.1.4.1.4 | Work with GUMS team to improve unit and regression tests | 2010-01-01 | 2010-04-30 | Packard | Lead
1.0.1.4.1.5 | Work with GRATIA team to improve unit testing and regression tests | 2010-05-01 | 2010-09-30 | Canal |  |  |  |  | Lead
1.0.1.5 | Examine Year 4 goals from other areas and identify developmental work | 2009-10-01 | 2010-10-01 | Roy, Altunay |  |  |  |  | Co-lead | [9 empty] | Co-lead
1.0.1.6 | Divert and allocate STG-owned effort to starving projects | 2009-10-01 | 2010-10-01 | Roy, Altunay |  |  |  |  | Co-lead | [9 empty] | Co-lead
1.0.1.6.1 | OSG-TG gateway | 2009-10-01 | 2010-01-30 | Padmanabhan | [9 empty] | Lead
1.0.2 | Production Coordination |  |  | Fraser |  |  | Lead
1.0.2.1 | Identify and articulate OSG issues that impact the effectiveness of sites & VOs and lead/coordinate OSG teams to resolve the issues. | 2009-10-01 | 2010-09-30 | Fraser |  |  | Lead
1.0.2.1.1 | Lead weekly Production calls, highlight important issues, and follow up on action items. | 2009-10-01 | 2010-09-30 | Fraser |  |  | Lead
1.0.2.1.2 | Work with the VO, Sites, and Operation Area coordinators to coordinate activities related to production. | 2009-10-01 | 2010-09-30 | Fraser |  |  | Lead
1.0.2.1.3 | Work with the Metrics Coordinator to monitor the performance of the OSG infrastructure and develop measures and metrics that assess the state of the facility. | 2009-10-01 | 2010-09-30 | Fraser |  |  | Lead
1.0.2.1.4 | Analyze the usage patterns and efficiency of resource utilization, and develop trend data for the OSG; use that data to propose improvement plans for the facility. | 2009-10-01 | 2010-09-30 | Fraser |  |  | Lead
1.0.2.1.5 | Provide written quarterly reports to the OSG ET on production activities. | 2009-10-01 | 2010-09-30 | Fraser |  |  | Lead
1.0.2.2 | Serve as the OSG Tier-3 Liaison to the US-ATLAS and US-CMS communities and establish regular, ongoing, point-to-point contact with the US ATLAS and US CMS Tier-3 support staff to enable cross-VO communication and collaboration, where appropriate. | 2009-10-01 | 2010-09-30 | Fraser |  |  | Lead
1.0.2.2.1 | Work with Atlas and CMS to define an operational plan for supporting T3s that includes appropriate VO and OSG combined efforts. | 2009-10-01 | 2010-09-30 | Fraser, Levshina |  |  | Lead |  | Support
1.0.2.2.2 | Work with the Security Coordinator and Atlas/CMS T3 liasons to provide a practical “hands-on” security plan for T3s. | 2009-10-01 | 2010-09-30 | Fraser, Altunay |  |  | Lead |  | Support
1.0.2.3 | Manage relationships and communication with stakeholders (especially CMS, Atlas, and LIGO) to understand status and issues and communicate them to the OSG-ET, with recommendations if possible. | 2009-10-01 | 2010-09-30 | Fraser |  |  | Lead
1.0.2.3.1 | Establish effective communication channels with OSG T1/T2/T3 site admins. | 2009-10-01 | 2010-09-30 | Fraser |  |  | Lead
1.0.2.3.2 | Represent the needs of these stakeholders at key internal OSG meetings and communications and escalate priorities as needed | 2009-10-01 | 2010-09-30 | Fraser, Mambelli |  |  | Lead
1.0.2.3.3 | Create a list of top 3-5 OSG requirements based on discussions with the site admins. | 2009-10-01 | 2010-09-30 | Fraser, Mambelli |  |  | Lead
1.0.2.3.4 | Include reports on these communications as part of the Production quarterly report. | 2009-10-01 | 2010-09-30 | Fraser |  |  | Lead
1.0.2.4 | Assist the Executive Team in providing guidance to and working with the Operations, Sites, VOs and Education/Training area coordinators to communicate and facilitate the resolution of issues in the prioritization and planning of activities, assessment of success, and allocation of effort across the areas. | 2009-10-01 | 2010-09-30 | Fraser |  |  | Lead
1.0.2.5 | Based on guidance and approval by the OSG Executive Team, lead and coordinate plans to improve the OSG facility. | 2009-10-01 | 2010-09-30 | Fraser |  |  | Lead
1.0.3 | Biology and Biomedical Outreach |  |  | Sliz | [6 empty] | Lead
1.0.3.1 | Establish Robust gateway for submission of jobs |  |  | Sliz | [6 empty] | Lead
1.0.3.1.1 | Provide NEBioGrid operational services at 85% reliability measured on a monthly basis | 2009-10-01 | 2010-09-30 | Sliz | [6 empty] | Lead
1.0.3.1.2 | Upgrade and fine-tune OSG software on participating NEBioGrid sites | 2010-01-01 | 2010-09-30 | Sliz | [6 empty] | Lead
1.0.3.1.3 | Develop an OSG Branch of HPC Biomedical Applications | 2010-01-01 | 2010-03-30 | Sliz | [6 empty] | Lead
1.0.3.1.4 | Expand the OSG Branch of Biomedical | 2010-04-01 | 2010-09-30 | Sliz | [6 empty] | Lead
1.0.3.1.5 | Configure MPI cluster for MD computations | 2009-11-01 | 2009-12-30 | Sliz | [6 empty] | Lead
1.0.3.2 | Integrate biomedical resources with common infrastructure |  |  | Sliz | [6 empty] | Lead
1.0.3.2.1 | Integrate a one new biomedical site in New England area | 2010-01-01 | 2010-03-30 | Sliz | [6 empty] | Lead
1.0.3.2.2 | Integrate a second new biomedical site in New England area | 2010-07-01 | 2010-09-30 | Sliz | [6 empty] | Lead
1.0.3.2.3 | Provide OSG support for researchers from the participating NEBioGrid institutions | 2009-10-01 | 2010-09-30 | Sliz | [6 empty] | Lead
1.0.3.3 | Provide outreach, educational and training opportunities for members of biomedical community |  |  | Sliz | [6 empty] | Lead
1.0.3.3.1 | Deploy a website to support activities of the NEBioGrid community | 2009-10-01 | 2009-10-15 | Sliz | [6 empty] | Lead
1.0.3.3.2 | Organize an OSG training session as part of SBGrid user meeting | 2010-03-30 | 2010-06-30 | Sliz | [6 empty] | Lead
1.0.3.3.3 | Organize monthly HPC/Grid seminars | 2009-10-01 | 2010-09-30 | Sliz | [6 empty] | Lead
1.0.3.4 | Generate plan that provides a sustainable model for OSG partnership with the Biology and Biomedical Science communities. | 2009-11-01 | 2010-03-31 | Sliz | [6 empty] | Lead
1.0.4 | LIGO |  |  | Blackburn |  | Lead
1.0.4.1 | Improved LIGO science production via Einstein@Home |  |  | Engel, Daudert |  | Lead
1.0.4.1.1 | Submission code and documentation maintenance in support continued production use of Einstein@Home on the OSG (E@OSG) | 2009-10-01 | 2010-09-30 | Engel |  | Lead
1.0.4.1.2 | Coordinate the operational submission of E@OSG jobs onto the OSG production sites (currently handled by Britta) to assure LIGO science goals. | 2009-10-01 | 2010-09-30 | Daudert, Engel |  | Lead
1.0.4.2 | Support the continued development and deployment of the LIGO Binary Inspiral Workflow for use on the Open Science Grid. |  |  | Daudert |  | Lead
1.0.4.2.1 | Support OSG Storage Technologies on the Caltech OSG ITB cluster to assure usability in the LIGO Binary Inspiral Workflows through Pegasus and RLS. | 2009-10-01 | 2010-09-30 | Engel |  | Lead
1.0.4.2.2 | Work closely with the LIGO Binary Inspiral Data Analysis Working Group to understand and support the architectural changes for delivery onto the OSG. | 2009-10-01 | 2010-09-30 | Daudert |  | Lead
1.0.4.2.3 | Work closely with the Pegasus workflow planner developers at ISI to specify and track grid requirements for Pegasus related to the Binary Inspiral Workflow. | 2009-10-01 | 2010-09-30 | Daudert |  | Lead
1.0.4.2.4 | Work with the Syracuse group to support recently initiated efforts to establish an OSG site for binary inspiral data analysis. | 2009-10-01 | 2010-09-30 | Daudert |  | Lead
1.0.4.2.5 | Prototype near realtime binary inspiral data analysis on the OSG utilizing OSG storage, and data generation from the LIGO Observatories | 2009-10-01 | 2010-09-30 | Daudert |  | Lead
1.0.4.2.6 | Continue development and deployment of operational submission for binary inspiral jobs onto the OSG production sites consistent with LIGO needs. | 2009-10-01 | 2010-09-30 | Daudert |  | Lead
1.1 | Software | 2009-10-01 | 2010-09-30 | Roy | [14 empty] | Lead
1.1.1 | Ongoing OSG Support | 2009-10-01 | 2010-09-30 | Roy, Levshina |  |  |  |  | Support | [9 empty] | Lead
1.1.1.1 | Respond to user questions; troubleshooting | 2009-10-01 | 2010-09-30 | Roy, Levshina |  |  |  |  | Support | [9 empty] | Lead
1.1.1.2 | Maintenance: Fix bugs, minor enhancements | 2009-10-01 | 2010-09-30 | Roy, Levshina |  |  |  |  | Support | [9 empty] | Lead
1.1.1.3 | Regular software updates | 2009-10-01 | 2010-09-30 | Roy, Levshina |  |  |  |  | Support | [9 empty] | Lead
1.1.3.4 | Continue to improve internal testing of software | 2009-10-01 | 2010-09-30 | Roy, Levshina |  |  |  |  | Support | [9 empty] | Lead
1.1.3.5 | Participate in OSG VTB and ITB testing of software | 2009-10-01 | 2010-09-30 | Roy, Levshina |  |  |  |  | Support | [9 empty] | Lead
1.1.2 | Ongoing partner project support | 2009-10-01 | 2010-09-30 | Roy | [14 empty] | Lead
1.1.2.1 | Support EGEE uses of VDT | 2009-10-01 | 2010-09-30 | Roy | [14 empty] | Lead
1.1.2.2 | Support TeraGrid uses of VDT | 2009-10-01 | 2010-09-30 | Roy | [14 empty] | Lead
1.1.2.3 | Support other grids' uses of VDT | 2009-10-01 | 2010-09-30 | Roy | [14 empty] | Lead
1.1.3 | Phase in native packaging of VDT | 2009-06-01 | 2010-09-30 | Roy | [14 empty] | Lead
1.1.3.1 | Add Debian source packages for LIGO's needs | 2009-06-01 | 2009-09-30 | Roy | [14 empty] | Lead
1.1.3.2 | Add RPM source packages for LIGO's needs | 2009-08-15 | 2009-10-30 | Roy | [14 empty] | Lead
1.1.3.3 | Add glexec RPMs (requested by ATLAS & CMS) | 2009-11-01 | 2009-12-01 | Roy | [14 empty] | Lead
1.1.3.4 | Add worker node RPMs (very fuzzy dates) | 2009-11-01 | 2010-03-01 | Roy | [14 empty] | Lead
1.1.3.5 | Add RPMs for complete GUMS server (very fuzzy dates) | 2010-01-01 | 2010-05-01 | Roy | [14 empty] | Lead
1.1.3.6 | Add RPMs for complete Bestman server | 2010-01-01 | 2010-09-30 | Roy, Sim | [10 empty] | Support |  |  |  | Lead
1.1.3.7 | Add RPMs for complete CE | 2010-01-01 | 2010-09-30 | Roy | [14 empty] | Lead
1.1.3.8 | Add RPMs for HadoopFS & GridFTP HadoopFS | 2009-10-01 | 2010-01-01 | Roy, Levshina, Rana |  |  |  |  | Support | [8 empty] | Support | Lead
1.1.4 | Better integrate storage team into VDT team | 2009-10-01 | 2010-09-30 | Roy, Levshina |  |  |  |  | Support | [9 empty] | Lead
1.1.4.1 | Institute regular whole VDT meetings | 2009-10-01 | 2009-11-01 | Roy, Levshina |  |  |  |  | Support | [9 empty] | Lead
1.1.4.2 | Merge ticketing procedures | 2009-10-01 | 2010-01-01 | Roy, Levshina |  |  |  |  | Support | [9 empty] | Lead
1.1.4.3 | Investigate share support responsibilities | 2009-10-01 | 2009-11-01 | Roy, Levshina |  |  |  |  | Support | [9 empty] | Lead
1.1.5 | Add new platform support |  |  | Roy | [14 empty] | Lead
1.1.5.1 | Add SLES 10 support (NERSC) | 2009-10-01 | 2010-12-31 | Roy | [14 empty] | Lead
1.1.6 | Improve software documentation | 2009-10-01 | 2010-09-30 | Roy | [14 empty] | Lead
1.1.6.1 | Participate in documentation alignment activity | 2009-10-01 | 2010-09-30 | Roy | [14 empty] | Lead
1.1.6.2 | Provide "best practice" documentation for storage targeted at Tier 3s | 2009-10-01 | 2009-12-01 | Levshina |  |  |  |  | Lead
1.1.7 | Harmonize OSG software license |  |  | Roy | [14 empty] | Lead
1.1.7.1 | Propose license for all OSG developed software | 2009-08-01 | 2009-08-30 | Roy | [14 empty] | Lead
1.1.7.2 | Apply license to all VDT-developed software | 2009-11-01 | 2009-12-01 | Roy | [14 empty] | Lead
1.1.7.3 | Work with configure_osg developer to apply license | 2009-11-01 | 2010-02-01 | Roy | [14 empty] | Lead
1.1.7.4 | Work with RSV/OIM developer to apply license | 2009-11-01 | 2010-02-01 | Roy | [14 empty] | Lead
1.1.8 | Storage troubleshooting |  |  | Levshina |  |  |  |  | Lead
1.1.8.1 | Investigate tools to improve storage troubleshooting | 2009-10-01 | 2010-01-03 | Levshina |  |  |  |  | Lead
1.1.8.2 | Investigate tools to improve storage administration | 2009-10-01 | 2010-01-03 | Levshina |  |  |  |  | Lead
1.1.8.3 | Implement RSV Probe that verifies Storage BDII content | 2009-10-01 | 2010-01-01 | Levshina |  |  |  |  | Lead
1.1.9 | Opportunistic Storage |  |  | Levshina |  |  |  |  | Lead
1.1.9.1 | Work with VOs and storage providers to facilitate setup and usage of requested opportunistic storage | 2009-10-01 | 2010-09-30 | Levshina, Rana |  |  |  |  | Lead | [8 empty] | Support
1.1.9.2 | Work with VOs to help them use storage discovery tool | 2009-10-01 | 2010-01-01 | Levshina, Rana |  |  |  |  | Lead | [8 empty] | Support
1.1.10 | Establish effective methods for working with external projects |  |  | Roy, Sehgal |  |  |  |  | Support | [9 empty] | Lead
1.1.10.1 | Decide on minimum input requirements for software: send to ET and then apply to five components | 2009-10-01 | 2010-12-31 | Roy, Sehgal |  |  |  |  | Support | [9 empty] | Lead
1.1.10.2 | Work as a liaison between major stakeholders and storage software developers | 2009-10-01 | 2010-09-30 | Levshina |  |  |  |  | Lead
1.1.10.3 | Participate in LCG TG work, report issues to OSG ET | 2009-10-01 | 2010-09-30 | Levshina |  |  |  |  | Lead
1.1.10.4 | Monitor LCG install capacity activities related to SE Glue schema | 2009-10-01 | 2010-09-30 | Levshina |  |  |  |  | Lead
1.1.11 | New storage-related technical effort | 2009-10-01 | 2010-09-30 | Levshina |  |  |  |  | Lead
1.1.11.1 | Evaluate/test/package chimera as a possible replacement for pnfs | 2009-10-01 | 2009-12-01 | Levshina |  |  |  |  | Lead
1.1.11.2 | Evaluate/test dcache support for ACL | 2009-12-01 | 2010-01-01 | Levshina |  |  |  |  | Lead
1.1.11.3 | Evaluate/test/package dcache implementation of delegation service | 2010-03-01 | 2010-05-01 | Levshina |  |  |  |  | Lead
1.1.11.4 | Evaluate/test dcache srm load balancing in dcache | 2010-03-01 | 2010-05-01 | Levshina |  |  |  |  | Lead
1.1.11.5 | Evaluate/test BeStMan delegation service | 2010-01-01 | 2010-02-01 | Levshina |  |  |  |  | Lead
1.1.11.6 | Provide RSV probe that replaces Bestman srmtester | 2009-11-01 | 2009-12-01 | Levshina |  |  |  |  | Lead
1.1.11.7 | Develop/package gratia storage probe for hadoop and xrootd | 2010-01-01 | 2010-04-01 | Levshina |  |  |  |  | Lead
1.1.12 | Online OSG-TeraGrid school |  |  | Roy | [14 empty] | Lead
1.1.12.1 | Propose scope and goals to Executive Team | 2009-10-01 | 2009-10-15 | Roy | [14 empty] | Lead
1.1.12.2 | Make initial contact with TeraGrid contacts | 2009-10-01 | 2009-10-15 | Roy | [14 empty] | Lead
1.1.12.3 | Expand Software WBS for OSG-TeraGrid work based on proposal and ET feedback | 2009-10-15 | 2009-10-31 | Roy | [14 empty] | Lead
1.1.13 | Expand testing of external software components |  |  | Roy | [14 empty] | Lead
1.1.13.1 | Work with Bestman developers on improved Bestman testing | 2009-10-01 | 2009-12-01 | Roy, Levshina, Sim |  |  |  |  | Support | [5 empty] | Support |  |  |  | Lead
1.1.13.2 | Work with GUMS developers on improved GUMS testing | 2009-10-01 | 2009-01-01 | Roy | [14 empty] | Lead
1.1.14 | Build software not currently being built by VDT |  |  | Roy | [14 empty] | Lead
1.1.14.1 | Build GUMS from source | 2009-10-01 | 2009-01-01 | Roy | [14 empty] | Lead
1.1.14.2 | Build Bestman from source | 2009-01-01 | 2010-05-01 | Roy, Sim | [10 empty] | Support |  |  |  | Lead
1.1.15 | Improve ownership in OSG software caches |  |  | Roy | [14 empty] | Lead
1.1.15.1 | Evaluate ownership of OSG-specific configuration | 2009-10-01 | 2009-12-31 | Roy | [14 empty] | Lead
1.1.15.2 | Evaluate ownership of OSG-Pacman cache | 2009-10-01 | 2009-12-31 | Roy | [14 empty] | Lead
1.2 | Operations | 2009-10-01 | 2010-09-30 | Quick | [7 empty] | Lead
1.2.1 | Support LHC | 2009-10-01 | 2010-09-30 | Quick | [7 empty] | Lead
1.2.1.1 | Provide operational issue management for WLCG in collaboration with US-CMS and US-ATLAS | 2009-10-01 | 2010-09-30 | Quick | [7 empty] | Lead
1.2.1.2 | Publish availability and reliability metrics to WLCG | 2009-10-01 | 2010-09-30 | Quick | [7 empty] | Lead
1.2.1.3 | Maintain the relationship with WLCG operations entities (monitoring, GGUS ticketing, VOs, infrastructure services) | 2009-10-01 | 2010-09-30 | Quick | [7 empty] | Lead
1.2.2 | Routine Process Execution | 2009-10-01 | 2010-09-30 | Quick | [7 empty] | Lead
1.2.2.1 | Negotiate and document Service Level Agreements (SLAs) for all services | 2009-01-05 | 2009-12-30 | Quick, Chadwick |  |  |  |  | Support |  |  | Lead
1.2.2.2 | Operate OSG Services at levels that meet the SLAs | 2009-10-01 | 2010-09-30 | Quick, Chadwick |  |  |  |  | Support |  |  | Lead
1.2.2.3 | Communication of Operational Issues to OSG Community | 2009-10-01 | 2010-09-30 | Quick | [7 empty] | Lead
1.2.2.3.1 | Notification of events for Core and Support Services | 2009-10-01 | 2010-09-30 | Quick | [7 empty] | Lead
1.2.2.3.2 | Maintain 24x7 phone, email, and web support for trouble ticket submission | 2009-10-01 | 2010-09-30 | Quick | [7 empty] | Lead
1.2.2.3.3 | Weekly operations phone call | 2009-10-01 | 2010-09-30 | Quick | [7 empty] | Lead
1.2.2.3.4 | Wellness visits to major OSG stakeholder sites | 2009-10-01 | 2010-09-30 | Quick | [7 empty] | Lead
1.2.2.3.5 | Improve Communication with OSG Stakholders by Initiating Phone Contact | 2009-10-01 | 2010-09-30 | Quick | [7 empty] | Lead
1.2.2.4 | Ticket Handling | 2009-10-01 | 2010-09-30 | Quick | [7 empty] | Lead
1.2.2.4.1 | Continue Normal Ticket Troubleshooting and Routine | 2009-10-01 | 2010-09-30 | Quick | [7 empty] | Lead
1.2.2.4.2 | Prepare Staff and Services for Increased Load from LHC | 2009-10-01 | 2009-12-30 | Quick | [7 empty] | Lead
1.2.2.5 | Provide 24x7 Support for Security | 2009-10-01 | 2010-09-30 | Quick | [7 empty] | Lead
1.2.2.6 | Provide OSG internal metrics on operations | 2009-10-01 | 2010-09-30 | Quick, Bockleman | [7 empty] | Lead |  |  |  | Support
1.2.2.6.1 | Ticket Handling | 2009-10-01 | 2010-09-30 | Quick | [7 empty] | Lead
1.2.2.6.2 | Publish availability and reliability metrics to WLCG | 2009-10-01 | 2010-09-30 | Quick | [7 empty] | Lead
1.2.2.6.3 | Others as Identified | 2009-10-01 | 2010-09-30 | Quick, Bockleman | [7 empty] | Lead |  |  |  | Support
1.2.3 | Improving Operational Processes | 2009-10-01 | 2010-09-30 | Quick | [7 empty] | Lead
1.2.3.1 | Documentation of OSG operational processes and procedures | 2008-10-01 | 2010-03-31 | Quick | [7 empty] | Lead
1.2.3.2 | Analysis of benefit and impact of distributed operational Infrastructure (compare with centralized model) | 2009-10-01 | 2010-06-30 | Quick | [7 empty] | Lead
1.2.3.3 | Improve efficiency of administrative processes (automation) | 2009-10-01 | 2010-09-30 | Quick | [7 empty] | Lead
1.2.3.3.1 | TWiki account creation | 2009-10-01 | 2009-12-30 | Quick | [7 empty] | Lead
1.2.3.3.2 | VO package creation | 2009-10-01 | 2009-12-30 | Quick | [7 empty] | Lead
1.2.3.3.3 | CA distribution updates | 2009-10-01 | 2009-11-30 | Quick | [7 empty] | Lead
1.2.3.3.4 | Others as identified | 2009-10-01 | 2010-09-30 | Quick | [7 empty] | Lead
1.2.3.4 | Define and implement change management procedures as defined in SLAs | 2009-10-01 | 2010-01-31 | Quick | [7 empty] | Lead
1.2.3.5 | Conduct an operational process review | 2009-10-01 | 2009-03-31 | Quick | [7 empty] | Lead
1.2.4 | Assist NYSGrid and GridUNSP in implementing a "local" Operations infrastructure | 2009-10-01 | 2010-09-30 | Quick | [7 empty] | Lead
1.3 | Integration and Sites | 2009-10-01 | 2010-09-30 | Gardner |  |  | Lead
1.3.1 | Improve release processes for ITB | 2009-10-01 | 2009-11-01 | Gardner |  |  | Lead
1.3.1.1 | Adapt ITB testing process to native packaging tools | 2009-10-01 | 2010-09-30 | Gardner, Thapa |  |  | Lead
1.3.1.2 | Provide installation packages and cache in a managed software repository | 2009-10-01 | 2010-09-30 | Thapa |  |  | Lead
1.3.1.3 | Work with Software to specify software release deployment, testing and documenation for OSG services | 2009-10-01 | 2010-09-30 | Thapa |  |  | Lead
1.3.1.4 | Contribute technical content and documentation relevant for VTB, ITB releases. | 2009-10-01 | 2010-09-30 | Engel, Thapa, Sakrejda |  | Lead | Support | [7 empty] | Support
1.3.2 | Automate VTB & ITB Testing | 2009-11-01 | 2010-09-30 | Gardner, Thapa |  |  | Lead
1.3.2.1 | Setup single RSV instance for ITB | 2009-11-01 | 2009-11-30 | Thapa |  |  | Lead
1.3.2.2 | Synthetic workload based on Glide-in WMS for ITB | 2009-11-01 | 2009-12-30 | Thapa |  |  | Lead
1.3.2.3 | Synthetic workload based on Panda for ITB | 2010-01-01 | 2010-03-01 | Thapa |  |  | Lead
1.3.2.4 | Contribute technical documentation for automated testing | 2010-01-01 | 2010-09-30 | Thapa |  |  | Lead
1.3.3 | Improve management and operation of the persistent ITB | 2009-10-01 | 2010-09-30 | Gardner, Thapa |  |  | Lead
1.3.3.1 | Define operational SLA for pledged sites. | 2009-10-01 | 2009-11-01 | Gardner |  |  | Lead
1.3.3.2 | Keep sites up to date with incremental updates. | 2009-10-01 | 2010-09-30 | Engel, Sakrejda, tbd1-uc |  | Lead | Support | [7 empty] | Support
1.3.3.3 | Commission OSG-dedicated persistent ITB site | 2009-10-01 | 2009-12-01 | tbd1-uc |  |  | Lead
1.3.3.4 | Provide continuous monitoring of ITB resources. | 2009-10-01 | 2010-09-30 | Thapa |  |  | Lead
1.3.3.5 | Provide support for on-demand VO testing. | 2009-10-01 | 2010-09-30 | Sakrejda | [10 empty] | Lead
1.3.3.6 | Contribute technical content and documentation relevant for the persistent ITB. | 2009-10-01 | 2010-09-30 | Sakrejda, Engel, Thapa |  | Support | Support | [7 empty] | Lead
1.3.4 | Community building for site administrators | 2010-10-01 | 2010-09-30 | Gardner, Mambelli |  |  | Lead
1.3.4.1 | Organize hands-on site administrator’s workshops. | 2010-10-01 | 2010-09-30 | Mambelli |  |  | Lead
1.3.4.2 | Organize site administrators online meetings. | 2010-10-01 | 2010-09-30 | Mambelli |  |  | Lead
1.3.4.3 | Work with Content Management and Training to develop technical materials relevant to OSG site administrators. | 2010-10-01 | 2010-09-30 | Engel, Thapa, Sakrejda |  | Lead | Support | [7 empty] | Support
1.3.4.4 | Work with Production area to provide support for LHC Tier 3 sites. | 2010-10-01 | 2010-09-30 | Mambelli |  |  | Lead
1.3.4.5 | Support sites through chat support | 2010-10-01 | 2010-09-30 | Engel, Thapa, Sakrejda |  | Lead | Support | [7 empty] | Support
1.3.4.6 | Contribute to campus grids program of work to foster OSG spreading at the campus level | 2010-10-01 | 2010-09-30 | Thapa, Mambelli |  |  | Lead
1.3.4.7 | Contribute technical content and documentation relevant for OSG site administrators. | 2010-10-01 | 2010-09-30 | Engel, Thapa, Sakrejda |  | Lead | Support | [7 empty] | Support
1.3.4.8 | Create sites forum, blog, content collaborative platform | 2010-10-01 | 2010-11-30 | Mambelli |  |  | Lead
1.4 | VOs Group Coordination | 2009-10-01 | 2010-09-30 | Rana | [13 empty] | Lead
1.4.1 | Track VOs opportunistic utilization and production efficiency | 2009-10-01 | 2010-09-30 | Rana | [13 empty] | Lead
1.4.1.1 | In phase with LHC startup, gauge any limitations of opportunistic resource availability for other VOs on OSG. | 2010-01-01 | 2010-09-30 | Rana, Fraser |  |  | Support | [10 empty] | Lead
1.4.1.2 | Monitor accounting data and characteristics of VOs. Use both views - OSG Accounting and VOs Accounting. | 2009-10-01 | 2010-09-30 | Rana | [13 empty] | Lead
1.4.1.3 | Preemption/Eviction are prevalent problems in opportunistic grid usage. With ET's direction, commission a recommendation/solution for adoption by affected VOs. | 2010-02-01 | 2010-06-30 | Rana | [13 empty] | Lead
1.4.1.4 | With ET's direction, organize and lead Joint TaskForces to rapidly resolve wide-range matters for specific VOs. Ensure closure within 4-6 weeks. | 2009-10-01 | 2010-09-30 | Rana | [13 empty] | Lead
1.4.2 | Analyse portfolio of functional VOs and recommend needed actions to the OSG-ET | 2009-10-01 | 2010-09-30 | Rana | [13 empty] | Lead
1.4.2.1 | Value delivery to Group 1: D0, CDF, Fermi-VO. | 2009-10-01 | 2010-09-30 | Rana | [13 empty] | Lead
1.4.2.2 | Value delivery to Group 2: DES (+ JDEM), DOSAR, ILC, STAR. | 2009-10-01 | 2010-09-30 | Rana | [13 empty] | Lead
1.4.2.3 | Value delivery to Group 3: Geant4, NYSGrid. | 2009-10-01 | 2010-09-30 | Rana | [13 empty] | Lead
1.4.2.4 | Quarterly executive summary to ET on functional VOs. | 2009-10-01 | 2010-09-30 | Rana | [13 empty] | Lead
1.4.3 | Manage portfolio of VOs that have limited activity | 2009-10-01 | 2010-09-30 | Rana | [13 empty] | Lead
1.4.3.1 | IceCube: Phased expansion on OSG using glideinWMS and Squid/SRM Storage. | 2009-10-01 | 2009-12-31 | Rana | [13 empty] | Lead
1.4.3.2 | ALICE: Phased increase in operations on OSG. Execute USALICE plan on NERSC & LLNL, and/or VO-Box at GLOW. | 2009-10-01 | 2010-09-30 | Rana | [13 empty] | Lead
1.4.3.3 | CompBioGrid, GPN, GROW, nanoHUB: Provide specialized support to enable gradual increase in quantitative activity; evaluate results | 2009-10-01 | 2010-03-31 | Rana | [13 empty] | Lead
1.4.3.4 | NEBioGrid, SBGrid: If needed, work with peer Biology Area to manage gradual increase in quantitative activity. | 2009-10-01 | 2010-03-31 | Rana, Sliz | [6 empty] | Support | [6 empty] | Lead
1.4.3.5 | CIGI, GRASE, NWICG: Assess availability of roadmaps. | 2009-10-01 | 2009-12-31 | Rana | [13 empty] | Lead
1.4.3.6 | With ET's direction, assess viability (and closure) of a VO if success-roadmap and value proposition is unclear. | 2009-10-01 | 2010-09-30 | Rana, Fraser |  |  | Support | [10 empty] | Lead
1.4.3.7 | New VO registrations in GOC: Evaluate clarity of plan, and assist EB in deciding approval or denial of registration. | 2009-10-01 | 2010-09-30 | Rana, Quick | [7 empty] | Support | [5 empty] | Lead
1.4.3.8 | New VO formations via Engagement: Work with Engagement & CampusGrids area to assess/execute plan. | 2009-10-01 | 2010-09-30 | Rana, McGee, Goasguen |  |  |  | Support | [8 empty] | Support | Lead
1.4.3.9 | Quarterly executive summary to ET on inactive VOs. | 2009-10-01 | 2010-09-30 | Rana | [13 empty] | Lead
1.4.4 | Organize a forum for regular stakeholder interaction | 2009-10-01 | 2010-09-30 | Rana | [13 empty] | Lead
1.4.4.1 | Organize Weekly-VO-Forum teleconferences, inviting select VOs and peer OSG Areas. | 2009-10-01 | 2010-09-30 | Rana, Ritchie, Teckenbrock |  |  |  |  | Support | [8 empty] | Lead
1.4.4.2 | Organize F2F Annual OSG VOs & Users Meeting. | 2010-07-01 | 2010-07-31 | Rana | [13 empty] | Lead
1.4.4.3 | Organize F2F meetings with specific VOs as needed. | 2009-10-01 | 2010-09-30 | Rana, Pordes |  |  |  |  | Support | [8 empty] | Lead
1.4.4.4 | Serve as conduit for peer OSG Areas to facilitate at-large VOs matters. E.g., Content Mgt, Software, Sites Coordination, Storage, Scalability/Reliability/Usability. | 2009-10-01 | 2010-09-30 | Rana | [13 empty] | Lead
1.4.4.5 | Collect VOs scientific publications (including ATLAS, CMS, LIGO) for annual DOE & NSF reports. | 2009-10-01 | 2010-09-30 | Ritchie, Rana |  |  |  |  | Lead | [8 empty] | Support
1.4.5 | Coordinate Stakeholder participation in OSG planning and software | 2009-10-01 | 2010-09-30 | Rana | [13 empty] | Lead
1.4.5.1 | Organize periodic collection of VOs plans and requirements. Communicate VOs direct input to Council. | 2009-10-01 | 2010-09-30 | Rana | [13 empty] | Lead
1.4.5.2 | Plan and execute pre-release software validation by VOs (including ATLAS, CMS, LIGO) on ITB. | 2009-10-01 | 2010-09-30 | Rana, Gardner |  |  | Support | [10 empty] | Lead
1.4.5.3 | Manage and track VOs software requirements. | 2009-10-01 | 2010-09-30 | Rana, Roy | [13 empty] | Lead | Support
1.5 | Engagement |  |  | McGee | [12 empty] | Lead
1.5.1 | Engage at least 15 new users during year 4 | 2009-10-01 | 2010-09-30 | McGee, Rynge | [12 empty] | Lead
1.5.2 | Support the campus engagements efforts in coordination with Goasguen | 2009-10-01 | 2010-09-30 | McGee, Rynge | [12 empty] | Lead
1.5.3 | Investigate the inclusion of GlideinWMS into the hosted services for user engagements | 2009-10-01 | 2010-09-30 | Rynge | [12 empty] | Lead
1.5.4 | Investigate a viral engagement model: a successfully engaged researcher helping a new user on our behalf | 2009-10-01 | 2010-09-30 | McGee | [12 empty] | Lead
1.5.5 | Publish a paper, article, or tech report on the engagement process and model | 2009-10-01 | 2010-09-30 | McGee | [12 empty] | Lead
1.5.6 | Develop preliminary results for a broader national engagement strategy, with a geographically and science-domain diverse set of collaborators | 2009-10-01 | 2010-09-30 | McGee | [12 empty] | Lead
1.5.7 | Enable ITER application advertisement and central submission/multi-site broking using OSGMM. Goal of 5 ITER users | 2009-10-01 | 2010-09-30 | Green, Garzoglio |  |  |  |  | Lead
1.5.8 | Verify sustainable production validation operations for Geant4 VO for next pre-release. Ensure ability to troubleshoot new and failing sites using existing tools in use by Geant4 (GANGA, DIANE, WLCG-WMS) | 2009-10-01 | 2010-09-30 | Green, Garzoglio |  |  |  |  | Lead
1.5.9 | Develop scalable OSG-TG gateway operations using GT2 & GT4 and multi-site matching. Bring multiple applications online to use gateway going forward. ** | 2009-10-01 | 2010-09-30 | Green, Garzoglio |  |  |  |  | Lead
1.5.10 | Develop OSG-TG gateway to handle MPI applications ** | 2009-10-01 | 2010-09-30 | Green, Garzoglio |  |  |  |  | Lead
1.5.11 | Continue engagement with genetics group from Arizona | 2009-10-01 | 2010-09-30 | Thain | [14 empty] | Lead
1.5.12 | Work with STAR folks to get the VM running in GLOW/OSG | 2009-10-01 | 2010-09-30 | Thain | [14 empty] | Lead
1.5.13 | Work on MPI code in OSG | 2009-10-01 | 2010-09-30 | Thain | [14 empty] | Lead
1.5.14 | In coordination with the Training Area, develop, deploy, field test, and assess an online training module for one common model of OSG usage from the engagement program | 2009-10-01 | 2010-09-30 | McGee, Weichel |  |  |  |  | Support | [7 empty] | Lead
1.6 | Campus Grids |  |  | Goasguen |  |  |  | Lead
1.6.1 | Organize One Campus grid ( and possibly connect to OSG) | 2009-10-01 | 2010-03-01 | Goasguen |  |  |  | Lead
1.6.2 | Organize Second Campus grid ( and possibly connect to OSG) | 2010-01-01 | 2010-08-01 | Goasguen |  |  |  | Lead
1.6.3 | Gratia probe accounting for BOINC work to OSG done | 2009-05-01 | 2009-12-01 | Goasguen |  |  |  | Lead
1.6.4 | Define Campus grid success | 2009-10-01 | 2009-12-01 | Goasguen |  |  |  | Lead
1.6.5 | Draft Campus Grid vision and action steps | 2009-10-01 | 2009-12-01 | Goasguen |  |  |  | Lead
1.6.6 | Campus Infrastructure Workshop (in Chicago) | 2009-10-01 | 2009-12-09 | Goasguen, Gardner |  |  | Support | Lead
1.7 | Security |  |  | Altunay |  |  |  |  | Lead
1.7.1 | Increased Support for Sites (T3-T2-T1) and VOs |  |  | Barlow | [9 empty] | Lead
1.7.1.1 | Direct communication with VO and site contacts. Concrete goal: a phone call with a site and VO contact per week. | 2009-09-01 | 2010-10-01 | Barlow, Altunay |  |  |  |  | Support |  |  |  |  | Lead
1.7.1.2 | Understand security environment of VO and site. (Friendly conversation, not a hostile security questionnaire. VO security contact may not know the security environment) | 2009-09-01 | 2010-10-01 | Barlow, Altunay |  |  |  |  | Support |  |  |  |  | Lead
1.7.1.3 | Understand what type of support needs are there. | 2009-09-01 | 2010-10-01 | Barlow, Altunay |  |  |  |  | Support |  |  |  |  | Lead
1.7.2 | Incident Response and Monitoring |  |  | Anand, Sfiligoi | [9 empty] | Lead |  |  |  | Support
1.7.2.1 | Focus on proactive monitoring tools | 2009-09-01 | 2010-10-01 | Anand, Altunay |  |  |  |  | Support |  |  |  |  | Lead
1.7.2.1.1 | Identify high level threats and if needed, find and/or develop monitoring tools for these threats (This is the only software development activity for next year) | 2009-09-01 | 2010-10-01 | Anand, Altunay |  |  |  |  | Support |  |  |  |  | Lead
1.7.2.1.2 | Use Gratia records to establish regular usage patterns in OSG. | 2009-09-01 | 2010-10-01 | Anand, Altunay |  |  |  |  | Support |  |  |  |  | Lead
1.7.2.1.3 | check if a site has applied announced patches. e.g. check access logs, check vdt version or look rsv probe results | 2009-09-01 | 2010-10-01 | Anand, Altunay |  |  |  |  | Support |  |  |  |  | Lead
1.7.2.2 | Conduct Incident Drills | 2009-09-01 | 2010-10-01 | Sfiligoi | [13 empty] | Lead
1.7.2.2.1 | Repeat WLCG drill against Tier-2 and Tier-1s | 2009-09-01 | 2010-10-01 | Sfiligoi | [13 empty] | Lead
1.7.2.2.2 | Drop a VO | 2009-09-01 | 2010-10-01 | Sfiligoi | [13 empty] | Lead
1.7.2.2.3 | Drop a site | 2009-09-01 | 2010-10-01 | Sfiligoi | [13 empty] | Lead
1.7.2.2.4 | Conduct a silent drill against OSG services to measure OSG staff’s awareness, e.g. show penetrating into VDT software cache, GOC security tickets, etc | 2009-09-01 | 2010-10-01 | Sfiligoi | [13 empty] | Lead
1.7.3 | Audit, Risk Assessment and Mitigation |  |  | Altunay, Barlow, Olson |  |  |  |  | Lead |  |  |  |  | Support | Support
1.7.3.1 | Mitigate risks found in RA infrastructure | 2009-07-30 |  | Olson | [10 empty] | Lead
1.7.3.2 | Document and Analyse certificate revocation Issues when an individual leaves a VO | 2009-08-20 | 2009-10-31 | Olson | [10 empty] | Lead
1.7.3.3 | Implement disaster recovery plans | 2009-07-30 |  | Olson | [10 empty] | Lead
1.7.3.4 | Implement or ask VDT and GOC to implement secure software distribution channels and secure CA distribution channels. | 2009-07-30 |  | Altunay, Roy, Quick |  |  |  |  | Lead |  |  | Support | [6 empty] | Support
1.7.3.5 | Implement or ask VDT to implement a vulnerability notification process with software providers | 2009-07-30 |  | Altunay, Roy |  |  |  |  | Lead | [9 empty] | Support
1.7.3.6 | Understand and review the software components in VDT. This is not a code-level audit. This is a general understanding of which authN, configuration variable and etc are used by a component. | 2009-09-01 | 2010-10-01 | Barlow | [9 empty] | Lead
1.7.3.7 | Transition to SHA-2 | 2009-09-01 | 2010-10-01 | Barlow | [9 empty] | Lead
1.7.4 | Education & Documentation |  |  | Olson, Altunay |  |  |  |  | Support | [5 empty] | Lead
1.7.4.1 | Contribute to documentation effort | 2009-07-30 | 2010-10-01 | Olson | [10 empty] | Lead
1.7.4.2 | Prepare How to guides: | 2009-07-30 | 2010-10-01 | Olson, Altunay |  |  |  |  | Support | [5 empty] | Lead
1.7.4.2.1 | How to respond to incidents | 2009-07-30 | 2010-10-01 | Olson | [10 empty] | Lead
1.7.4.2.2 | How to securely configure and install VDT (including non-security software) | 2009-07-30 | 2010-10-01 | Altunay |  |  |  |  | Lead
1.7.4.2.3 | How to operate a site securely (for site admins, day-day tasks, how to register with OIM, read security advisories, check security team’s signatures, etc) | 2009-07-30 | 2010-10-01 | Olson | [10 empty] | Lead
1.7.4.2.4 | How to access OSG for end user (get cert, import into a browser, renew, register with VOMS, etc) | 2009-07-30 | 2010-10-01 | Olson | [10 empty] | Lead
1.7.4.2 | Training | 2009-07-30 | 2010-10-01 | Altunay |  |  |  |  | Lead
1.4.2.2.1 | Security Training for OSG staff (once a year) | 2009-07-30 | 2010-10-01 | Altunay, Olson |  |  |  |  | Lead | [5 empty] | Support
1.4.2.2.2 | Security Training for sites, VO, users | 2009-07-30 | 2010-10-01 | Altunay, Olson |  |  |  |  | Lead | [5 empty] | Support
1.7.5 | Continuous Operational Security Tasks |  |  | Altunay, Barlow |  |  |  |  | Lead |  |  |  |  | Support
1.7.5.1 | respond to incidents | 2009-07-30 | 2010-10-01 | Altunay, Barlow, Olson, Padmanabhan, Sfiligoi |  |  |  |  | Lead |  |  |  |  | Support | Support |  |  | Support
1.7.5.2 | security tickets | 2009-07-30 | 2010-10-01 | Sfiligoi, Padmanabhan | [9 empty] | Support |  |  |  | Lead
1.7.5.3 | read software vulnerability bulletin boards for 3rd party software | 2009-07-30 | 2010-10-01 | Altunay, Barlow, Olson, Padmanabhan, Sfiligoi |  |  |  |  | Lead |  |  |  |  | Support | Support |  |  | Support
1.7.5.4 | prepare CA package | 2009-07-30 | 2010-10-01 | Barlow | [9 empty] | Lead
1.7.5.5 | Run RA | 2009-07-30 | 2010-10-01 | Olson | [10 empty] | Lead
1.7.5.6 | Prepare 2 identity workshop with ESNet | 2009-07-31 | 2009-11-01 | Olson | [10 empty] | Lead
1.7.5.7 | ST&E | 2009-08-01 | 2009-12-31 | Cudzewicz, Altunay |  |  |  |  | Lead
1.7.5.8 | update risk assessment document. | 2009-08-01 | 2009-12-31 | Altunay, Barlow, Olson |  |  |  |  | Lead |  |  |  |  | Support | Support
1.7.5.9 | attend EuGridPMA 3 times a year, Europe | 2009-07-30 | 2010-10-01 | Barlow | [9 empty] | Lead
1.7.5.10 | attend TAGPMA 2 times a year, Americas | 2009-07-30 | 2010-10-01 | Olson | [10 empty] | Lead
1.7.5.11 | attend JSPG only remote | 2009-07-30 | 2010-10-01 | Barlow | [9 empty] | Lead
1.7.5.12 | CA/CRL outages communicate to IGTF | 2009-07-30 | 2010-10-01 | Barlow, Olson | [9 empty] | Lead | Support
1.7.5.13 | OSG Review | 2009-12-01 | 2009-12-31 | Altunay |  |  |  |  | Lead
1.7.5.14 | Automated merging of VO packaged (Leftover from last year) | 2009-08-20 | 2009-10-20 | Sfiligoi | [13 empty] | Lead
1.7.5.15 | Build interactive comm mechanisms with security contacts | 2009-08-20 | 2009-12-31 | Altunay, Quick |  |  |  |  | Lead |  |  | Support
1.8 | Training and Content Management |  |  | Weichel | [5 empty] | Lead
1.8.1 | Content Management (Actual Documents for T3 and security, etc. are in other WBS areas and not duplicated here.) |  |  | Weichel | [5 empty] | Lead
1.8.1.1 | Define Architect Responsibilities | 2009-09-01 | 2009-11-01 | Weichel, Engel |  | Support |  |  |  | Lead
1.8.1.2 | Define workflow and responsibilities for production, review, and acceptance process for documentation | 2009-10-15 | 2009-12-15 | Weichel, Engel, Thapa, Mambelli, Gardner |  | Support | Support |  |  | Lead
1.8.1.3 | Create Documentation TWiki | 2009-12-01 | 2009-01-15 | Gross | [7 empty] | Lead
1.8.1.4 | Identify owners for each documentation area | 2009-12-01 | 2010-03-01 | Weichel, Engel |  | Support |  |  |  | Lead
1.8.1.5 | Develop adobe connect training for documentation owners/reviewers | 2009-12-15 | 2010-02-01 | Engel, tbd2-uc |  | Lead | Support
1.8.1.6 | Develop standards and templates for documents | 2010-01-01 | 2010-02-01 | Engel, Mambelli |  | Lead | Support
1.8.1.7 | Identify and Deploy technology for Annotation | 2009-10-01 | 2009-11-15 | Gross, Engel | [7 empty] | Lead | [5 empty] | Support
1.8.1.8 | Deploy technology for Document Rating and Collection of Ratings | 2009-10-01 | 2010-02-01 | Gross, Engel | [7 empty] | Lead | [5 empty] | Support
1.8.1.9 | Better organize documentation for each major role in OSG | 2009-11-01 | 2010-05-01 | Engel, Cartwright, Gross |  | Lead | [5 empty] | Support | [5 empty] | Support
1.8.1.10 | Implement an effective search for Documentation | 2010-03-01 | 2010-05-01 | Engel, Gross |  | Lead | [5 empty] | Support
1.8.1.11 | Get all documentation into Documentation TWiki | 2010-02-01 | 2010-09-30 | Gardner, Weichel, Mambelli, Gross |  |  | Lead
1.8.2 | Training (Development of specific training also appears in other WBS areas) |  |  | Weichel | [5 empty] | Lead
1.8.2.1 | Develop standard Training Process for OSG (Process, Templates, Info Capture, Adobe Connect, Student Feedback, etc.) | 2009-10-01 | 2009-12-15 | tbd2-uc, Weichel |  |  | Lead |  |  | Support
1.8.2.2 | Capture OSG delivered training on Adobe Connect | 2009-12-01 | 2010-09-30 | tbd2-uc, Roy, Altunay, Mambelli, Thapa |  |  | Lead |  | Support | [9 empty] | Support
1.8.2.3 | Provide adobe connect T3 Site Setup and Administration Training | 2009-11-01 | 2010-01-31 | Fraser, Mambelli, Thapa. tbd2-uc |  |  | Lead
1.8.2.4 | Assist OSG Staff developing Training sessions, making them accessible on-line, and getting student feedback | 2009-11-15 | 2010-09-30 | tbd2-uc |  |  | Lead
1.8.3 | Identify and prototype "personalized" email contact management system (email spoofing) | 2009-10-01 | 2009-12-31 | Weichel | [5 empty] | Lead
2.1 | Scalability, Reliability and Usability | 2009-10-01 | 2010-09-30 | Sfiligoi | [13 empty] | Lead
2.1.1 | Test scalability and reliability of storage. Includes dCache/SRM, Bestman/Hadoop, Bestman/xrootd and Bestman/NFS. | 2009-10-01 | 2010-09-30 | Sfiligoi, Martin, Padhi, Haifeng | [13 empty] | Lead
2.1.1.1 | Scalability goal is to get 50Hz for both SRM ls and cp of small files | 2009-10-01 | 2010-01-31 | Sfiligoi, Martin, Padhi, Haifeng | [13 empty] | Lead
2.1.1.2 | Scalability goal is to get 100Hz for both SRM ls and cp of small files | 2010-02-01 | 2010-09-30 | Sfiligoi, Martin, Padhi, Haifeng | [13 empty] | Lead
2.1.1.3 | Reliability goal is to get error rates as seen by jobs to below 5%. | 2009-10-01 | 2010-09-30 | Sfiligoi, Martin, Padhi, Haifeng | [13 empty] | Lead
2.1.1.4 | Profile IO characteristics of a sample of OSG sites | 2009-10-01 | 2009-12-31 | Sfiligoi, Haifeng | [13 empty] | Lead
2.1.2 | Test new CE middleware | 2009-10-01 | 2009-12-31 | Sfiligoi, Martin | [13 empty] | Lead
2.1.2.1 | Test GRAM5 | 2009-08-01 | 2009-12-31 | Sfiligoi, Martin | [13 empty] | Lead
2.1.2.2 | Test CREAM | 2009-10-01 | 2009-11-30 | Sfiligoi, Martin | [13 empty] | Lead
2.1.2.3 | Test ARC | 2009-11-01 | 2009-12-31 | Sfiligoi, Martin | [13 empty] | Lead
2.1.3 | Test scalability and reliability of glideinWMS. | 2009-10-01 | 2010-09-30 | Sfiligoi | [13 empty] | Lead
2.1.3.1 | Scalability goal is to scale to 40k running test jobs on single schedd and O(100) sites worldwide. | 2009-10-01 | 2010-09-30 | Sfiligoi | [13 empty] | Lead
2.1.3.2 | Reliability goal is to get O(20k) level system stable under heavy user activity. | 2009-10-01 | 2010-09-30 | Sfiligoi | [13 empty] | Lead
2.1.4 | Investigate and develop usability guidelines | 2010-01-01 | 2010-09-30 | Sfiligoi | [13 empty] | Lead
2.1.4.1 | Develop guidelines for local batch system installation and tuning | 2010-01-01 | 2010-03-31 | Sfiligoi | [13 empty] | Lead
2.1.4.2 | Develop guidelines for efficiently and reliably accessing storage from the worker nodes | 2010-04-01 | 2010-06-30 | Sfiligoi | [13 empty] | Lead
2.1.4.3 | Investigate ease of use of non-standard/non-single-threaded applications | 2010-07-01 | 2010-09-30 | Sfiligoi | [13 empty] | Lead
2.1.4.4 | Assist Security team with end user documentation | 2010-07-01 | 2010-09-30 | Sfiligoi | [13 empty] | Lead
2.1.5 | Load test all services at least once every 6 months | 2009-10-01 | 2010-09-30 | Sfiligoi | [13 empty] | Lead
2.1.5.1 | Load test 2 sites | 2009-10-01 | 2010-09-30 | Sfiligoi | [13 empty] | Lead
2.1.5.2 | Load test OSG central services | 2009-10-01 | 2010-09-30 | Sfiligoi | [13 empty] | Lead
2.2 | Workload Management Systems |  |  | Potekhin | Lead
2.2.1 | Support of LHC experiments |  |  | Potekhin | Lead
2.2.1.1 | Complete integration of Panda WMS with WLCG SCAS system (ATLAS) | 2009-10-01 | 2009-11-15 | Caballero | Lead
2.2.1.2 | Implement Pilot job generation for ATLAS user analysis | 2009-10-01 | 2009-12-15 | Caballero | Lead
2.2.1.3 | Deploy glideinWMS (from CMS) to meet the needs of existing and emerging VO's | 2009-10-01 | 2010-09-30 | Sfiligoi | [13 empty] | Lead
2.2.2 | Use WMS to enhance OSG site testing |  |  | Potekhin | Lead
2.2.2.1 | Create a mechanism for submission of ITB testing jobs through Panda | 2009-10-01 | 2010-01-31 | Potekhin | Lead
2.2.3 | Improve data movement capabilities of WMS |  |  | Potekhin | Lead
2.2.3.1 | Create, test and maintain a running instance of the DataHost service | 2009-10-01 | 2010-09-30 | Potekhin | Lead
2.2.3.2 | Create a light-weight Panda Data Mover | 2010-01-01 | 2010-09-30 | Caballero | Lead
2.2.4 | Improve Panda monitoring capabilities |  |  | Potekhin | Lead
2.2.4.1 | Create a prototype of an improved monitoring framework for Panda | 2009-11-01 | 2010-04-01 | Potekhin | Lead
2.2.4.2 | Initiate migration from legacy monitoring system | 2009-03-01 | 2010-06-01 | Wenaus | Lead
2.2.5 | Leverage WMS capabilities of OSG for Engagement |  |  | Potekhin | Lead
2.2.5.1 | Create a Panda-based testbed for DUSEL | 2009-10-01 | 2009-12-31 | Caballero | Lead
2.2.5.2 | Introduce emerging VO's (Nonproliferation, Spectroscopy) to OSG WMS | 2009-10-01 | 2010-09-30 | Potekhin | Lead
2.4 | Internet2 | 2009-10-01 | 2010-09-30 | Carlson | [7 empty] | Lead
2.4.1 | LHC Support Activities | 2009-10-01 | 2010-09-30 | Carlson | [7 empty] | Lead
2.4.1.1 | Publish best pratices guide - Initial co | 2009-10-01 | 2009-11-01 | Carlson | [7 empty] | Lead
2.4.1.2 | Supply perfSONAR Performance Toolkit ISO image | 2009-10-01 | 2009-11-01 | Carlson | [7 empty] | Lead
2.4.1.3 | Assist in deplyoment and configuration of Toolkit based servers | 2009-10-01 | 2009-12-01 | Carlson | [7 empty] | Lead
2.4.1.4 | Maintain certralized perfSONAR infrastructure and services | 2009-10-01 | 2009-09-30 | Carlson | [7 empty] | Lead
2.4.2 | Provide operationsl training and support | 2009-10-01 | 2009-09-30 | Carlson | [7 empty] | Lead
2.4.2.1 | Provide hands-on training to OSG site-admins at scheduled workshops | 2009-10-01 | 2009-09-30 | Carlson | [7 empty] | Lead
2.4.2.2 | Develop on-line training guilde - Howto monitor a site | 2010-01-01 | 2010-04-01 | Carlson | [7 empty] | Lead
2.4.2.3 | Develop on-line training guide - Howto debug performance problems | 2010-03-01 | 2010-06-01 | Carlson | [7 empty] | Lead
2.4.3 | Tool integration | 2009-10-01 | 2010-09-30 | Carlson | [7 empty] | Lead
2.4.3.1 | Supply code updates for client tools | 2009-10-01 | 2010-09-30 | Carlson | [7 empty] | Lead
2.4.3.2 | Assist in the wide-spread deployment of Performance Toolkit based servers | 2009-10-01 | 2010-09-30 | Carlson | [7 empty] | Lead
3.1 | Metrics |  |  | Bockelman | [11 empty] | Lead
3.1.1 | OSG Storage, Network, and Transfer Reports |  |  | Bockelman | [11 empty] | Lead
3.1.1.1 | Continue to monitor sites reporting transfer and storage data | 2009-10-01 | 2010-09-30 | Bockelman, Arunachalam | [11 empty] | Lead
3.1.1.2 | Deploy daily Gratia-based transfer and storage reports | 2009-10-01 | 2009-12-01 | Bockelman, Arunachalam | [11 empty] | Lead
3.1.1.3 | Collaborate with I2 to develop network metrics | 2009-10-01 | 2009-12-01 | Bockelman, Carlson | [8 empty] | Support |  |  | Lead
3.1.1.4 | Collect network metrics into Gratia collector | 2010-01-01 | 2010-04-01 | Bockelman, Green |  |  |  |  | Support | [6 empty] | Lead
3.1.1.5 | Update Gratia transfer/storage reports with network metrics | 2010-04-01 | 2010-06-01 | Bockelman, Arunachalam | [11 empty] | Lead
3.1.1.6 | Collaborate with external SE developers on improved probes | 2009-10-01 | 2010-09-30 | Bockelman | [11 empty] | Lead
3.1.2 | Maintenance and Sustainability |  |  | Bockelman | [11 empty] | Lead
3.1.2.1 | Update Gratia to collect historical batch system status info | 2009-10-01 | 2009-11-01 | Bockelman | [11 empty] | Lead
3.1.2.2 | Switch all reports to be based on Gratia | 2009-11-01 | 2010-02-01 | Bockelman | [11 empty] | Lead
3.1.2.3 | Package all metrics reports to be run at GOC | 2009-12-01 | 2010-02-01 | Bockelman | [11 empty] | Lead
3.1.2.4 | Deploy all metrics reports at GOC | 2010-02-01 | 2010-04-01 | Bockelman | [11 empty] | Lead
3.1.3 | Ongoing reports |  |  | Bockelman | [11 empty] | Lead
3.1.3.1 | Continue eJOT reports | 2009-10-01 | 2010-09-30 | Bockelman | [11 empty] | Lead
3.1.3.2 | Review metric thumbnails with Production Coordinator | 2009-10-01 | 2009-12-01 | Bockelman | [11 empty] | Lead
3.1.3.3 | Based on output from 3.1.2.1, possibly continue thumbnails | 2009-12-01 | 2010-09-30 | Bockelman | [11 empty] | Lead
3.1.4 | Internal Metrics ** |  |  | Bockelman | [11 empty] | Lead
3.1.4.1 | Review Year 3 Internal Metrics with ET | 2009-10-01 | 2009-11-01 | tbd | [11 empty] | Lead
3.1.4.2 | Update Internal Metrics | 2009-10-01 | 2009-11-15 | tbd | [11 empty] | Lead
3.1.4.3 | Year 4 Internal Metrics Mid-term report | 2010-01-01 | 2010-03-01 | tbd | [11 empty] | Lead
3.1.4.4 | Year 4 Internal Metrics Final report | 2010-08-01 | 2010-10-01 | tbd | [11 empty] | Lead
3.1.5 | Information Systems Consistency |  |  | Bockelman | [11 empty] | Lead
3.1.5.1 | Create inventory of information system information | 2009-10-01 | 2009-11-01 | Bockelman | [11 empty] | Lead
3.1.5.2 | Create implementation plan for consistency checker | 2010-11-01 | 2010-01-15 | Bockelman | [11 empty] | Lead
3.1.5.3 | Implement consistency checker | 2010-01-15 | 2010-05-01 | Bockelman | [11 empty] | Lead
3.1.5.4 | Operate consistency checker | 2010-05-01 | 2010-09-30 | Bockelman, Quick | [7 empty] | Support |  |  |  | Lead
3.1.6 | Liason to External Software Projects | 2009-10-01 | 2010-09-30 | Bockelman | [11 empty] | Lead
3.1.6.1 | Gratia | 2009-10-01 | 2010-09-30 | Bockelman | [11 empty] | Lead
3.1.6.2 | MyOSG | 2009-10-01 | 2010-09-30 | Bockelman | [11 empty] | Lead
3.2 | Communications and Education |  |  | Ritchie |  |  |  |  | Lead
3.2.1 | Provide Communications |  |  | Ritchie |  |  |  |  | Lead
3.2.1.1 | Provide Communications to Wide Area Audiences | 2009-10-01 | 2010-09-30 | Ritchie, Teckenbrock |  |  |  |  | Lead
3.2.1.1.1 | Communicate via print media | 2009-10-01 | 2010-09-30 | Ritchie, Teckenbrock |  |  |  |  | Lead
3.2.1.1.2 | Communicate via multi-media | 2009-10-01 | 2010-09-30 | Ritchie, Urish, Teckenbrock |  |  |  |  | Lead
3.2.1.2 | Provide Communications to External Communicators | 2009-10-01 | 2010-09-30 | Ritchie, Teckenbrock |  |  |  |  | Lead
3.2.1.2.1 | Communicate via one-on-one email conversations | 2009-10-01 | 2010-09-30 | Ritchie, Teckenbrock |  |  |  |  | Lead
3.2.1.2.2 | Communicate via Quarterly Phone Meetings | 2009-10-01 | 2010-09-30 | Ritchie, Teckenbrock |  |  |  |  | Lead
3.2.1.2.3 | Communicate via Annual Face-To-Face at AHM | 2009-10-01 | 2010-09-30 | Ritchie |  |  |  |  | Lead
3.2.1.3 | Produce Research Highlights | 2009-10-01 | 2010-09-30 | Ritchie |  |  |  |  | Lead
3.2.1.4 | Produce iSGTW | 2009-10-01 | 2010-09-30 | Ritchie, Boon |  |  |  |  | Lead
3.2.1.5 | Produce OSG News | 2009-10-01 | 2010-09-30 | Ritchie |  |  |  |  | Lead
3.2.2 | Provide Education |  |  | Ritchie |  |  |  |  | Lead
3.2.2.1 | Contribute to National CyberInfrastructure Education Activities | 2009-10-01 | 2010-09-30 | Ritchie |  |  |  |  | Lead
3.2.2.1.1 | Joint OSG TeraGrid Student programs at OSG AH | 2009-10-01 | 2010-09-30 | Ritchie, tbd2-uc |  |  |  |  | Lead
3.2.2.1.2 | Joint OSG TeraGrid Student programs at TG10 | 2009-10-01 | 2010-09-30 | Ritchie, tbd2-uc |  |  |  |  | Lead
3.2.2.1.3 | SuperComputing 09 Education Programs | 2009-10-01 | 2010-09-30 | Ritchie, tbd2-uc |  |  |  |  | Lead
3.2.2.1.4 | Grace Hopper | 2009-10-01 | 2010-09-30 | Ritchie, tbd2-uc |  |  |  |  | Lead
3.2.2.2 | Publicise OSG Computer Science Fellowship program | 2009-10-01 | 2010-09-30 | Ritchie, tbd2-uc |  |  |  |  | Lead
3.2.2.3 | Publicise OSG intern and summer student activities | 2009-10-01 | 2010-09-30 | Ritchie, tbd2-uc |  |  |  |  | Lead
3.2.3 | Track Publications |  |  | Ritchie, Rana |  |  |  |  | Lead
3.2.3.1 | Track and document publications By OSG Members | 2009-10-01 | 2010-09-30 | Ritchie, Rana |  |  |  |  | Lead
3.2.3.2 | Track and document publications in which OSG resources are responsible for research results | 2009-10-01 | 2010-05-30 | Ritchie, Rana |  |  |  |  | Lead
3.3 | Project Management |  |  | Sehgal |  |  |  |  | Lead
3.3.1 | Complete work plan definition for year4 |  |  | Sehgal |  |  |  |  | Lead
3.3.1.1 | Establish WBS, staff plan, and budget | 2009-08-01 | 2009-08-30 | Sehgal |  |  |  |  | Lead
3.3.1.2 | Generate SOWs and circulate for approvals with institutions | 2009-09-01 | 2009-09-30 | Sehgal |  |  |  |  | Lead
3.3.1.3 | Achieve 85% OSG internal sign-off on sub-contract affecting SOWs | 2009-10-01 | 2009-11-15 | Sehgal |  |  |  |  | Lead
3.3.2 | Track financial status and work progress execution |  |  | Sehgal |  |  |  |  | Lead
3.3.2.1 | Bi-Weekly Area Coordinator Meetings to review progress | 2009-10-01 | 2010-09-30 | Sehgal, tbd |  |  |  |  | Lead
3.3.2.2 | Monthly WBS update | 2009-10-01 | 2010-09-30 | Sehgal, tbd |  |  |  |  | Lead
3.3.2.3 | Quarterly Financial Reports | 2009-10-01 | 2010-09-30 | Sehgal, tbd |  |  |  |  | Lead
3.3.3 | Support the OSG interaction with funding agencies |  |  | Sehgal |  |  |  |  | Lead
3.3.3.1 | Support the OSG-ET in effective interaction with the OSG-JOT | 2009-10-01 | 2010-09-30 | Sehgal |  |  |  |  | Lead
3.3.3.2 | Coordinate the production of the annual DOE report | 2009-12-01 | 2009-12-22 | Sehgal, Avery |  |  |  |  | Co-lead | Co-lead
3.3.3.3 | Coordinate the creation and delivery of FWPs to DOE | 2010-01-30 | 2010-02-28 | Sehgal, Wenaus, Olson | Support |  |  |  | Lead | [5 empty] | Support
3.3.3.4 | Support OSG review with NSF/DOE, if needed | 2009-12-01 | 2010-01-30 | Sehgal |  |  |  |  | Lead
3.3.3.5 | Coordinate the production of the annual NSF report | 2009-06-01 | 2010-06-30 | Sehgal, Avery |  |  |  |  | Co-lead | Co-lead
3.3.4 | Organize and maintain OSG policies |  |  | Sehgal, tbd |  |  |  |  | Lead
3.3.4.1 | Baseline structure and determine additional needs | 2009-10-01 | 2009-10-30 | Sehgal, tbd |  |  |  |  | Lead
3.3.4.2 | Complete population of policies | 2009-11-01 | 2010-02-01 | Sehgal, tbd |  |  |  |  | Lead
3.3.5 | Establish effective methods for working with Satellite proposals |  |  | Sehgal |  |  |  |  | Lead
3.3.5.1 | Proposal for concurrence by OSG-ET | 2009-10-01 | 2009-11-15 | Sehgal |  |  |  |  | Lead
3.3.5.2 | Implement plan | 2009-12-01 | 2010-01-05 | Sehgal |  |  |  |  | Lead
3.3.6 | Evaluate and report quarterly on the state of work execution and action item tracking | 2009-10-01 | 2010-09-30 | Sehgal |  |  |  |  | Lead
3.3.7 | Provide planning support (estimated to by 0.5 FTE for 6 months) to the OSG-ET and OSG Council for the "future of OSG" proposal | 2009-11-01 | 2010-04-30 | Sehgal |  |  |  |  | Lead