## Sheet1
WBS_Number | Work_Item | Start | Finish | Owners
1.0.4 | LIGO | 2010-10-01 | 2011-09-30 | Blackburn
1.0.4.1 | Sustain LIGO E@H science production on OSG | 2010-10-01 | 2011-09-30 | Engel
1.0.4.1.1 | Evaluate and adopt glideinWMS, if appropriate | 2011-01-15 | 2011-04-15 | Engel
1.0.4.1.2 | Operate production submission "factory" and resolve issues | 2010-10-01 | 2011-09-30 | Engel
1.0.4.2 | Transition LIGO Binary Inspiral Workflow into production mode on OSG | 2010-10-01 | 2011-09-30 | Daudert, Engel
1.0.4.2.1 | Develop and deploy data movement plan (movement, validation, cataloging) | 2010-10-01 | 2010-11-01 | Daudert, Engel, Levshina
1.0.4.2.2 | Develop and deploy execution environment using Pegasus and Corral-WMS | 2010-10-01 | 2011-01-15 | Daudert, Engel, Rynge
1.0.4.2.3 | Demonstrate scalable sustained production over multiple sites | 2011-02-01 | 2011-06-30 | Daudert, Engel, Rynge
1.0.4.2.4 | Operate production submission "factory" and resolve issues | 2011-06-01 | 2011-09-30 | Daudert, Engel