## Task_Table1
ID | WBS | Name | InCharge | Duration | Predecessors | Start_Date | Finish_Date
0 | 0 | Future OSG CA Project | Altunay | 305 days |  | 2/2/15 8:00 AM | 4/1/16 5:00 PM
1 | 1 | Planning Phase | Altunay | 19 days |  | 2/2/15 8:00 AM | 2/26/15 5:00 PM
2 | 1.1 | Finalize the MOU between OSG and XSEDE | Altunay, Sehgal | 2 days |  | 2/2/15 8:00 AM | 2/3/15 5:00 PM
3 | 1.2 | Development and Deployment Plan | Altunay, Quick, Hayashi | 5 days | 2 | 2/4/15 8:00 AM | 2/10/15 5:00 PM
4 | 1.3 | Transition Plan | Hill | 3 days | 3 | 2/11/15 8:00 AM | 2/13/15 5:00 PM
5 | 1.4 | Acceptance Test Plan | Hill | 3 days | 4 | 2/16/15 8:00 AM | 2/18/15 5:00 PM
6 | 1.5 | Communications Plan | Clemmie | 3 days | 5 | 2/19/15 8:00 AM | 2/23/15 5:00 PM
7 | 1.6 | Decide whether CILogon HSM or OSG will post the CRL file on the Internet. If needed, generate a process and publish the CRL file. | Altunay, Basney | 3 days | 6 | 2/24/15 8:00 AM | 2/26/15 5:00 PM
8 | 2 | Development Phase | Altunay | 111 days | 1 | 2/27/15 8:00 AM | 7/31/15 5:00 PM
9 | 2.1 | OIM software development | Hayashi | 25 days |  | 2/27/15 8:00 AM | 4/2/15 5:00 PM
10 | 2.1.1 | Document an initial SLA with XSEDE | Teige, Hayashi, Basney | 3 days |  | 2/27/15 8:00 AM | 3/3/15 5:00 PM
11 | 2.1.2 | Freeze the CILogon HSM API as seen by OSG | Basney | 2 days | 10 | 3/4/15 8:00 AM | 3/5/15 5:00 PM
12 | 2.1.3 | Integrate the OIM Backend with CILogon HSM service | Hayashi | 5 days | 11 | 3/6/15 8:00 AM | 3/12/15 5:00 PM
13 | 2.1.4 | Create the capability in OIM ITB for requesting test certs from CILogon HSM as well as DigiCert CA (the gating switch based on VO name) | Altunay, Hayashi | 15 days | 12 | 3/13/15 8:00 AM | 4/2/15 5:00 PM
14 | 2.2 | Testing | Thapa | 65 days | 9 | 4/3/15 8:00 AM | 7/2/15 5:00 PM
15 | 2.2.1 | Test certificate issuance in ITB | Hill, Thapa | 15 days |  | 4/3/15 8:00 AM | 4/23/15 5:00 PM
16 | 2.2.2 | Test use of certs in ITB (normal use cases) | Thapa, Cartwright, Theisen | 20 days | 15 | 4/24/15 8:00 AM | 5/21/15 5:00 PM
17 | 2.2.3 | Friendly user testing | tbd VOs | 30 days | 15,16 | 5/22/15 8:00 AM | 7/2/15 5:00 PM
18 | 2.3 | Decide on moving to deployment | Altunay, OSG-ET | 21 days | 14 | 7/3/15 8:00 AM | 7/31/15 5:00 PM
19 | 2.3.1 | Complete a report on testing results | Hill, Altunay | 5 days |  | 7/3/15 8:00 AM | 7/9/15 5:00 PM
20 | 2.3.2 | Review with OSG Management for go/no-go | Altunay, OSG-ET | 5 days | 19 | 7/10/15 8:00 AM | 7/16/15 5:00 PM
21 | 2.3.3 | Make a plan for minimizing the pain of changing user DN. Explore automated propagation of DNs to service owners | Hill | 5 days | 10,20 | 7/17/15 8:00 AM | 7/23/15 5:00 PM
22 | 2.3.4 | Validate with DigiCert CA on how long they will continue to publish CRLs and revoke OSG users certs as needed | Quick, Altunay | 3 days | 21 | 7/24/15 8:00 AM | 7/28/15 5:00 PM
23 | 2.3.5 | Document any necessary changes to OSG policies and procedures | Gross, Altunay | 3 days | 22 | 7/29/15 8:00 AM | 7/31/15 5:00 PM
24 | 3 | IGTF Accreditation | Altunay, Basney | 160 days | 1 | 2/27/15 8:00 AM | 10/8/15 5:00 PM
25 | 3.1 | Prepare and submit IGTF Submission package | Altunay, Hill, Basney | 40 days |  | 2/27/15 8:00 AM | 4/23/15 5:00 PM
26 | 3.2 | Receive approval from IGTF | Altunay | 120 days | 25 | 4/24/15 8:00 AM | 10/8/15 5:00 PM
27 | 4 | Deployment Phase | Altunay | 61 days | 8,24 | 10/9/15 8:00 AM | 1/1/16 5:00 PM
28 | 4.1 | Update/Execute Communication Plan | Clemmie | 1 day |  | 10/9/15 8:00 AM | 10/9/15 5:00 PM
29 | 4.2 | Distribute new IGTF bundle to OSG stakeholders | Padmanabhan | 10 days | 28 | 10/12/15 8:00 AM | 10/23/15 5:00 PM
30 | 4.3 | Wait for first wave VOs to deploy new IGTF bundle | Altunay | 20 days | 29 | 10/26/15 8:00 AM | 11/20/15 5:00 PM
31 | 4.4 | Cutover system from ITB to Production | Hayashi | 2 days | 30 | 11/23/15 8:00 AM | 11/24/15 5:00 PM
32 | 4.5 | Propagate the new user DNs automatically to VOMS admins, service owners | Hill | 20 days | 31 | 11/25/15 8:00 AM | 12/22/15 5:00 PM
33 | 4.6 | Complete implementing the changes to OSG Process and Policies | Gross, Teige | 5 days | 32 | 12/23/15 8:00 AM | 12/29/15 5:00 PM
34 | 4.7 | Update the SLA with CILogon | Teige, Hayashi, Basney | 3 days | 33 | 12/30/15 8:00 AM | 1/1/16 5:00 PM
35 | 5 | Transition | Altunay | 65 days | 27 | 1/4/16 8:00 AM | 4/1/16 5:00 PM
36 | 5.1 | Transition first wave of VOs | Hill, Gross | 20 days |  | 1/4/16 8:00 AM | 1/29/16 5:00 PM
37 | 5.2 | Management Review - Continue Transition? | Altunay, OSG-ET | 5 days | 36 | 2/1/16 8:00 AM | 2/5/16 5:00 PM
38 | 5.3 | Transition second wave of VOs | Hill, Gross | 20 days | 37 | 2/8/16 8:00 AM | 3/4/16 5:00 PM
39 | 5.4 | Transition all remaining VOs | Hill, Gross | 20 days | 38 | 3/7/16 8:00 AM | 4/1/16 5:00 PM