## Sheet1
ID | WBS | Agency | TaskName | InCharge | Summary | Start | Finish | %Complete | Ways and Means
232 | 1.4.4.1 | No | Organize Weekly-VO-Forum teleconferences, inviting select VOs and peer OSG Areas. | Rana, Ritchie, Teckenbrock | No | 2009-10-01 08:00 | 2010-09-30 | 75% | Continue successful activity
233 | 1.4.4.2 | No | Organize F2F Annual OSG VOs & Users Meeting. | Rana | No | 2010-07-01 08:00 | 2010-07-31 | 0%
234 | 1.4.4.3 | No | Organize F2F meetings with specific VOs as needed. | Rana, Pordes | No | 2009-10-01 08:00 | 2010-09-30 | 75%
235 | 1.4.4.4 | No | Serve as conduit for peer OSG Areas to facilitate at-large VOs matters. E.g., Content Mgt, Software, Sites Coordination, Storage, Scalability/Reliability/Usability. | Rana | No | 2009-10-01 08:00 | 2010-09-30 | 75%
236 | 1.4.4.5 | No | Collect VOs scientific publications (including ATLAS, CMS, LIGO) for annual DOE & NSF reports. | Ritchie, Rana | No | 2009-10-01 08:00 | 2010-09-30 | 100% | Have arranged to have the SPIRES Mirror at Fermilab catalog and tag with OSG and VO indicators OSG publications allowing generation of publication list reports for input to DOE / NSF
237 | 1.4.5 | No | Coordinate Stakeholder participation in OSG planning and software | Rana | Yes | 2009-10-01 08:00 | 2010-09-30 | 59%
238 | 1.4.5.1 | No | Organize periodic collection of VOs plans and requirements. Communicate VOs direct input to Council. | Rana | No | 2009-10-01 08:00 | 2010-09-30 | 66%
239 | 1.4.5.2 | No | Plan and execute pre-release software validation by VOs (including ATLAS, CMS, LIGO) on ITB. | Rana, Gardner | No | 2009-10-01 08:00 | 2010-09-30 | 35%
240 | 1.4.5.3 | No | Manage and track VOs software requirements. | Rana, Roy | No | 2009-10-01 08:00 | 2010-09-30 | 75%
241 | 1.5 | No | Engagement | McGee | Yes | 2009-10-01 08:00 | 2010-09-30 17:00 | 37%
242 | 1.5.1 | No | Engage at least 10 new users during year 4 | McGee, Rynge | No | 2009-10-01 08:00 | 2010-09-30 | 50%
244 | 1.5.4 | No | Investigate a viral engagement model: a successfully engaged researcher helping a new user on our behalf | McGee | No | 2009-10-01 08:00 | 2010-09-30 | 0%
245 | 1.5.5 | No | Publish a paper, article, or tech report on the engagement process and model | McGee | No | 2009-10-01 08:00 | 2010-09-30 | 0%
246 | 1.5.6 | No | Develop preliminary results for a broader national engagement strategy, with a geographically and science-domain diverse set of collaborators | McGee | No | 2009-10-01 08:00 | 2010-09-30 | 20%
247 | 1.5.7 | No | ISI Led Engagement tasks | Deelman | Yes | 2009-12-01 08:00 | 2010-09-30 17:00 | 12%
248 | 1.5.7.1 | No | Investigate the inclusion of GlideinWMS into the hosted services for user engagements | Rynge | No | 2009-12-01 08:00 | 2010-04-30 17:00 | 95%
249 | 1.5.7.2 | No | Monitor and administer the set of OSG Engagement hosted services | Rynge | No | 2009-12-01 08:00 | 2010-09-30 17:00 | 0%
250 | 1.5.7.3 | No | Develop plans for migrating Engage production services to the production environments such as GOC | Rynge | No | 2009-12-01 08:00 | 2010-07-01 17:00 | 0%
251 | 1.5.7.4 | No | Provide ongoing support and software maintenance for the OSG-MM | Rynge | No | 2009-12-01 08:00 | 2010-09-30 17:00 | 0%
252 | 1.5.7.5 | No | Investigate the application of new technologies for Engage including Pegasus, GlideinWMS, etc | Rynge | No | 2009-12-01 08:00 | 2010-07-30 17:00 | 0%
253 | 1.5.8 | No | FNAL Led Engagement tasks | Garzoglio | Yes | 2009-10-01 08:00 | 2010-09-30 | 72%
254 | 1.5.8.1 | No | Enable ITER application advertisement and central submission/multi-site broking using OSGMM. Goal of 5 ITER users | Green, Garzoglio | No | 2009-10-01 08:00 | 2010-09-30 | 41%
255 | 1.5.8.2 | No | Verify sustainable production validation operations for Geant4 VO for next pre-release. Ensure ability to troubleshoot new and failing sites using existing tools in use by Geant4 (GANGA, DIANE, WLCG-WMS) | Green, Garzoglio | No | 2009-10-01 08:00 | 2010-09-30 | 45%
258 | 1.5.9 | No | Wiconsin Led Engagement Tasks | Livny | Yes | 2009-10-01 08:00 | 2010-09-30 | 0%
259 | 1.5.9.1 | No | Continue engagement with genetics group from Arizona | Thain | No | 2009-10-01 08:00 | 2010-09-30 | 0%
260 | 1.5.9.2 | No | Work with STAR folks to get the VM running in GLOW/OSG | Thain | No | 2009-10-01 08:00 | 2010-09-30 | 0%
261 | 1.5.9.3 | No | Work on MPI code in OSG | Thain | No | 2009-10-01 08:00 | 2010-09-30 | 0%
263 | 1.5.15 | No | Document (on the twiki) the Engage Infrastructure - the list of services, the hardware and software platforms | McGee | No | 2010-01-20 08:00 | 2010-02-12 17:00 | 90%
264 | 1.6 | No | Campus Grids | tbd | Yes | 2009-05-01 08:00 | 2010-09-30 17:00 | 93%
265 | 1.6.1 | No | Organize One Campus grid ( and possibly connect to OSG) | tbd | No | 2009-10-01 08:00 | 2010-03-01 | 100%
266 | 1.6.2 | No | Organize Second Campus grid ( and possibly connect to OSG) | tbd | No | 2010-01-01 08:00 | 2010-08-01 | 100%
267 | 1.6.3 | No | Gratia probe accounting for BOINC work to OSG done | Goasguen | No | 2009-05-01 08:00 | 2009-12-01 | 100%
268 | 1.6.4 | No | Define Campus grid success | tbd | No | 2009-10-01 08:00 | 2009-12-01 | 0%
269 | 1.6.5 | No | Draft Campus Grid vision and action steps | Pordes, Livny | No | 2009-10-01 08:00 | 2009-12-01 | 30%
270 | 1.6.6 | No | Campus Infrastructure Workshop (in Chicago) | Gardner | No | 2009-10-01 08:00 | 2009-12-09 | 100%
271 | 1.6.7 | No | Maintain OSG EDU submit machine | Goasguen | No | 2009-10-01 08:00 | 2010-09-30 17:00 | 100%
272 | 1.6.8 | No | Evaluate use of CERNVM for campus grids | Goasguen | No | 2009-10-01 08:00 | 2010-03-31 | 100%
274 | 1.6.10 | No | Work with STAR to evaluate VM mechanisms on Clemson | Goasguen, Lauret | No | 2009-10-01 08:00 | 2009-12-31 | 100%
275 | 1.7 | No | Security | Altunay | Yes | 2009-07-30 08:00 | 2010-09-30 | 43%
276 | 1.7.1 | No | Increased Support for Sites (T3-T2-T1) and VOs | Barlow, Sfiligoi | Yes | 2009-09-01 08:00 | 2010-09-30 | 23%
277 | 1.7.1.1 | No | Direct communication with VO and site contacts. Concrete goal: a phone call with a site and VO contact per week. | Barlow, Sfiligoi | No | 2009-09-01 08:00 | 2010-09-30 | 20%
278 | 1.7.1.2 | No | Understand security environment of VO and site. (Friendly conversation, not a hostile security questionnaire. VO security contact may not know the security environment) | Barlow, Sfiligoi | No | 2009-09-01 08:00 | 2010-09-30 | 20%
279 | 1.7.1.3 | No | Understand what type of support needs exist in stakeholder community | Barlow, Sfiligoi | No | 2009-09-01 08:00 | 2010-09-30 | 30%
280 | 1.7.2 | No | Incident Response and Monitoring | Padmanabhan, Barlow, Altunay | Yes | 2009-09-01 08:00 | 2010-09-30 | 29%
281 | 1.7.2.1 | No | Focus on proactive monitoring tools | Padmanabhan, Altunay | Yes | 2009-09-01 08:00 | 2010-09-30 | 33%
282 | 1.7.2.1.1 | No | Identify high level threats and if needed, find and/or develop monitoring tools for these threats (This is the only software development activity for next year) | Padmanabhan, Altunay | No | 2009-09-01 08:00 | 2010-09-30 | 10%
283 | 1.7.2.1.2 | No | Use Gratia records to establish regular usage patterns in OSG. | Padmanabhan, Altunay | No | 2009-09-01 08:00 | 2010-09-30 | 0%
284 | 1.7.2.1.3 | No | check if a site has applied announced patches. e.g. check access logs, check vdt version or look rsv probe results | Padmanabhan, Altunay | No | 2009-09-01 08:00 | 2010-09-30 | 90%
285 | 1.7.2.2 | No | Conduct Incident Drills | Barlow | Yes | 2009-09-01 08:00 | 2010-09-30 | 25%
286 | 1.7.2.2.1 | No | Repeat WLCG drill against Tier-2 and Tier-1s | Barlow | No | 2009-09-01 08:00 | 2010-09-30 | 100%
287 | 1.7.2.2.2 | No | Drop a VO | Barlow | No | 2009-09-01 08:00 | 2010-09-30 | 0%
288 | 1.7.2.2.3 | No | Drop a site | Barlow | No | 2009-09-01 08:00 | 2010-09-30 | 0%
289 | 1.7.2.2.4 | No | Conduct a silent drill against OSG services to measure OSG staff’s awareness, e.g. show penetrating into VDT software cache, GOC security tickets, etc | Barlow | No | 2009-09-01 08:00 | 2010-09-30 | 0%
290 | 1.7.3 | No | Audit, Risk Assessment and Mitigation | Olson, Sfiligoi, Padmanabhan | Yes | 2009-07-30 08:00 | 2010-09-30 | 55%
291 | 1.7.3.1 | No | Mitigate risks found in RA infrastructure | Olson | No | 2009-07-30 08:00 | 2010-09-30 | 90%
292 | 1.7.3.2 | No | Document and Analyze certificate revocation Issues when an individual leaves a VO | Olson | No | 2009-08-20 08:00 | 2009-10-31 | 90%
293 | 1.7.3.3 | No | Implement disaster recovery plans | Olson | No | 2009-07-30 08:00 | 2010-09-30 | 70%
294 | 1.7.3.4 | No | Implement or ask VDT and GOC to implement secure software distribution channels and secure CA distribution channels. | Sfiligoi, Roy, Quick | No | 2009-07-30 08:00 | 2010-03-01 | 50%
295 | 1.7.3.5 | No | Implement or ask VDT to implement a vulnerability notification process with software providers | Sfiligoi, Roy | No | 2009-07-30 08:00 | 2010-03-01 | 100%
296 | 1.7.3.6 | No | Understand and review the software components in VDT. This is not a code-level audit. This is a general understanding of which authN, configuration variable and etc are used by a component. | Padmanabhan, Sfiligoi | No | 2009-09-01 08:00 | 2010-09-30 | 10%
297 | 1.7.3.7 | No | Transition to SHA-2 | Padmanabhan, Sfiligoi | No | 2009-09-01 08:00 | 2010-09-30 | 20%
298 | 1.7.4 | No | Education & Documentation | Olson, Altunay | Yes | 2009-07-30 08:00 | 2010-09-30 | 46%
299 | 1.7.4.1 | No | Contribute to documentation effort | Olson | No | 2009-07-30 08:00 | 2010-09-30 | 20%
300 | 1.7.4.2 | No | Prepare How to guides: | Olson, Altunay | Yes | 2009-07-30 08:00 | 2010-09-30 | 50%
301 | 1.7.4.2.1 | No | How to respond to incidents | Olson | No | 2009-07-30 08:00 | 2010-09-30 | 100%
302 | 1.7.4.2.2 | No | How to securely configure and install VDT (including non-security software) | Altunay | No | 2009-07-30 08:00 | 2010-09-30 | 0%
303 | 1.7.4.2.3 | No | How to operate a site securely (for site admins, day-day tasks, how to register with OIM, read security advisories, check security team’s signatures, etc) | Olson | No | 2009-07-30 08:00 | 2010-09-30 | 50%
304 | 1.7.4.2.4 | No | How to access OSG for end user (get cert, import into a browser, renew, register with VOMS, etc) | Olson | No | 2009-07-30 08:00 | 2010-09-30 | 50%
305 | 1.7.4.2 | No | Training | Altunay | Yes | 2009-07-30 08:00 | 2010-09-30 | 50%
306 | 1.7.4.2.1 | No | Security Training for OSG staff (once a year) | Altunay, Olson | No | 2009-07-30 08:00 | 2010-09-30 | 0%
307 | 1.7.4.2.2 | No | Security Training for sites, VO, users | Altunay, Olson | No | 2009-07-30 08:00 | 2010-09-30 | 100%
308 | 1.7.5 | No | Continuous Operational Security Tasks | Altunay, Barlow | Yes | 2009-07-30 08:00 | 2010-09-30 | 50%
309 | 1.7.5.1 | No | Respond to incidents | Barlow, Altunay, Olson, Padmanabhan, Sfiligoi | No | 2009-07-30 08:00 | 2010-09-30 | 50%
310 | 1.7.5.2 | No | Operational Security Tickets with GOC | Barlow | No | 2009-07-30 08:00 | 2010-09-30 | 50%
311 | 1.7.5.3 | No | Read software vulnerability bulletin boards for 3rd party software | Altunay, Barlow, Olson, Padmanabhan, Sfiligoi | No | 2009-07-30 08:00 | 2010-09-30 | 50%
312 | 1.7.5.4 | No | Prepare CA package | Olson | No | 2009-07-30 08:00 | 2010-09-30 | 50%
313 | 1.7.5.5 | No | Run RA | Olson | No | 2009-07-30 08:00 | 2010-09-30 | 50%
314 | 1.7.5.6 | No | Prepare 2 identity workshop with ESNet | Olson | No | 2009-07-31 08:00 | 2009-11-01 | 50%
315 | 1.7.5.7 | No | ST&E | Cudzewicz, Altunay | No | 2009-08-03 08:00 | 2009-12-31 | 0%
316 | 1.7.5.8 | No | Update risk assessment document. | Altunay | No | 2009-08-03 08:00 | 2009-12-31 | 30%
317 | 1.7.5.9 | No | Attend Security forums and advise stakeholders of proposed changes affecting their operations and inter-operability with other Grids | Altunay, Olson | Yes | 2009-10-01 08:00 | 2010-09-30 | 50%
318 | 1.7.5.9.1 | No | attend EuGridPMA 3 times a year, Europe | Olson | No | 2009-10-01 08:00 | 2010-09-30 | 50%
319 | 1.7.5.9.2 | No | attend TAGPMA 2 times a year, Americas | Olson | No | 2009-10-01 08:00 | 2010-09-30 | 50%
320 | 1.7.5.9.3 | No | attend JSPG only remote | Altunay | No | 2009-10-01 08:00 | 2010-09-30 | 50%
321 | 1.7.5.12 | No | CA/CRL outages communicate to IGTF | Olson | No | 2009-07-30 08:00 | 2010-09-30 | 100%
323 | 1.7.5.14 | No | Automated merging of VO packaged (Leftover from last year) | Sfiligoi | No | 2009-08-20 08:00 | 2009-10-20 | 85%
324 | 1.7.5.15 | No | Build interactive comm mechanisms with security contacts | Altunay, Quick | No | 2009-08-20 08:00 | 2009-12-31 | 100%
325 | 1.7.5.16 | No | Software Tickets with VDT | Sfiligoi | No | 2009-07-30 08:00 | 2010-09-30 | 0%
326 | 1.7.5.17 | No | Monitor results of RSV tests and Gratia reports | Altunay | No | 2009-08-20 08:00 | 2009-10-20 | 50%
327 | 1.8 | No | Training and Content Management | Weichel | Yes | 2009-09-01 08:00 | 2010-09-30 | 83%
328 | 1.8.1 | No | Content Management (Actual Documents for T3 and security, etc. are in other WBS areas and not duplicated here.) | Weichel | Yes | 2009-09-01 08:00 | 2010-09-30 | 72%
329 | 1.8.1.1 | No | Define Architect Responsibilities | Weichel, Engel | No | 2009-09-01 08:00 | 2009-11-01 | 100%
330 | 1.8.1.2 | No | Define workflow and responsibilities for production, review, and acceptance process for documentation | Weichel, Engel, Thapa, Mambelli, Gardner | No | 2009-10-15 08:00 | 2009-12-15 | 100%
331 | 1.8.1.3 | No | Create Documentation TWiki | Gross | No | 2009-12-01 08:00 | 2010-01-15 17:00 | 100%
332 | 1.8.1.4 | No | Identify owners for each documentation area | Weichel, Engel | No | 2009-12-01 08:00 | 2010-03-01 | 100%
334 | 1.8.1.6 | No | Develop standards and templates for documents | Engel, Mambelli | No | 2010-01-01 08:00 | 2010-02-01 | 80%
335 | 1.8.1.7 | No | Identify and Deploy technology for Annotation | Gross, Engel | No | 2009-10-01 08:00 | 2009-11-15 | 100%
337 | 1.8.1.9 | No | Better organize documentation for each major role in OSG | Engel, Cartwright, Gross | No | 2009-11-02 08:00 | 2010-05-01 | 20%
338 | 1.8.1.10 | No | Implement an effective search for Documentation | Engel, Gross | No | 2010-03-01 08:00 | 2010-05-01 | 60%
339 | 1.8.1.11 | No | Get all Documentation into new process | Weichel, Mambelli, Gross | No | 2010-02-01 08:00 | 2010-09-30 | 60%
340 | 1.8.2 | No | Training (Development of specific training also appears in other WBS areas) | Weichel | Yes | 2009-10-01 08:00 | 2010-09-30 | 91%
343 | 1.8.2.3 | No | Provide adobe connect T3 Site Setup and Administration Training | Fraser, Mambelli, Thapa. tbd2-uc | No | 2009-11-02 08:00 | 2010-01-31 | 0%
346 | 2 | No | Extensions | Wuerthwein, Wenaus | Yes | 2009-08-03 08:00 | 2010-09-30 | 59%
347 | 2.1 | No | Scalability, Reliability and Usability | Sfiligoi | Yes | 2009-08-03 08:00 | 2010-09-30 | 58%
348 | 2.1.1 | No | Test scalability and reliability of storage. Includes dCache/SRM, Bestman/Hadoop, Bestman/xrootd and Bestman/NFS. | Sfiligoi, Martin, Padhi, Pi | Yes | 2009-10-01 08:00 | 2010-09-30 | 42%
349 | 2.1.1.1 | No | Scalability goal is to get 50Hz for both SRM ls and cp of small files | Sfiligoi, Martin, Padhi, Pi | No | 2009-10-01 08:00 | 2010-01-31 | 90%
350 | 2.1.1.2 | No | Scalability goal is to get 100Hz for both SRM ls and cp of small files | Sfiligoi, Martin, Padhi, Pi | No | 2010-02-01 08:00 | 2010-09-30 | 50%
351 | 2.1.1.3 | No | Reliability goal is to get error rates as seen by jobs to below 5%. | Sfiligoi, Martin, Padhi, Pi | No | 2009-10-01 08:00 | 2010-09-30 | 20%
352 | 2.1.1.4 | No | Profile IO characteristics of a sample of OSG sites | Sfiligoi, Pi | No | 2009-10-01 08:00 | 2009-12-31 | 40%
353 | 2.1.2 | No | Test new CE middleware | Sfiligoi, Martin | Yes | 2009-08-03 08:00 | 2010-03-31 17:00 | 88%
354 | 2.1.2.1 | No | Test GRAM5 | Sfiligoi, Martin | No | 2009-08-03 08:00 | 2010-01-29 17:00 | 95%
355 | 2.1.2.2 | No | Test CREAM | Sfiligoi, Martin | No | 2009-11-02 08:00 | 2010-02-26 17:00 | 95%
356 | 2.1.2.3 | No | Test ARC | Sfiligoi, Martin | No | 2010-03-01 08:00 | 2010-03-31 17:00 | 20%
357 | 2.1.3 | No | Test scalability and reliability of glideinWMS. | Sfiligoi | Yes | 2009-10-01 08:00 | 2010-09-30 | 57%
358 | 2.1.3.1 | No | Scalability goal is to scale to 40k running test jobs on single schedd and O(100) sites worldwide. | Sfiligoi | No | 2009-10-01 08:00 | 2010-09-30 | 80%
359 | 2.1.3.2 | No | Reliability goal is to get O(20k) level system stable under heavy user activity. | Sfiligoi | No | 2009-10-01 08:00 | 2010-09-30 | 35%
360 | 2.1.4 | No | Investigate and develop usability guidelines | Sfiligoi | Yes | 2010-01-01 08:00 | 2010-09-30 | 37%
361 | 2.1.4.1 | No | Develop guidelines for local batch system installation and tuning | Sfiligoi | No | 2010-01-01 08:00 | 2010-03-31 | 100%
362 | 2.1.4.2 | No | Develop guidelines for efficiently and reliably accessing storage from the worker nodes | Sfiligoi | No | 2010-04-01 08:00 | 2010-06-30 | 0%
363 | 2.1.4.3 | No | Investigate ease of use of non-standard/non-single-threaded applications | Sfiligoi | No | 2010-07-01 08:00 | 2010-09-30 | 50%
364 | 2.1.4.4 | No | Assist Security team with end user documentation | Sfiligoi | No | 2010-07-01 08:00 | 2010-09-30 | 0%
365 | 2.1.5 | No | Load test all services at least once every 6 months | Sfiligoi | Yes | 2009-10-01 08:00 | 2010-09-30 | 75%
366 | 2.1.5.1 | No | Load test 2 sites | Sfiligoi | No | 2009-10-01 08:00 | 2010-09-30 | 50%
367 | 2.1.5.2 | No | Load test OSG central services | Sfiligoi | No | 2009-10-01 08:00 | 2010-09-30 | 100%
368 | 2.2 | No | Workload Management Systems | Potekhin | Yes | 2009-10-01 08:00 | 2010-09-30 | 60%
369 | 2.2.1 | No | Support of LHC experiments | Caballero | Yes | 2009-10-01 08:00 | 2010-09-30 | 54%
370 | 2.2.1.1 | No | Complete integration of Panda WMS with WLCG SCAS system (ATLAS) | Caballero | No | 2009-10-01 08:00 | 2009-11-15 | 100%
371 | 2.2.1.2 | No | Implement Pilot job generation for ATLAS user analysis | Caballero | No | 2009-10-01 08:00 | 2009-12-15 | 0%
372 | 2.2.1.3 | No | Deploy glideinWMS (from CMS) to meet the needs of existing and emerging VO's | Sfiligoi | No | 2009-10-01 08:00 | 2010-09-30 | 60%
373 | 2.2.2 | No | Use WMS to enhance OSG site testing | Potekhin | Yes | 2009-10-01 08:00 | 2010-01-31 | 100%
374 | 2.2.2.1 | No | Create a mechanism for submission of ITB testing jobs through Panda | Potekhin | No | 2009-10-01 08:00 | 2010-01-31 | 100%
375 | 2.2.3 | No | Improve data movement capabilities of WMS | Potekhin | Yes | 2009-10-01 08:00 | 2010-09-30 | 62%
376 | 2.2.3.1 | No | Create, test and maintain a running instance of the DataHost service | Potekhin | No | 2009-10-01 08:00 | 2010-09-30 | 100%
377 | 2.2.3.2 | No | Create a light-weight Panda Data Mover | Caballero | No | 2010-01-01 08:00 | 2010-09-30 | 10%
378 | 2.2.4 | No | Improve Panda monitoring capabilities | Potekhin | Yes | 2009-11-02 08:00 | 2010-05-31 17:00 | 100%
379 | 2.2.4.1 | No | Create a prototype of an improved monitoring framework for Panda | Potekhin | No | 2009-11-02 08:00 | 2010-04-01 | 100%
380 | 2.2.4.2 | No | Provide a JSON-based feed of Panda monitoring data to the ATLAS Dashboard | Potekhin | No | 2010-03-02 08:00 | 2010-05-31 17:00 | 100%
381 | 2.2.5 | No | Leverage WMS capabilities of OSG for Engagement | Potekhin | Yes | 2009-10-01 08:00 | 2010-09-30 | 32%
382 | 2.2.5.1 | No | Create a Panda-based testbed for DUSEL | Caballero | No | 2009-10-01 08:00 | 2009-12-31 | 100%
383 | 2.2.5.2 | No | Introduce emerging VO's (Nonproliferation, Spectroscopy) to OSG WMS | Potekhin | No | 2009-10-01 08:00 | 2010-09-30 | 15%
384 | 2.4 | No | Internet2 | Boote | Yes | 2009-09-29 08:00 | 2010-09-30 | 58%
385 | 2.4.1 | No | LHC Support Activities | Boote | Yes | 2009-09-29 08:00 | 2009-12-15 | 100%
386 | 2.4.1.1 | No | Publish best pratices guide - Initial version | Boote | No | 2009-10-01 08:00 | 2009-12-15 | 100%
387 | 2.4.1.2 | No | Supply perfSONAR Performance Toolkit ISO image | Boote | No | 2009-10-01 08:00 | 2009-11-01 | 100%
388 | 2.4.1.3 | No | Assist in deplyoment and configuration of Toolkit based servers | Boote | No | 2009-10-01 08:00 | 2009-12-01 | 100%
389 | 2.4.1.4 | No | Maintain certralized perfSONAR infrastructure and services | Boote | No | 2009-09-29 08:00 | 2009-09-30 | 100%
390 | 2.4.2 | No | Provide operationsl training and support | Boote | Yes | 2009-09-29 08:00 | 2010-06-01 | 1%
391 | 2.4.2.1 | No | Provide hands-on training to OSG site-admins at scheduled workshops | Boote | No | 2009-09-29 08:00 | 2009-09-30 | 100%
392 | 2.4.2.2 | No | Develop on-line training guilde - Howto monitor a site | Boote | No | 2010-01-01 08:00 | 2010-04-01 | 0%
393 | 2.4.2.3 | No | Develop on-line training guide - Howto debug performance problems | Boote | No | 2010-03-01 08:00 | 2010-06-01 | 0%
394 | 2.4.3 | No | Tool integration | Boote | Yes | 2009-10-01 08:00 | 2010-09-30 | 63%
395 | 2.4.3.1 | No | Supply code updates for client tools | Boote | No | 2009-10-01 08:00 | 2010-09-30 | 50%
396 | 2.4.3.2 | No | Assist in the wide-spread deployment of Performance Toolkit based servers | Boote | No | 2009-10-01 08:00 | 2010-09-30 | 75%
397 | 3 | No | Project Administration | Pordes | Yes | 2009-08-03 08:00 | 2010-09-30 | 31%
398 | 3.1 | No | Metrics | Bockelman | Yes | 2009-10-01 08:00 | 2010-09-30 | 28%
399 | 3.1.1 | No | OSG Storage, Network, and Transfer Reports | Bockelman | Yes | 2009-10-01 08:00 | 2010-09-30 | 24%
400 | 3.1.1.1 | No | Continue to monitor sites reporting transfer and storage data | Bockelman, Arunachalam | No | 2009-10-01 08:00 | 2010-09-30 | 25%
401 | 3.1.1.2 | No | Deploy daily Gratia-based transfer and storage reports | Bockelman, Arunachalam | No | 2009-10-01 08:00 | 2009-12-01 | 75%
402 | 3.1.1.3 | No | Collaborate with I2 to develop network metrics | Bockelman, Boote | No | 2009-10-01 08:00 | 2009-12-01 | 20%
403 | 3.1.1.4 | No | Collect network metrics into Gratia collector | Bockelman, Green | No | 2010-01-01 08:00 | 2010-04-01 | 0%
404 | 3.1.1.5 | No | Update Gratia transfer/storage reports with network metrics | Bockelman, Arunachalam | No | 2010-04-01 08:00 | 2010-06-01 | 0%
405 | 3.1.1.6 | No | Collaborate with external SE developers on improved probes | Bockelman | No | 2009-10-01 08:00 | 2010-09-30 | 25%
406 | 3.1.2 | No | Maintenance and Sustainability | Bockelman | Yes | 2009-10-01 08:00 | 2010-04-01 | 45%
407 | 3.1.2.1 | No | Update Gratia to collect historical batch system and cluster capacity information | Bockelman | No | 2009-10-01 08:00 | 2009-11-01 | 100%
408 | 3.1.2.2 | No | Switch all reports to be based on Gratia | Bockelman | No | 2009-11-02 08:00 | 2010-02-01 | 50%
409 | 3.1.2.3 | No | Package all metrics reports to be run at GOC | Bockelman | No | 2009-12-01 08:00 | 2010-02-01 | 50%
410 | 3.1.2.4 | No | Deploy all metrics reports at GOC | Bockelman | No | 2010-02-01 08:00 | 2010-04-01 | 0%
411 | 3.1.2.5 | No | Coordinate change in the CPU normalization metric from SI2000 to HEPSPEC-06 | Bockelman | No | 2009-10-01 08:00 | 2010-01-31 | 40%
412 | 3.1.2.6 | No | Report the science of the user/VO for Sites | Bockelman | No | 2009-10-01 08:00 | 2010-02-28 | 50%
413 | 3.1.3 | No | Ongoing reports | Bockelman | Yes | 2009-10-01 08:00 | 2010-09-30 | 13%
414 | 3.1.3.1 | No | Continue eJOT reports | Bockelman | No | 2009-10-01 08:00 | 2010-09-30 | 25%
415 | 3.1.3.2 | No | Review metric thumbnails with Production Coordinator | Bockelman | No | 2009-10-01 08:00 | 2009-12-01 | 0%
416 | 3.1.3.3 | No | Based on output from 3.1.2.1, possibly continue thumbnails | Bockelman | No | 2009-12-01 08:00 | 2010-09-30 | 0%
417 | 3.1.4 | No | Internal Metrics | Weichel | Yes | 2009-10-01 08:00 | 2010-09-30 | 84%
418 | 3.1.4.1 | No | Review Year 3 Internal Metrics with ET | Weichel | No | 2009-10-01 08:00 | 2009-11-01 | 0%
422 | 3.1.5 | No | Information Systems Consistency | Bockelman | Yes | 2009-10-01 08:00 | 2010-09-30 | 8%
423 | 3.1.5.1 | No | Create inventory of information system information | Bockelman | No | 2009-10-01 08:00 | 2009-11-01 | 75%
424 | 3.1.5.2 | No | Create implementation plan for consistency checker | Bockelman | No | 2010-01-14 08:00 | 2010-01-15 | 25%
425 | 3.1.5.3 | No | Implement consistency checker | Bockelman | No | 2010-01-15 08:00 | 2010-05-01 | 0%
426 | 3.1.5.4 | No | Operate consistency checker | Bockelman, Quick | No | 2010-05-03 08:00 | 2010-09-30 | 0%
427 | 3.1.6 | No | Liason to External Software Projects | Bockelman | Yes | 2009-10-01 08:00 | 2010-09-30 | 25%
428 | 3.1.6.1 | No | Gratia | Bockelman | No | 2009-10-01 08:00 | 2010-09-30 | 25%
429 | 3.1.6.2 | No | MyOSG | Bockelman | No | 2009-10-01 08:00 | 2010-09-30 | 25%
430 | 3.1.7 | No | Live OSG key statistics display for DOE-ASCR | Bockelman | No | 2009-11-18 08:00 | 2010-02-17 17:00 | 50%
431 | 3.2 | No | Communications and Education | Ritchie | Yes | 2009-10-01 08:00 | 2010-09-30 | 7%
432 | 3.2.1 | No | Provide Communications | Ritchie | Yes | 2009-10-01 08:00 | 2010-09-30 | 13%
433 | 3.2.1.1 | No | Provide Communications to Wide Area Audiences | Ritchie, Teckenbrock | Yes | 2009-10-01 08:00 | 2010-09-30 | 5%
434 | 3.2.1.1.1 | No | Communicate via print media | Ritchie, Teckenbrock | No | 2009-10-01 08:00 | 2010-09-30 | 5% | Review need with OSG council representatives and/or survey to identify affordable need.
435 | 3.2.1.1.2 | No | Communicate via multi-media | Ritchie, Urish, Teckenbrock | No | 2009-10-01 08:00 | 2010-09-30 | 5% | Review need for print material with OSG council representives; survey to identify affordable need.
436 | 3.2.1.2 | No | Provide Communications to External Communicators | Ritchie, Teckenbrock | Yes | 2009-10-01 08:00 | 2010-09-30 | 5%
437 | 3.2.1.2.1 | No | Communicate via one-on-one email conversations | Ritchie, Teckenbrock | No | 2009-10-01 08:00 | 2010-09-30 | 5% | Except on a crisis need basis, these elements are not being accomplished due to the press of Fermilab-related work.
438 | 3.2.1.2.2 | No | Communicate via Quarterly Phone Meetings | Ritchie, Teckenbrock | No | 2009-10-01 08:00 | 2010-09-30 | 10% | Except on a crisis need basis (that's the 10%), these elements are not being accomplished due to the press of Fermilab-related work.
439 | 3.2.1.2.3 | No | Communicate via Annual Face-To-Face at AHM | Ritchie | No | 2009-10-01 08:00 | 2010-09-30 | 0%
440 | 3.2.1.3 | No | Produce Research Highlights | Ritchie | No | 2009-10-01 08:00 | 2010-09-30 | 0%
441 | 3.2.1.4 | No | Produce iSGTW | Ritchie, Boon | Yes | 2009-10-01 08:00 | 2010-09-30 | 40%
442 | 3.2.1.4.1 | No | Convene monthly meeting between iSGTW editor and OSG to identify ideas for articles | Ritchie, Boon | No | 2009-10-01 08:00 | 2010-09-30 | 40% | Meetings are occuring but they need to be more targeted as to what OSG wants consistent with editorial perogatives.
443 | 3.2.1.5 | No | Produce OSG News | Ritchie | No | 2009-10-01 08:00 | 2010-09-30 | 40% | Needs more resources put to it
444 | 3.2.2 | No | Provide Education | Ritchie | Yes | 2009-10-01 08:00 | 2010-09-30 | 0% | Except on a crisis need basis, these elements are not being accomplished due to the press of Fermilab-related work.
445 | 3.2.2.1 | No | Contribute to National CyberInfrastructure Education Activities | Ritchie | Yes | 2009-10-01 08:00 | 2010-09-30 | 0% | Effort relating to an NSF proposal has been discontinued..
446 | 3.2.2.1.1 | No | Joint OSG TeraGrid Student programs at OSG AH | Ritchie, tbd2-uc | No | 2009-10-01 08:00 | 2010-09-30 | 0% | I am not aware of any Joint OSG TeraGrid student progams at last year's OSG AH.
447 | 3.2.2.1.2 | No | Joint OSG TeraGrid Student programs at TG10 | Ritchie, tbd2-uc | No | 2009-10-01 08:00 | 2010-09-30 | 0% | It is my understanding that there is a commitment of DJR for a few days at TG10.
448 | 3.2.2.1.3 | No | SuperComputing 09 Education Programs | Ritchie, tbd2-uc | No | 2009-10-01 08:00 | 2010-09-30 | 0% | I am not aware of any Supercomputing 09 OSG education programs.
449 | 3.2.2.1.4 | No | Grace Hopper | Ritchie, tbd2-uc | No | 2009-10-01 08:00 | 2010-09-30 | 0% | I am not aware of any effort in the Grace Hopper area.
450 | 3.2.2.2 | No | Publicise OSG Computer Science Fellowship program | Ritchie, tbd2-uc | No | 2009-10-01 08:00 | 2010-09-30 | 0% | I am not aware of any effort in this area.
451 | 3.2.2.3 | No | Publicise OSG intern and summer student activities | Ritchie, tbd2-uc | No | 2009-10-01 08:00 | 2010-09-30 | 0% | I am not aware of any effort in this area.
452 | 3.2.3 | No | Track Publications | Ritchie, Rana | Yes | 2009-10-01 08:00 | 2010-09-30 | 0%
453 | 3.2.3.1 | No | Track and document publications By OSG Members | Ritchie, Rana | No | 2009-10-01 08:00 | 2010-09-30 | 0% | I believe that progress will be made in this area via the arrangements made with the Spires Mirror at the Fermilab library
454 | 3.2.3.2 | No | Track and document publications in which OSG resources are responsible for research results | Ritchie, Rana | No | 2009-10-01 08:00 | 2010-05-30 | 0% | I believe that progress will be made in this area via the arrangements made with the SPIRES Mirror at the Fermilab library