## Sheet1
WBS_Number | Work_Item | Start_Date | End_Date | Owners | Staff | Metrics
1.3 | Integration and Sites |  |  | Mambelli, Thapa
1.3.1 | Improve release processes for ITB |  |  | Thapa
1.3.1.1 | Adapt ITB testing process to native packaging tools | 2010-10-01 | 2011-09-30 | Thapa | Thapa | Number of new processes defined
1.3.1.2 | Provide installation packages and cache in a managed software repository | 2010-10-01 | 2011-09-30 | Thapa | Thapa | Number of packages modified
1.3.1.3 | Coordinate with GOC to provide testing of central services | 2010-10-01 | 2011-09-30 | Thapa | Thapa | # of services checked
1.3.1.4 | Coordinate with Security to provide testing of ca cert and certificate updates and changes | 2010-10-01 | 2011-09-30 | Thapa | Thapa | # of updates checked,
1.3.1.5 | Coordinate with Storage to provide more testing of storage releases and coverage of additional components as they are added | 2010-10-01 | 2011-09-30 | Thapa | Thapa | # of new packages tested
1.3.2 | Automate VTB & ITB Testing |  |  | Thapa
1.3.2.1 | Improve existing tests and integrate with osg test suite if possible | 2010-10-01 | 2011-09-30 | Thapa | Thapa
1.3.2.2 | Create site to present historical information on previous test runs | 2010-10-01 | 2010-12-31 | Thapa | Thapa | # of jobs, # of work-types, # submitters
1.3.2.3 | Provide clear and easy to understand report on tests conducted for each release | 2010-10-01 | 2011-09-30 | Thapa | Thapa | # of jobs, # of work-types, # submitters
1.3.3 | Improve management and operation of the persistent ITB |  |  | Thapa
1.3.3.1 | Revise VTB and ITB testing to speedup release cycle. | 2010-10-01 | 2011-09-30 | Thapa | Thapa, Sakrejda | Length of time for test cycle | 9
1.3.3.2 | Keep sites up to date with incremental updates. | 2010-10-01 | 2011-09-30 | Thapa | Sakrejda | Number of sites * number of updates | 9
1.3.3.3 | Commission OSG-dedicated persistent ITB site | 2010-10-01 | 2011-09-30 | Thapa | Thapa, Yehle | Number of ITB job slots, # GB
1.3.3.4 | Provide continuous monitoring of ITB resources. | 2010-10-01 | 2011-09-30 | Thapa | Thapa | Number of operational tickets + # issues
1.3.3.5 | Provide support for on-demand VO testing. | 2010-10-01 | 2011-09-30 | Thapa | Sakrejda | Number of VOs testing on-demand
1.3.3.6 | Virtualize ITB resources to allow testing to be reproduced reliably and to aid in troubleshooting | 2010-10-01 | 2011-01-31 | Thapa | Thapa | # of services and systems virtualized
1.3.3.7 | Setup configuration management of ITB site for better reliability | 2010-10-01 | 2010-12-31 | Thapa | Thapa
1.3.4 | Community building for site administrators |  |  | Mambelli
1.3.4.1 | Organize hands-on site administrator’s workshops. | 2010-10-01 | 2011-09-30 | Mambelli | Mambelli | Number of workshops, toal # participants
1.3.4.2 | Organize site administrators online meetings. | 2010-10-01 | 2011-09-30 | Mambelli | Mambelli | Number of onine meetings, total # particpants
1.3.4.3 | Support sites through chat support | 2010-10-01 | 2011-09-30 | Mambelli | Thapa, Sakrejda, Mambelli | Total number of Campfire hours
1.3.4.4 | Contribute to campus grids program of work to foster OSG spreading at the campus level | 2010-10-01 | 2011-09-30 | Mambelli | Mambelli, Thapa | Number of workshops+meetings; # new CG
1.3.4.5 | Create sites forum, blog, content collaborative platform | 2010-10-01 | 2011-09-30 | Mambelli | Mambelli | Number of registered users, page views, forum
1.3.5 | Documentation |  |  | Mambelli, Thapa
1.3.5.1 | Update documentation based on recommendations of documentation group | 2010-10-01 | 2011-09-30 | Thapa | Thapa, Sakrejda, Mambelli | Number of pages: created, edited, removed
1.3.5.2 | Review and prune existing documentation to remove outdated materials | 2010-10-01 | 2011-09-30 | Thapa | Thapa, Sakrejda, Mambelli | Number of pages: created, edited, removed
1.3.5.3 | Work with Content Management and Training to develop technical materials relevant to OSG site administrators. | 2010-10-01 | 2011-09-30 | Mambelli | Thapa, Sakrejda, Mambelli, Engel | Number of consultation hours given to C&T
1.3.5.4 | Contribute technical content and documentation relevant for OSG site administrators. | 2010-10-01 | 2011-09-30 | Mambelli | Thapa, Sakrejda, Mambelli, Engel | Number of pages: created, edited, removed
1.3.5.5 | Contribute technical documentation for automated testing | 2010-10-01 | 2011-09-30 | Thapa | Thapa | Number of pages: created, edited, removed
1.3.5.6 | Contribute technical content and documentation relevant for the persistent ITB. | 2010-10-01 | 2011-09-30 | Thapa | Thapa, Sakrejda, Engel | Number of pages: created, edited, removed
1.3.6 | Small Scale Sites |  |  | Mambelli
1.3.6.1 | Devise simplified configurations for small sites with limited IT support | 2010-10-01 | 2011-09-30 | Mambelli | Mambelli | # of recipes, average # of FTE needed to administer a small site, # of new sites joining OSG, # of VO and groups in OSG
1.3.6.2 | Write a alternative set of documents easier for new site administrators | 2010-10-01 | 2010-11-30 | Mambelli | Mambelli | Number of pages: created, edited, removed; average # of FTE needed to administer a small site, # of new sites joining OSG, # of VO and groups in OSG
1.3.6.3 | Survey which are the barriers for the entrance into OSG of smaller sites | 2010-10-01 | 2010-11-30 | Mambelli | Mambelli | Report
1.3.6.4 | Work with Production area to provide support for LHC Tier 3 sites. | 2010-10-01 | 2011-09-30 | Mambelli | Mambelli | Number of consultation hours given to T3
1.3.6.5 | Work with VO area to provide support forfor sites of other VOs, especially smaller sites with limited IT personnel | 2010-10-01 | 2011-09-30 | Mambelli | Mambelli | Number of consultation hours given to small sites
1.3.6.6 | Create, maintain and use a virtual Tier 3 cluster to test different configurations | 2010-10-01 | 2011-09-30 | Mambelli | Mambelli | Running cluster, possible options
1.3.6.7 | Test software solution targeting simple deployment for small sites | 2010-10-01 | 2011-09-30 | Mambelli | Mambelli | # of different configurations and tests