## Slide 1: OSG Area Coordinators Meeting Security Team Report
Mine Altunay
12/21/2011

## Slide 2
 | WBS Ongoing Activities | 
1 | Incident response and vulnerability assessment | Minimizing the end-end response time to an incident, 1 day for a severe incident, 1 week for a moderate incident, and 1 month for a low-risk incient.
2 | Troubleshooting; processing security tickets including user requests, change requests from stakeholders, technical problems | Goal is to acknowledge tickets within one day of receipt.
3 | Maintaining security scripts (vdt-update-certs, vdt-ca-manage, cert-scripts, etc) | Maintain and provide bug fixes according to the severity of bugs. For urgent problems, provide an update in one week; For moderate severity, provide an update in a month; For low risk problems, provide an update in 6 months.
4 | Supporting OSG RA in processing certificate requests | Each certificate request is resolved within one week; requests for GridAdmin and RA Agents are served within 3 days.
5 | Preparing CA releases (IGTF), modifying OSG software as the changes in releases require | CA release for every two months
6 | Security Policy work with IGTF, TAGPMA, JSPG and EGI | Meet with IGTF and TAGPMA twice a year. Attend JSPG and EGI meteings remotely and face-face once a year. Track security policy changes and report to OSG management.
7 | Security Test and Controls | Execute all the controls included in the Security Plan and prepare a summary analysis.
8 | Weekly Security Team Meeting to review work items | Coordinate weekly work items.
9 | Weekly reporting to OSG-Production | Report important items that will affect production; incidents, vulnerabilities, changes to PKI infrastructure
10 | Monthly reporting to OSG-ET | Meet with ET once a month to discuss work items
11 | Quarterly reporting to Area Coordinator meeting | Meet with area coordinators to discuss work items.

## Slide 3: Ongoing Work: Operational Security
1. Software Vulnerabilities/Incidents
  No major incidents.
  Gratia security updates,
  Supposed DOS attack at Fermilab – turned out to be non-security issue
  Ongoing attention still taking a lot of effort.
10. replaced by area coordinators reports. Will be dropped.
5. DOEGrids CA certificate change. The older CA cert will have lifetime issues after January 23, 2012.
  https://ticket.grid.iu.edu/goc/viewer?id=11270
  Quick turn around from ITB folks -- Many thanks.
  Tested and released into production by Dec 13.
6. Jim attended Federated ID management workshop in UK and TAGPMA

## Slide 4
4.1 | Identity Management | Basney, Altunay |  | 
4.1.1 | Work Plan agreed by OSG Management and Security team | Basney, Altunay | 8/1/11 | 9/15/11
4.1.2 | Integrate a UCSD VO with CILogon CA to utilize local resources | Basney, Altunay | 8/15/11 | 9/30/11
4.1.3 | Integrate a VO with Cilogon CA which can submit jobs to OSG resources | Basney, Altunay | 9/16/11 | 12/30/11
4.1.4 | Provide documented and supported alternatives to the DOEGrids CA for OSG host certificates | Basney, Altunay |  | 
4.1.4.1 | Set up a implementation testbed | Basney, Altunay | 9/30/11 | 10/30/11
4.1.4.2 | Integrate OSG host cert system with XSEDE CAs | Basney, Altunay | 10/30/11 | 7/15/12
4.1.7 | Enable user access without certificates | Basney, Altunay | 5/15/12 | 9/30/12
4.2 | Conduct Security Controls and Tests | Altunay, Slagell |  | 
4.2.1 | Execute the security controls in OSG Security Plan | Altunay, Slagell | 3/1/12 | 7/1/12
4.2.2 | Prepare a report on findings from the Security Controls | Altunay, Slagell | 7/1/12 | 7/22/12
Will not report on items that start after 1/1/12

## Slide 5: ID Management
Will update WBS to reflect DOE Grids CA transition
  4.1.1, 4.1.2, and 4.1.3 are complete
  4.1.4 replaced by Digicert Pilot. Integration with XSEDE to date does not need any work from Security on Cas.
DigiCert pilot
  Started on 10/25/2011. Goal to complete on 2/9/2012.
  Tested the new certificates on ITB. Completed on 12/14. Our original target date was 12/5.
  10-day delay was due to Digicert’s latency in giving us access to their portals and certificates
  ITB testing was difficult and time-consuming due to the number of components and ITB sites involved. The remaining items will not require help from outside of the pilot project members. Many thanks to ITB staff!
  Detailed WBS update is periodically sent to Proj Manager (Chander)

## Slide 6: SHA-2
Confusion here and in Europe on when SHA-2 certificates must be supported.
Clear that OSG cannot support Sha-2 certificates for many months given the amount of s/w that must be converted.
Must also support sha-1 and md5 simultaneously
Project currently being planned at https://twiki.grid.iu.edu/bin/view/Security/SHA2SupportProject
Actvity moved to Software with Alain as the lead. Security will help. Will not be in the security WBS.
  IGTF decided not to enforce or encourage any CAs to switch to SHA-2 immediately.
  EGI/WLCG struggles with complying with SHA-2 requirement.
  Project goal is to ensure OSG software stack that is compatible with SHA-2 end user certificates and proxies (without dropping support for MD5 and SHA-1).
  Contacted software providers and collecting their plans for sha-2 support.
  Tentative date so far is April. – is this realistic? Over to Alain to say.

## Slide 7: Action Items from Last report to Area Coordinators – will add to WBS
Switch to new layout CA bundles.
  Has been tested and released as default to production.
We have two separate processes for releasing CA bundles :
  one for releasing to Koji/VDT
  Other for releasing pacman packages via GOC.
  Review and reconciliation of the processes by software, operations and security teams due before the end of 2/2012

## Slide 8: New WBS Item
OSG consulting services requested by DES. Provide help on policies and procedures e.g. VO Policies and AUPs, User /Member Agreements, etc
Deliverable is more understanding of what documents are useful, what VO documents we can point to, a wiki page to make any further VO’s life easier.
Investigation stage. No due date is yet set.
Estimated to be 2 fte week worth of work. Mine will do this.

## Slide 9: Issues /Worries
DOE Grids CA transition implementation will be high priority and high visibility. Do we have confidence in the effort needed? It looks like handling of storage/data areas is not really understood or provided for.
Kevin Hill is a great asset. Need him to ramp up to full time before the ST&E start.
Not doing sufficient training – this is not on the WBS; should it be?