## general_report
Key | Summary | Priority | Due Date | Community Notification | Review Comments
MYOSG-74 | Update tooltip information on site icon on RSV Status Map page. | Major |  | No
MYOSG-70 | Add sam-bdii to top level bdii testing | Major | 2010-07-06 | No
MYOSG-60 | Create Operations Status Overview Page in MyOSG | Major |  | No | This view already exists: http://tinyurl.com/24y9x9v
MISC-63 | Install service monitor on is.grid | Major |  | No
MISC-55 | Remove USATLAS SC from FP's Support Center Team | Major |  | No
GOCTICKET-61 | Investigate why destination ticket ID was cleared on https://ticket.grid.iu.edu/goc/viewer?id=8753 | Major |  | No
DISPLAY-5 | Embed Brian's Tutorial Video | Major |  | No | Hey Soichi, I passed the URL to Ruth to get feedback from her. Any reason you suggested YouTube and not just keeping it on the FNAL media server? Brian
BDII-9 | BDII-8 Document steps required to: Allow SEs to publish to PRODUCTION BDII | Major |  | No
BDII-8 | Allow SEs to Publish to BDII | Major | 2010-07-06 | No
BDII-6 | Create Summary Report of Diff between reources reporting to CEMon (is1 vs is2) | Major |  | No
TX-25 | Discuss feasibility to create a new field "TX-Priority" | Minor |  | No
TX-15 | GGUS does not allow title update from our side but we allow GGUS to overwrrite GOCTicket title | Minor |  | No
RSV-32 | Create ReSS RSV Probe to use condor-status | Minor |  | No
RSV-29 | Add calculation of RG status (and availability/reliability if feasible) to RSVProcess | Minor |  | No
RSV-25 | Test glexec RSV Probe | Minor | 2010-05-04 | No
RSV-23 | RSV Should Creating a Proxy at Runtime | Minor | 2010-04-12 | Yes
RSV-15 | Quiet down the root emails sent by rsv-client3 when it updates CRLs and CA certs | Minor
OIM-37 | add check for SSL_CLIENT_VERIFY | Minor |  | No
OIM-33 | OIM-30 Confirm changes to required fields | Minor | 2010-06-04 | No
OIM-21 | Add help tooltips to various OIM fields | Minor |  | No
OIM-17 | Downtime editor does not allow deletions following a recent release | Minor |  | No
OIM-15 | Should "Degraded Service" be a downtime outage | Minor |  | Yes
OIM-13 | (Per OIM-12) How should we do software "testing" at GOC? | Minor
OIM-11 | Update VOMS information in OIM; generate two files in software cache | Minor
OIM-3 | Allow entering Resource Group wide downtime | Minor |  | Yes | Rob will chat with OSG stakeholders and management about the impact and priority of this change.
MYOSG-68 | MYOSG-60 Add central Gratia accounting server and software cache servers to GOC RSV monitoring | Minor |  | No
MYOSG-67 | Fix RSV status map anchor history issue | Minor |  | No
MYOSG-66 | Setup site environment parameter information gatherer | Minor | 2010-07-13 | No
MYOSG-57 | MyOSG's delayed fetch doesn't work correctly with FF 3.6 | Minor |  | No | I don't think a browser specific issue warrants a Major status. Let's do this when we have the time, but it is not a priority.
MYOSG-54 | MYOSG-41 Create XSD schema for BDII XML | Minor |  | No
MYOSG-53 | Add Open a Ticket on this Isse Link | Minor |  | No
MYOSG-51 | Check feasibility of using Ted Hesselroth's SE discovery tool for BDII information gathering (rendered on MyOSG) | Minor |  | No
MYOSG-50 | Eliminate duplicate counting of worker nodes, jobs, etc. between queues | Minor |  | No
MYOSG-42 | Create page where it shows OIM profile information | Minor |  | Yes
MYOSG-39 | MySQL CSV can't be open on Linux | Minor |  | No
MYOSG-38 | Request to tweak promo map (Ruth Pordes) | Minor |  | No
MYOSG-37 | Implement gratia metric detail storage system for rsvprocess | Minor |  | No
MYOSG-21 | MYOSG-18 Tweak RSVProcess consolidator to handle this change | Minor
MYOSG-20 | Modify how historical status is presented in MyOSG -> RGHistory | Minor
MYOSG-18 | Install updated GIP validator, and modify MyOSG's XML parser | Minor | 2010-02-02
MYOSG-13 | Publish job manager information (and perhaps others?) retrieved from BDII on MyOSG | Minor |  |  | LIGO and ATLAS have expressed interest in this information. Work on this should be postponed until high level OSG/GOC talks can determine the agreed upon place for OSG to gather this information.
MYOSG-11 | Document MyOSG API | Minor | 2009-12-30
MYOSG-2 | Install Brian's Gratia Graph on dev.grid | Minor | 2009-11-27
MISC-62 | Create a service-monitor check to detect process run off. | Minor |  | No
MISC-52 | Disable Footprints email attachment | Minor |  | Yes
MISC-48 | GOC Reports question | Minor |  | No
MISC-47 | Monitor Display for Freshness of Gratia Data | Minor |  | No
MISC-45 | Discussion of Network Monitoring from GRNOC to OSG Resources | Minor |  | No
MISC-43 | GOC_Authorization_Service status is UNKNOWN | Minor |  | No
MISC-42 | Trick Browser into reloading CSS File if it's new | Minor |  | No
MISC-37 | dev.grid's /var is 92% full. | Minor |  | No
MISC-35 | Requestfor ETA - Access to RT's Nagios instance | Minor |  | No
MISC-28 | Evaluate performance of OSG Display from downtime | Minor |  | No
MISC-27 | stemcell's /root directory is trashy | Minor |  | No
MISC-13 | What to do with http://www.grid.iu.edu/ | Minor
MISC-7 | MISC-6 Request display1, display2, and display RR from DNS admins | Minor
GOCTICKET-64 | Goc Ticket shows email address in tickets publicly.... | Minor | 2010-07-09 | No | Please investigate and get back to me.. I suppose
GOCTICKET-62 | Allow GOC Staff to access old ticket navigator | Minor |  | No
GOCTICKET-59 | Alain getting assigned tickets after 3pm | Minor |  | No
GOCTICKET-58 | Document FP dependencies of GOCTicket for GRNOC | Minor | 2010-06-29 | No
GOCTICKET-57 | GOCTICKET-56 Document steps to create a new GOCticket *application* instance | Minor | 2010-06-29 | No
GOCTICKET-56 | Add application instance for storage team ticketing (/storage) | Minor | 2010-06-29 | No
GOCTICKET-50 | GOCTICKET-45 Add "Hot Issue" button | Minor |  | No
GOCTICKET-49 | GOCTICKET-45 Similar ticket search | Minor |  | No
GOCTICKET-47 | GOCTICKET-45 Ticket Metadata Templates | Minor |  | No
GOCTICKET-46 | GOCTICKET-45 Blank GOC Ticket Creation Form | Minor |  | No
GOCTICKET-45 | Implement action items from GOC user experience lab | Minor |  | No
GOCTICKET-38 | Support is mistakenly sending notification from security address | Minor |  | No
GOCTICKET-36 | Support center flag to indicate unresponsive ones | Minor |  | No
GOCTICKET-33 | Report of Tickets Using the GGUS Exchange | Minor |  | No
GOCTICKET-26 | ReSS Tickets don't go to correct assignees | Minor |  | No
GOCTICKET-24 | More detail in update time. | Minor |  | No
GOCTICKET-18 | New Ticket View - All | Minor |  | No
GOCTICKET-12 | Investiage why FP SOAP API is so slow. | Minor
DISPLAY-8 | Create 30-day graphs | Minor |  | No
RSV-5 | Discuss replacing Gratia collector for GOC internal monitoring with MQ based system | Trivial
MYOSG-72 | Typo on MyOSG page | Trivial |  | No
MYOSG-45 | Selecting a "Specific Date" for the graphs | Trivial |  | No
MYOSG-30 | Add Open Tickets to Resource Summary | Trivial |  | No
MYOSG-10 | Update RSV Probe documentation | Trivial |  | No
MISC-44 | FermiGrid Systems Re-Rack | Trivial |  | No
MISC-3 | OSG Blog | Trivial | 2010-03-01