## Sheet1
WBS | Task | Start date | End date | Owners
1.5 | Engage
1.5.1 | User Engagement
1.5.1.1 | Engage 10 new users | 2010-10-01 | 2011-09-30 | McGee
1.5.1.2 | Continue MPI efforts across OSG | 2010-10-01 | 2011-09-30 | Thain
1.5.1.3 | Steffen Bass et al - thoughput and iRODS | 2010-10-01 | 2011-01-30 | McGee, S.Cox
1.5.2 | Engage Infrastructure
1.5.2.1 | Maintain existing infrastructure for existing users | 2010-10-01 | 2011-09-30 | McGee, S.Cox
1.5.2.2 | Investigate GlideinWMS as a replacement for OSGMM | 2010-10-01 | 2011-01-30 | S.Cox
1.5.2.3 | Support RENCI Science Portal as an OSG access mechanism | 2010-10-01 | 2011-09-30 | J.Reilly, S.Cox
1.5.2.4 | OSG Access to RENCI-BlueRidge | 2010-10-01 | 2010-11-30 | S.Cox
1.5.3 | Clemson Contributions
1.5.3.1 | Engage users requiring virtualization on OSG | 2010-10-01 | 2011-09-30 | Goasguen
1.5.3.2 | Work with campuses to deploy | 2010-10-01 | 2011-09-30 | Goasguen
1.5.3.3 | Investigate VM computing across OSG, Magelllan and Future Grid | 2010-10-01 | 2011-09-30 | Goasguen
1.5.4 | VO Engagement
1.5.4.1 | LSST | 2010-10-01 | 2011-09-30 | Garzoglio
1.5.4.2 | ITER | 2010-10-01 | 2011-09-30 | Garzoglio