## Sheet1
WBS Number | Work Item | Start Date | End Date | In Charge
1.0.1 | Software Tools Group |  |  | Roy, Altunay
1.0.1.1 | Continue overseeing OSG-owned software | 2010-10-01 | 2011-09-30 | Roy, Altunay
1.0.1.1.1 | RSV development | 2010-10-01 | 2011-09-30 | Roy, Altunay
1.0.1.1.2 | OIM development | 2010-10-01 | 2011-09-30 | Roy, Altunay
1.0.1.1.3 | OSG VO Map development | 2010-10-01 | 2011-09-30 | Roy, Altunay
1.0.1.1.4 | OSG Discovery tool | 2010-10-01 | 2011-09-30 | Roy, Altunay
1.0.1.2 | Continue interaction with OSG-catalyzed software | 2010-10-01 | 2011-09-30 | Roy, Altunay
1.0.1.2.1 | GUMS | 2010-10-01 | 2011-09-30 | Roy, Altunay
1.0.1.2.2 | Bestman | 2010-10-01 | 2011-09-30 | Roy, Altunay
1.0.1.2.3 | Gratia | 2010-10-01 | 2011-09-30 | Roy, Altunay
1.0.1.2.4 | PPDG Cert Scripts | 2010-10-01 | 2011-09-30 | Roy, Altunay
1.0.1.2.5 | GIP | 2010-10-01 | 2011-09-30 | Roy, Altunay
1.0.1.2.6 | OSG Matchmaker | 2010-10-01 | 2011-09-30 | Roy, Altunay
1.0.1.3 | Continune integration of software development best practices into STG-managed software | 2010-10-01 | 2011-09-30 | Roy, Altunay | 9
1.0.1.3.1 | Work with Bestman team to build and distribute from source | 2010-10-01 | 2011-09-30 | Roy, Altunay | 9
1.0.1.3.2 | Work with Bestman team to improve testing | 2010-10-01 | 2011-09-30 | Roy, Altunay
1.0.1.3.3 | Work with RSV team on improved testing | 2010-10-01 | 2011-09-30 | Roy, Altunay
1.0.1.3.4 | Work with GUMS team to build and distribute from source | 2010-10-01 | 2011-09-30 | Roy, Altunay
1.0.1.3.5 | Work with GUMS team to improve testing | 2010-10-01 | 2011-09-30 | Roy, Altunay
1.0.1.3.6 | Work with Gratia team on improved unit testing | 2010-10-01 | 2011-09-30 | Roy, Altunay
1.0.1.4 | Work with ET to find and divert STG-owned effort to starving projects, as needed | 2010-10-01 | 2011-09-30 | Roy, Altunay