## Slide 1: OSG Area Coordinators Meeting Security Team Report
Mine Altunay
4/11/2012

## Slide 2
 | WBS Ongoing Activities | 
1 | Incident response and vulnerability assessment | Minimizing the end-end response time to an incident, 1 day for a severe incident, 1 week for a moderate incident, and 1 month for a low-risk incient.
2 | Troubleshooting; processing security tickets including user requests, change requests from stakeholders, technical problems | Goal is to acknowledge tickets within one day of receipt.
3 | Maintaining security scripts (vdt-update-certs, vdt-ca-manage, cert-scripts, etc) | Maintain and provide bug fixes according to the severity of bugs. For urgent problems, provide an update in one week; For moderate severity, provide an update in a month; For low risk problems, provide an update in 6 months.
4 | Supporting OSG RA in processing certificate requests | Each certificate request is resolved within one week; requests for GridAdmin and RA Agents are served within 3 days.
5 | Preparing CA releases (IGTF), modifying OSG software as the changes in releases require | CA release for every two months
6 | Security Policy work with IGTF, TAGPMA, JSPG and EGI | Meet with IGTF and TAGPMA twice a year. Attend JSPG and EGI meteings remotely and face-face once a year. Track security policy changes and report to OSG management.
7 | Security Test and Controls | Execute all the controls included in the Security Plan and prepare a summary analysis.
8 | Weekly Security Team Meeting to review work items | Coordinate weekly work items.
9 | Weekly reporting to OSG-Production | Report important items that will affect production; incidents, vulnerabilities, changes to PKI infrastructure
10 | Monthly reporting to OSG-ET | Meet with ET once a month to discuss work items
11 | Quarterly reporting to Area Coordinator meeting | Meet with area coordinators to discuss work items.

## Slide 3: Ongoing Work: Operational Security
Software Vulnerabilities/Incidents
  Root level compromise at TTU. Affected all TTU machines, Glow pilot jobs and users (order of ten). Initial response happened within an hour of ticket creation. Affected users/services are contacted; attack contained within 24 hours. Attack vector unpatched ssh. Close-out summary sent to OSG ET.
  Software vulnerabilities: Voms-admin, Voms, Tomcat, Apache, MySQL, Java, telnetd, glibc, sudo, RH6, and condor vulnerabilities are assessed.
  A new Incident Drill is being prepared. Technical set up is completed. Identified Tier3s and sought agreement for participation. Will be conducted in May.

## Slide 4: Ongoing Work: Operational Security
XSEDE operational security interface
  Logistics are dealt with, joined the group, set up twiki accounts, PGP keys, etc.
  Calling into weekly Incident Response calls and biweekly Security Operations calls. The latter may be dropped if we find the former sufficient. Too early to tell.

## Slide 5: Ongoing Work: Operational Security
2. DOEGrids CA service outage
  Lasted for 30 hours. Lost ability to renew user certificates and obtain service certificates.
  Ran into issues in reporting tickets to ESNet NOC. Silent failure. Used GOC ticketing system to report to ESNet NOC. GOC had the incorrect email address for ESNet NOC. But the confirmation from GOC had the correct address that should have been sent to.
  GOC staff corrected the issue.
  We added an additional step in our process to reach Esnet NOC via phone for emergencies.
  Found workarounds to obtaining certificates, but that was not necessary due to fast response from DOEGrids.
  Requested an analysis for the cause of the issue. Nothing concrete to report yet.
  Services are restored back to normal.

## Slide 6: Ongoing Work: Operational Security
3. Maintaining security scripts. 6 separate issues since January 2012. 5 is closed. 1 is still open.
5. Two items
  DOEGrids CA certificate lifetime extension. DOEgrids has issued a new CA cert. We put a change request to disseminate the new Cert to end users. DOEGrids made the changes promptly: Put instructions and Linked the new cert to DOEGrids CA web pages; Put email reminders to end users. OSG cert request web pages also updated with instructions and the new Cert.
  CA release process update. CA rpm bundle is moved to the GOC software rpm cache. OLD rpm cache is still alive. Checked the sotes hitting the old rpm on 4/9/2012 , will contact them soon. Reminders that old cache will be turned off on 5/31/2012

## Slide 7: Ongoing Work: Operational Security
6. WLCG Risk Assessment, Worker Node risk assessment, and glexec evaluation documents are reviewed.
7. Security test and Controls: Planned to start in May. It will be finished before mid-July.
Prepared a live incident demo at OSG AHM. Created a vulnerable ssh daemon and demo how easily it can be broken into. Showed hands-on tips on how to strengthen ssh. Chose ssh due to past attack history.

## Slide 8: WBS Items
4 | Security |  |  |  | 
4.1 | Identity Management | Basney, Altunay |  |  | 
4.1.1 | Work Plan agreed by OSG Management and Security team | Basney, Altunay | 8/1/11 | 9/15/11 | Completed
4.1.2 | Integrate a UCSD VO with CILogon CA to utilize local resources | Basney, Altunay | 8/15/11 | 9/30/11 | Completed
4.1.3 | Integrate a VO with Cilogon CA which can submit jobs to OSG resources | Basney, Altunay | 9/16/11 | 12/30/11 | Completed
4.2 | Conduct Security Controls and Tests | Altunay, Slagell |  |  | 
4.2.1 | Execute the security controls in OSG Security Plan | Altunay, Slagell | 5/1/12 | 7/1/12 | 
4.2.2 | Prepare a report on findings from the Security Controls | Altunay, Slagell | 7/1/12 | 7/22/12 | 
4.3 | DigiCert Pilot Project | Altunay | 10/25/11 | 2/9/12 | ***new*** Completed
4.3.1 | DigiCert Planing Phase | Altunay | 2/9/12 | 3/31/12 | ***new*** in Jan 2012
4.4 | Evaluate and update CA release process | Altunay, Roy, Quick | 12/21/11 | 2/29/12 | ***new*** Completed
4.5 | Provide DES VO with guidance over Security Policies and Procedures | Altunay | 1/12/12 | 2/31/2012 | ***new*** Completed

## Slide 9: WBS Items
4.1.1, 4.1.2, and 4.1.3 are complete
4.1.4 replaced by Digicert Pilot.
DigiCert pilot is completed.
DigiCert Planning effort is continuing.
  Per ET’s recommendation, this item will be taken out of security team WBS although I personally contribute effort to.

## Slide 10: WBS Items
4.4. Evaluate and Update CA Release process. We have two separate processes for releasing CA bundles :
  Review and reconciliation of the processes by software, operations and security teams due before the end of 2/2012
  The work is completed in Feb.
  Announcement was sent out to the sites.
  Identified and contacted sites who used the old repo.
  Searched sites who are still using old repo on 4/9/2012. Will contact them again.
  The old RPM repo will be turned off 5/31.

## Slide 11: WBS Items
4.5 Provide DES VO with guidance over Security Policies and Procedures
  Per stakeholder’s request, this item is postponed (at least for 6 months). Revisit with the stakeholder at the end of August.
New Work Item:
  Making a list of prospective security projects. Collaborated with XSEDE and WLCG/EGI security teams. Ran it by Chander and Alain so far. After broader discussion in OSG, some items will be added to this list.

## Slide 12: Any Other Issues
Kevin Hill is a great asset. He is transitioning into OSG security officially on June 1st.
Marco will ramp down to zero.
Vacations coming up for the remainder of April.
  Mine will be gone 4/13 to 5/1
  Anand will be gone 4/12 to 5/7