## WBS
ID | WBS | TaskName | InCharge | Start | Finish | Percent
240 | 1.7 | Security | Altunay | 2010-08-02 08:00 | 2011-09-30 | 2%
241 | 1.7.1 | Operational Security | Altunay | 2010-10-01 08:00 | 2011-09-30 | 2%
242 | 1.7.1.1 | Incident Response and Prevention | Barlow | 2010-10-01 08:00 | 2011-09-30 | 100%
243 | 1.7.1.1.1 | Exchange information with other grid security teams. Participate in grid-sec, globus-sec and other email lists for possible threats, vulnerabilities | Barlow | 2010-10-01 08:00 | 2011-09-30 | 100%
244 | 1.7.1.1.2 | Perform vulnerability watch : check security bulletins, one team member each week | Altunay, Padmanabhan, Barlow, Sfiligoi | 2010-10-01 08:00 | 2011-09-30 | 100%
245 | 1.7.1.1.3 | Conduct an incident drill | Padmanabhan, Altunay | 2010-10-01 08:00 | 2011-03-15 | 0%
246 | 1.7.1.1.4 | ST&E controls, and review and update of Security Plan and Risk Assessment Plan | Altunay, Padmanabhan | 2010-10-01 08:00 | 2011-09-30 | 20%
247 | 1.7.1.2 | T3 Support | Barlow | 2010-10-01 08:00 | 2011-09-30 | 0%
248 | 1.7.1.2.1 | Continue support for T3s (T2 and T1 included when necessary) | Barlow | 2010-10-01 08:00 | 2011-09-30 | 0%
249 | 1.7.1.2.2 | Help transitioning the Pakiti service to GOC, when necessary help GOC with operational problems | Padmanabhan | 2010-10-01 08:00 | 2010-12-31 17:00 | 15%
250 | 1.7.1.2.3 | Monitor the results from Pakiti service, contact T3 admins when necessary | Barlow | 2010-10-01 08:00 | 2011-09-30 | 100%
251 | 1.7.1.3 | Continuous Operational Work | Altunay | 2010-10-01 08:00 | 2011-09-30 | 5%
252 | 1.7.1.3.1 | Prepare CA distribution packages, every two months | Padmanabhan, Altunay | 2010-10-01 08:00 | 2011-09-30 | 100%
253 | 1.7.1.3.2 | Run DOEgrids RA | Quick | 2010-10-01 08:00 | 2011-09-30 | 100%
254 | 1.7.1.3.3 | Maintain Security RSV probes | Padmanabhan | 2010-10-01 08:00 | 2011-09-30 | 100%
255 | 1.7.1.3.4 | Participate in IGTF, send comments to JSPG | Altunay | 2010-10-01 08:00 | 2011-09-30 | 100%
256 | 1.7.1.3.5 | Work on security tickets in GOC and VDT ticketing queue | Altunay | 2010-10-01 08:00 | 2011-09-30 | 0%
257 | 1.7.2 | Authentication and Identity Infrastructure | Altunay | 2010-10-01 08:00 | 2011-02-15 | 0%
258 | 1.7.2.1 | Test CILogon CA in OSG infrastructure. Setup a test Shib IdP to be tested with CILogon | Altunay, Padmanabhan | 2010-10-01 08:00 | 2010-12-15 | 75%
259 | 1.7.2.2 | Complete OSG identity roadmap. Advertise the recommendations from the roadmap to the user community. When useful, collaborate with Galois to enhance and complete the identity roadmap. | Altunay | 2010-10-01 08:00 | 2011-02-15 | 75%
260 | 1.7.3 | Virtualization technologies | Altunay | 2010-10-01 08:00 | 2011-09-30 | 0%
261 | 1.7.3.1 | Understand and discuss security needs of virtualization technologies and clouds | Altunay | 2010-10-01 08:00 | 2011-09-30 | 0%
262 | 1.7.5 | Training, Education and Documentation | Sfiligoi, Barlow | 2010-08-02 08:00 | 2011-08-31 | 0%
263 | 1.7.5.1 | Prepare how-to guides for sites and users | Sfiligoi | 2010-08-02 08:00 | 2011-08-31 | 0%
264 | 1.7.5.2 | How to securely configure and install VDT (including non-security software) | Sfiligoi | 2010-08-02 08:00 | 2011-08-31 | 0%
265 | 1.7.5.3 | How to operate a site securely (for site admins, day-day tasks, how to register with OIM, read security advisories, check security team’s signatures, etc) | Sfiligoi | 2010-08-02 08:00 | 2011-08-31 | 0%
266 | 1.7.5.4 | How to access OSG for end user (get cert, import into a browser, renew, register with VOMS, etc) | Sfiligoi | 2010-08-02 08:00 | 2011-08-31 | 0%
267 | 1.7.5.5 | Help with completing documentation project | Barlow, Padmanabhan, Sfiligoi, Altunay | 2010-10-01 08:00 | 2010-10-01 17:00 | 100%
Future-Must
Comments from Joe: bring up the security controls discussion at next meeting. CA outages and CRL caches should be discussed more. Cas should have their own compromise plans. Controls at 1.7.1 are really important. Cilogon test is open to discussion. Pakiti service's future can be aligned with Fermilab operations Bring it up at next Ruth's meeting

## Task List
Completed Items since the last meeting. Color blue represents items that has been added after our last meeting
Type | Priority | WBS | Description | Priority | comments | Active | Start | Finish | Requestor | Effort Estimate | Reports/Comments | SME
Operations | Must | 1.7.5 | Preparation for AHM | 1 | Education/Training | Complete
Operations | Must | 1.7.1.1.2 | SSL renegotiation vulnerability at GOC twiki | 1 | Vulnerability/Response | Complete | 2011-03-10 | 2011-03-22 | Security Team | 0.2
Operations | Must | 1.7.1.1.2 | Dcache vulnerability initial response. Follow up item is listed below | 1 |  | Complete | 23/3/2011 | 2011-03-25 | Security Team
Operations | Must | 1.7.1 | Japanese CA outage -- initial response. Other work items sprung up from this work is listed below | 1 | Operations/Availability | Complete | 2011-03-11 | 2011-03-14 | Security team | 1
Operations | Must | 1.7.1 | Test how incident alerts/reports are dispatched and processed-- problems identified during the test are listed as work items below | 1 (1) | ST&E | Complete | 2010-10-01 | 2011-03-21 | Security Team | 0.3 | Changes to the processes have been completed. WE still have not tested whether the changes are implemented correctly | Barlow
Operations | Must | 1.7.1.3.5 | Run-time problems with Host Certificates. Ask CA to identify other users with similar cert problems | 2 |  | Complete | 2011-03-14 | 21/3/2011 | Site complaints | 0.2 |  | Mine
NewCap | Want | 1.7.1.3.5 | Dzero GUMS feature request---passed onto GUMS team | 4 |  | Complete | 2011-03-07 | 2011-03-15 | VO complaints | 0.1
Items that are either in progress or been requested. Color blue represents items that has been added after our last meeting
Operations | Must | 1.7.1.1.2 | Dcache vulnerability. Follow-up with sites whether they have follow the patching instructions | 1 | Vulnerability/Incident Response | y | 2011-03-23 | 2011-04-08 |  | 0.25
Operations | Must | 1.7.1.1.2 | Glexec vulnerability | 1 | Vulnerability | y | 2011-03-10 | 2011-04-08 |  | 0.1
Operations | Must | 1.7.1.1.4 | Security Test and Controls. Includes updating the Risk assessment document | 1 (1) | ST&E | n |  | 2011-08-15 | Security Team | 1 | https://twiki.grid.iu.edu/bin/view/Security/ControlsAssessment2010 | Mine & Anand
NewCap | Must | 1.7.1.2 | Security controls dashboard | 1 (5) | ST&E | n |  |  | Ruth |  | Requested on 3/14/2011 | Mine
Operations | Must | 1.7.1 | Watching site vulnerability status/Incident Response/Communication with EGI/TG security teams | 1 |  | y | Continuous |  | Security Team | 0.3 |  | Barlow
Operations | Must | 1.7.1 | Work with GOC to send the incident emails to incident-report-l. All other security tickets will be sent to Security support center. Test if the changes effectively in place | 1 (1) | ST&E | y | 2010-10-01 | Ask Rob if this date can be met 4/25/2011 | Security Team | 0.3 | Changes to the processes have been completed. WE still have not tested whether the changes are implemented correctly | Barlow
Operations | Must | 1.7.1 | Make a test how many security contacts can check pgp keys and read security team emails securely. Update documentation | 1 (3) | ST&E | n |  | 2011-04-30 | Security Team | 0.3 |  | Barlow
Operations | Must | 1.7.1.1.3 | Conduct an incident drill | 1 (1) | ST&E | n |  |  | Security Team |  |  | Padmanabhan, Altunay
NewCap | Must | 1.7.1.3.1 | Test the new certifcate layout in production. Find fall back mechanisms to produce the certificates until the tests conclude | 1 |  | y | 2011-03-08 | 2011-04-30 | Security Team | 0.4 | Anand was on vacation for 4 weeks and had visa troubles for 3-4 weeks after that. | Anand
NewCap | Must | 1.7.1.3.2 | Create documentation for RA processes. Train back up personnel at GOC | 2 |  | y | 2011-01-15 | 2011-04-15 | Miron/Ruth | 0.1 | https://twiki.grid.iu.edu/bin/view/Security/OsgRaAgents#Approving_renewing_Agents | Alain D
Operations | Must | 1.7.1.3.2 | Hold meetings with Ra Agents to go over processes, explore if there are any problems. | 1 (4) | ST&E | n |  | 2011-04-15 |  |  |  | Alain D and Mine
NewCap | Must | 1.7.1 | A checklist for site admins to follow after reporting the incident. | 1 (2) | ST&E | y | 2010-09-09 | 2011-04-15 | Security Team | 0.1 | The checklist exists at https://twiki.grid.iu.edu/bin/view/ReleaseDocumentation/IncidentFirstStepsThe list should be sent to the admin after opening the ticket. should we link this page to the GOC ticket submission web page? OR can we include this link in the confirmation email sent by GOC after the ticket is submitted? | Barlow
Operations | Must | 1.7.1.3.5 | Operations questions/inquiries/Customer Service | 4 (variable) | GOC | y | Continuous
Operations | Must | 1.7.1.3.4 | Policy work with EGI, TG, WLCG | 4 (variable) |  | y | Continuous |  | WLCG | 0.1 | The group will present at OGF | Mine & Barlow
Operations | Must | 1.7.1.2 | Weekly security calls with tier3 sites. Finish going over all sites in a year. Write an impact statement on the work item | 5 | Move to group conf call | n |  |  | Ruth |  | Requested on 3/15/2011 | Barlow
NewCap | Must | 1.7.1.3.3 and 1.7.1.3.1 | Test the code against the openssl 1.0. Contingent upon #32 | 5 |  | n |  |  | Security Team | 0.5 | https://twiki.grid.iu.edu/bin/view/Security/IGTFNewLayoutCodeChanges. The changes for the openssl v 0.9 is complete and relesed at 10/19/2010. Changes necessary for openssl 1.0 is postponed until our community start switching to the new libraries. I will re-visit this item and deliver the remaining changes by 8/31/2011 | Anand
NewCap | Must | 1.7.1 | Evaluate the impact of switching to Openssl 1.0 | 5 |  | n |  |  | Security Team |  | This is important to understand. Openssl has released v 1.0 while ago. Currently no OS vendors have switched their versioning. But eventually they will | Mine and Anand
Operations | Want | 1.7.1.1 | Sbgrid requested an evaluation of their authentication portal | 2 |  | n |  |  | Sbgrid |  | Requested on 3/15/2011 | Mine
Operations | Want | 1.7.1.1 | xrootd requested an evaluation of their authentication framework | 2 |  | n |  |  | Rob Gardner |  | Requested on 3/15/2011 | Anand
NewCap | Want | 1.7.1.2.2 | Vulnerability Assessment/Enumeration (e.g. Move Pakiti service to Production) | 3 |  | n |  | 2011-05-15 | WLCG | 0.2 | The person who runs the service is leaving ncsa. | Anand
NewCap | Want | 1.7.1.3.2 | Changes in the RA software run by DOEGrids CA | 4 |  | n |  | 2011-06-01 | DOEGrids CA | 0.2 |  | Alain D and Mine
NewCap | Want | 1.7.5 | Creating User Support Documentation for X.509 Certificates. Requesting, retrieving, obtaining, renewing, etc… | 5 |  | y | 2010-12-10 | 1931-04-01 | SBGrid initial requestor. Other Vos also like this request | 0.2 | Smaller scoped version for SBGrid will be finished 3/31/2011. | Marko Slyz
NewCap | Want | 1.7.5 | Create a website on OSG-WLCG interoperability as it relates to security | 5 |  | n |  |  | requested on 11/29/2010 need to get some updates. | 0.1 |  | Barlow
NewCap | Want | 1.7.2.2 | Announce the new certificate request page to VOs, collect feedback | 5 |  | y | 2010-12-20 | 2011-05-01 | Miron/Ruth | 0.1 | https://twiki.grid.iu.edu/bin/view/Security/CertificateDocumentationUsability. Continue this item until we finsihed addressing the needs | Marko Slyz
NewCap | Want | 1.7.2.1 | CILogon pilot test | 5 |  | n | 2011-02-04 | 2011-04-15 | Stakeholder request | 0.4 | https://twiki.grid.iu.edu/bin/view/Security/CiLogonPilot2010 | Mine
NewCap | Want |  | Create a joint identity roadmap document with ESNet | 5 |  | y | 2010-12-15 |  | Ruth | 0.1 |  | Mine
NewCap | Want | 1.7.2.2 | Address the VO requests on new certificate page. One stakeholder is Atlas. | 5 |  | n |  |  | Security Team | 0.3 |  | Anand-- needs to look at
NewCap | Want | 1.7.1.3.2 | Integrate RA certificate requests into GOC ticketing system | 5 |  | n |  |  | Security Team |  | Investigation of how much effort is needed. | Mine and Alain D
NewCap | Want | 1.7.2 | CERN ID mgmt meeting. explore the requirements for federated identity management across the different disciplines, compare the functionality, operational constraints and state of deployment of current technologies, and formulate a roadmap for how we could establish such a service in the future | 5 |  | n |  |  | WLCG/Stakeholders |  |  | Mine
NewCap | Want | 1.7.2 | Run a centralized OSG Registration Service | 5 |  | n |  |  | Miron |  | Requested on 1/22/2011 | Mine
NewCap | Want |  | Propose a central CRL cache for sites | 5 |  | n |  |  | Miron |  | Requested on 3/12/2011
NewCap | Want |  | CILogon project: engage another lab and a non-lab community. Announce the results of the risk assessment | 5 |  | n |  |  | Ruth |  | Requested on 3/14/2011
NewCap | Want |  | fetch-crl latest version release | 5 |  | n |  |  | Steve Timm
NewCap | Want |  | cert-request scripts feature addition | 5 |  | n |  |  | Sbgrid
Operations | Want |  | Generate metrics on RA request processing | 5 |  | n |  |  | Ruth |  | Requested on 3/16/2011

## Sheet2
Completed items
Operations | Must | Glexec vulnerability, SSL renegotiation vulnerability at GOC twiki | Mine | y | 2011-03-10 | 2011-03-22 | Security Team | 0.2