## Sheet1
WBS | TaskName | InCharge | Start | Finish
1.8 | Content Management | Engel | 2010-10-01 | 2011-09-30
1.8.1 | Staff and Contributor Coordination and Delivery
1.8.1.1 | Run weekly meetings to review, plan and discuss documentation activities | Engel, Document Area Coordinators. | 2010-10-01 | 2011-09-30 | changed from biweekly to weekly
1.8.1.2 | Continue to help document area coordinators with the infrastructure and delivery of documents | Engel, Document Area Coordinators. | 2010-10-01 | 2011-09-30
1.8.1.3 | Provide Training for Document Area Coordinators | Engel | 2010-10-01 | 2010-11-01 | as part of the weekly telecons
1.8.1.4 | Identify owners for each documentation area | Engel | 2010-10-01 | 2011-09-30 | Iwona to own CE, Suchandra to own Integration
1.8.2 | Content Management Infrastructure | Engel
1.8.2.1 | Evolve standards and templates for documents | Engel | 2010-10-01 | 2011-09-30
1.8.2.2 | Complete testing an effective "user" search for Documentation | Engel | 2010-10-01 | 2010-12-15 | Done for the purpose of Document Area Coordinators.
1.8.2.3 | Get all Documentation into new process | Engel | 2010-10-01 | 2011-04-01
1.8.2.4 | Participate planning support for new content management infrastructure for OSG Prime | Engel | 2010-10-01 | 2011-02-15
1.8.2.5 | Provide effective navigation | Engel | 2010-10-01 | 2011-01-15 | I need some support here, Tim is most knowledgable
1.8.2.6 | Provide Collaborative Document Rating for Twiki | Cartwright | 2010-10-01 | 2011-04-01
1.8.2.7 | Migrate Twiki to dedicated hardware | Quick | 2010-10-01 | 2010-12-01 | a dedicated multicore system where the Twiki data is provided on a solid state disk
1.8.2.8 | Complete Review and Test of Documentation under Content Mgmt Control, Provide Release | Engel | 2010-10-01 | 2011-04-01
1.8.2.8.1 | Tier3 : 22 Documents | Mambelli | 2010-09-01 | 2010-11-30
1.8.2.8.2 | User : 17 Documents | Bockelman | 2010-09-01 | 2010-11-30
1.8.2.8.3 | Storage : 69 Documents | Levshina, Hesselroth | 2010-09-01 | 2010-11-30
1.8.2.8.4 | Compute Element : 68 Documents | Sakrejda | 2010-09-01 | 2010-11-30
1.8.2.8.5 | Integration : 25 Documents | Thapa | 2010-09-01 | 2010-11-30
1.8.2.8.6 | Security : 40 Documents | Barlow | 2010-09-01 | 2010-11-30
1.8.2.8.7 | Virtual Organizations : 23 | Rana | 2010-09-01 | 2010-11-30
1.8.2.9 | Integrate Document Release Process into OSG Software Release Process | Engel, Thapa | 2011-04-01 | 2011-09-30 | in the sense that documentation issues to be discussed prior a software release
1.8.2.10 | Evaluate Documentation Imrovements | Engel | 2010-04-01 | 2011-09-30 | Google Analytics, Document Ratings, User Comments